## Sheet1
S.NO | Client Name | Project Name | Servicelines |  | PFM | PM | Current Status | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date |  | How likely are you to recommend COWI to others within your field? | How satisfied are you with the quality of the services we provide? | How satisfied are you with our ability to deliver at the agreed price? | How satisfied are you with our ability to deliver on the agreed time? | How satisfied are you with the project manager’s ability to identify with your situation and needs?
| Client Name | Project_Name | Servicelines | Service line count | PFM | PM | Current Status | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Cust_resp_days | NPS | Quality_score | Cost_score | Time_score | PM_score | Total Deliveries | Delays | Quality_feedback_on_delivery
4 | BSF-SPNO | 5 projects | AT/Vector/Ortho | 3 | MADV | MNJA | In Progress | 2017-12-13 | 2017-12-13 | 0 | 9 | 8 | 9.5 | 8 | 10 | 7 | 0 | 1
5 | Digital Globe | Nigeria Oil Theft Analysis - July | 2D | 1 | MADV | MNJA | Closed | 2017-09-13 | 2017-09-13 | 0 | 9 | 8 | 10 | 9 | 9 | 9 | 0 | 2
12 | FIRST BASE SOLUTION | 1737 DURH & 1737 HALT | Vector | 1 | NSPI | MVRA | Closed | 2017-10-10 | 2017-12-14 | 65 | 8 | 7 | 8 | 8 | 8 | 5 | 0 | 2
14 | VANSTEELANDT | GRB | Vector | 1 | MADV | MVRA | In Progress | 2017-10-12 | 2017-10-12 | 0 | 7 | 7 | 10 | 9 | 8 | 39 | 0 | 4
15 | BSF-SWISSPHOTO | M7016 DOP Luzern 2017 | Ortho | 1 | MADV | MVRA | Closed | 2017-12-07 | 2017-12-14 | 7 | 9 | 9 | 8 | 10 | 10 | 35 | 0 | 32
16 | XEOS Imaging | PR2572 | LiDAR | 1 | NSPI | MVRA | Closed | 2017-12-07 | 2017-12-15 | 8 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0
17 | BSF-SWISSPHOTO | DOP NL B06 & B10 | AT / Ortho | 2 | MADV | MVRA | Closed | 2017-09-15 | 2017-09-24 | 9 | 8 | 9 | 8 | 8 | 10 | 35 | 0 | 32
18 | XEOS Imaging | PR2341 | LiDAR | 1 | NSPI | MVRA | Closed | 2017-12-07 | 2017-12-14 | 7 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0
21 | BSF-SWISSPHOTO | Trelleborg | AT / Ortho | 2 | MADV | AISR | Closed | 2017-09-14 | 2017-10-09 | 25 | 9 | 9 | 9 | 8 | 10 | 35 | 0 | 32
22 | FIRST BASE SOLUTION | Ottawa | AT / Ortho | 2 | NSPI | AISR | Closed |  | Received | 14 | 5 | 6 | 5 | 8 | 4 | 5 | 0 | 2
23 | Topocart | CE/SCS | Vector | 1 | MADV | SKCY | Closed | 2017-10-12 | 2017-11-09 | 28 | 8 | 8 | 7 | 7 | 9 | 38 | 0 | 20
24 | ROSSI | RIM-5K mapping/1K Mapping | Vector | 1 | MADV | SKCY | Closed | 2017-10-31 | 2017-11-02 | 2 | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 4
26 | BSF-Swissphoto-AG | BW 2017 | LiDAR | 1 | MADV | NSPI | Closed | 2017-09-14 | 2017-09-15 | 1 | 7 | 7 | 6 | 10 | 9 | 9 | 0 | 5
43 | FIRST BASE SOLUTION | 1737ESSX | Vector | 1 | NSPI | RRKN | Closed | 2017-12-12 | 2017-12-14 | 2 | 8 | 7 | 8 | 8 | 8 | 5 | 0 | 2
2 | Fmaps | Fmaps - Various Jobs of AT & DTM | AT/Vector | 2 | MADV | RRKN | Closed | 2018-03-09 | 2018-03-27 | 18 | 8 | 9 | 10 | 8 | 9 | 15 | 0 | 4
3 | IBV KRANK | Project 2017-1 | LiDAR | 1 | MADV | MVRA | In Progress | 2018-03-19 | 2018-03-19 | 0 | 8.5 | 8 | 9 | 8 | 9 | 5 | 0 | 6
4 | XEOS | PR2341 | LiDAR | 1 | RASA | MVRA | Closed | 2018-03-19 | 2018-03-19 | 0 | 9 | 10 | 10 | 9 | 10 | 3 | 0 | 2
7 | Veris | Cranbrook | Vector | 1 | MADV | RRKN | Closed | 2018-03-19 | 2018-03-21 | 2 | 5 | 5 | 5 | 7 | 6 | 5 | 0 | 1
8 | CAS | AT, Vector | Vector/AT | 2 | RASA | SKCY | In Progress | 2018-03-22 | 2018-04-17 | 26 | 10 | 10 | 10 | 10 | 10 | 147 | 3 | 2
11 | Topocart | UR-Project | Vector | 1 | MADV | SKCY | In Progress | 2018-03-22 | 2018-04-30 | 39 | 7 | 7 | 6 | 7 | 9 | 52 | 0 | 25
12 | Geoconsult | OMAN | AT/Vector | 2 | MADV | MNJA | Closed | 2018-02-28 | 2018-03-06 | 6 | 8 | 9 | 5 | 7.5 | 10 | 4 | 0 | 0
13 | BSF-SPNO | 5 projects | AT/Vector/Ortho | 3 | MADV | MNJA | Delivered | 2018-03-19 | 2018-04-10 | 22 | 9 | 9 | 9 | 9 | 10 | 14 | 0 | 2
18 | Namibia | Namibia -2016 | 2DGIS | 1 | MADV | MYPZ | Closed | 2018-03-20 | 2018-04-24 | 35 | 6 | 6 | 5 | 6 | 5 | 74 | 0 | 50

## CSS
year | client_name | project_name | servicelines | service_line_count | pfm | pm | current_status | css_sent_date | css_feedback_receipt_date | cust_resp_days | customer_type | nps | quality_score | cost_score | time_score | pm_score | total_deliveries | delayed_deliveries | quality_feedback
2017 | BSF-SPNO | 5 projects | AT/Vector/Ortho | 3 | MADV | MNJA | In Progress | 2017-12-13 | 2017-12-13 | 0 | Promoter | 9 | 8 | 9.5 | 8 | 10 | 7 | 0 | 1
2017 | Digital Globe | Nigeria Oil Theft Analysis - July | 2D | 1 | MADV | MNJA | Closed | 2017-09-13 | 2017-09-13 | 0 | Promoter | 9 | 8 | 10 | 9 | 9 | 9 | 0 | 2
2017 | FIRST BASE SOLUTION | 1737 DURH & 1737 HALT | Vector | 1 | NSPI | MVRA | Closed | 2017-10-10 | 2017-12-14 | 65 | Passive | 8 | 7 | 8 | 8 | 8 | 5 | 0 | 2
2017 | VANSTEELANDT | GRB | Vector | 1 | MADV | MVRA | In Progress | 2017-10-12 | 2017-10-12 | 0 | Detractors | 7 | 7 | 10 | 9 | 8 | 39 | 0 | 4
2017 | BSF-SWISSPHOTO | M7016 DOP Luzern 2017 | Ortho | 1 | MADV | MVRA | Closed | 2017-12-07 | 2017-12-14 | 7 | Promoter | 9 | 9 | 8 | 10 | 10 | 35 | 0 | 32
2017 | XEOS | PR2572 | LiDAR | 1 | NSPI | MVRA | Closed | 2017-12-07 | 2017-12-15 | 8 | Promoter | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0
2017 | BSF-SWISSPHOTO | DOP NL B06 & B10 | AT/Ortho | 2 | MADV | MVRA | Closed | 2017-09-15 | 2017-09-24 | 9 | Passive | 8 | 9 | 8 | 8 | 10 | 35 | 0 | 32
2017 | XEOS Imaging | PR2341 | LiDAR | 1 | NSPI | MVRA | Closed | 2017-12-07 | 2017-12-14 | 7 | Promoter | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0
2017 | BSF-SWISSPHOTO | Trelleborg | AT/Ortho | 2 | MADV | AISR | Closed | 2017-09-14 | 2017-10-09 | 25 | Promoter | 9 | 9 | 9 | 8 | 10 | 35 | 0 | 32
2017 | FIRST BASE SOLUTION | Ottawa | AT/Ortho | 2 | NSPI | AISR | Closed |  |  | 14 | Detractors | 5 | 6 | 5 | 8 | 4 | 5 | 0 | 2
2017 | Topocart | CE/SCS | Vector | 1 | MADV | SKCY | Closed | 2017-10-12 | 2017-11-09 | 28 | Passive | 8 | 8 | 7 | 7 | 9 | 38 | 0 | 20
2017 | ROSSI | RIM-5K mapping/1K Mapping | Vector | 1 | MADV | SKCY | Closed | 2017-10-31 | 2017-11-02 | 2 | Passive | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 4
2017 | BSF-Swissphoto | BW 2017 | LiDAR | 1 | MADV | NSPI | Closed | 2017-09-14 | 2017-09-15 | 1 | Detractors | 7 | 7 | 6 | 10 | 9 | 9 | 0 | 5
2017 | FIRST BASE SOLUTION | 1737ESSX | Vector | 1 | NSPI | RRKN | Closed | 2017-12-12 | 2017-12-14 | 2 | Passive | 8 | 7 | 8 | 8 | 8 | 5 | 0 | 2
2018 | Fmaps | Fmaps - Various Jobs of AT & DTM | AT/Vector | 2 | MADV | RRKN | Closed | 2018-03-09 | 2018-03-27 | 18 | Passive | 8 | 9 | 10 | 8 | 9 | 15 | 0 | 4
2018 | IBV KRANK | Project 2017-1 | LiDAR | 1 | MADV | MVRA | In Progress | 2018-03-19 | 2018-03-19 | 0 | Promoter | 8.5 | 8 | 9 | 8 | 9 | 5 | 0 | 6
2018 | XEOS | PR2341 | LiDAR | 1 | RASA | MVRA | Closed | 2018-03-19 | 2018-03-19 | 0 | Promoter | 9 | 10 | 10 | 9 | 10 | 3 | 0 | 2
2018 | Veris | Cranbrook | Vector | 1 | MADV | RRKN | Closed | 2018-03-19 | 2018-03-21 | 2 | Detractors | 5 | 5 | 5 | 7 | 6 | 5 | 0 | 1
2018 | CAS | AT, Vector | AT/Vector | 2 | RASA | SKCY | In Progress | 2018-03-22 | 2018-04-17 | 26 | Promoter | 10 | 10 | 10 | 10 | 10 | 147 | 3 | 2
2018 | Topocart | UR-Project | Vector | 1 | MADV | SKCY | In Progress | 2018-03-22 | 2018-04-30 | 39 | Detractors | 7 | 7 | 6 | 7 | 9 | 52 | 0 | 25
2018 | Geoconsult | OMAN | AT/Vector | 2 | MADV | MNJA | Closed | 2018-02-28 | 2018-03-06 | 6 | Passive | 8 | 9 | 5 | 7.5 | 10 | 4 | 0 | 0
2018 | BSF-SPNO | 5 projects | AT/Vector/Ortho | 3 | MADV | MNJA | Delivered | 2018-03-19 | 2018-04-10 | 22 | Promoter | 9 | 9 | 9 | 9 | 10 | 14 | 0 | 2
2018 | Namibia | Namibia -2016 | 2DGIS | 1 | MADV | MYPZ | Closed | 2018-03-20 | 2018-04-24 | 35 | Detractors | 6 | 6 | 5 | 6 | 5 | 74 | 0 | 50

## Sheet3
2018-04-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable Hours | Remaining Billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Input/Output Register | Project Handover Date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) - (AE + AF + AG) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM | Client Name
2018-04-01 | 1 | Topocart | UR-10K | Vector | MADV | SKCY | 19709 | 18798 | 911 | 4000 |  | 2018-04-27 | 2018-06-15 | 2018-03-07 |  | Yes | 2018-02-08 | YES | YES | Yes | PO | Yes | To be invoiced | In progress |  | 2018-03-21 | 2018-04-30 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-30 | Client Name
2018-04-01 | 2 | CAS | CAS-AT, Ortho, Vector | Vector/AT/Ortho | RASA | SKCY | 9737 | 9737 | 0 | 1322 |  | 2018-04-30 |  | 2018-04-30 |  | YES | NA | YES | 2017-01-15 | 2017-01-15 | WO | Yes | Monthly Invoice | In progress |  | 2018-03-21 | 2018-04-17 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-30 | BSF-SPNO
2018-04-01 | 3 | Topocart | UR-1K | Vector | MADV | SKCY | 2628 | 2628 | 0 | 0 |  | 2018-01-29 |  | 2018-01-30 |  | Yes | 2017-11-28 | 2017-11-08 | 2018-01-10 | 2018-01-11 | PO | Yes | To be invoiced | Delivered |  |  |  | 0 | 0 | 6 | 6 | 0 | 0 | 0 |  | 2018-04-30 | Digital Globe
2018-04-01 | 4 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 136 | 0 | 2017-11-28 |  | 2017-12-21 |  | YES | 2018-01-23 | 2018-01-19 | 2018-01-22 | 2018-01-23 | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | * Feature Geometry Updation Complete, awaiting attribute update guideline to complete the project. | 2018-04-09 | FIRST BASE SOLUTION
2018-04-01 | 5 | GROUPE DEGAUDE | SNCF Amberieu railway station | LiDAR | MADV | RRKN | 48 | 48 | 0 |  |  | 2018-03-21 | 2018-03-26 | 2018-03-21 | 2018-03-23 |  | 2018-03-21 |  |  |  | Signed QS | NA | Invoiced | Delivered |  |  |  | 2 |  | 4 | 2 |  |  |  |  | 2018-04-09 | VANSTEELANDT
2018-04-01 | 6 | GROUPE DEGAUDE | Le Memont | LiDAR | MADV | RRKN | 2.7 | 0 | 2.7 |  |  |  | 2018-03-15 | [10 empty] | To be started | [10 empty] | Expected in 3rd week of March | 2018-04-09 | BSF-SWISSPHOTO
2018-04-01 | 7 | Rossi | Schio 2K Mapping | Vector | MADV | RRKN | 2048 | 2048 | 0 |  |  | 2018-03-05 |  | 2018-03-05 | 2018-03-12 | YES | 2018-03-07 | 2018-03-19 | 2018-03-22 | 2018-03-07 | Signed QS | YES |  | In progress |  |  |  | 4 | 1 | 5 | 5 |  |  |  |  | 2018-04-09 | XEOS Imaging
2018-04-01 | 8 | COWI AS | OSGB_Urban_2017_19 | Vector | MADV | RASA | 114019 | 114019 | 0 |  | 0 | 2018-03-15 |  | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-06 | BSF-SWISSPHOTO
2018-04-01 | 9 | COWI AS | OSGB_Rular_2017_19 | Vector | MADV | RASA | 52069 | 51469 | 0 |  |  |  |  | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | XEOS Imaging
2018-04-01 | 10 | COWI AS | NCR Pilot | Vector | MADV | RASA | 1848 | 1848 | 0 | 0 | 0 |  |  |  |  | YES | [7 empty] | In progress | [12 empty] | BSF-SWISSPHOTO
2018-04-01 | 11 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6714 | 6714 | 0 | 0 | 0 | 2017-08-25 |  | 2017-08-25 |  | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 | Signed QS | YES | To be invoiced | Delivered | 2018-04-13 | 2018-03-19 | 2018-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FIRST BASE SOLUTION
2018-04-01 | 12 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6714 | 4838 | 1876 | 2000 | 0 | 2017-12-01 | 2018-08-01 | 2017-12-01 |  | YES | YES | 2017-12-05 | 2017-12-05 | 2017-12-05 | Signed QS | YES | To be invoiced | In progress | 2018-04-13 | 2018-03-19 | 2018-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Topocart
2018-04-01 | 13 | ASI | Saylorville_Mapping | Vector | MADV | SUHH | 100 | 100 | 0 | 100 | 0 | 2018-04-09 |  |  |  | YES |  |  |  |  | Signed QS |  | To be invoiced | Delivered | [11 empty] | 2018-04-18 | ROSSI
2018-04-01 | 14 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6655 | 6189 | 466 | 513 | 0 | 2018-03-26 | 2018-05-07 |  |  | YES |  |  | 2017-08-10 |  | Signed QS | YES | To be invoiced | In progress |  | 2018-03-19 | 2018-03-19 | 2 | 0 | 5 | 5 | 0 | 0 | 0 |  | 2018-05-06 | BSF-Swissphoto-AG
2018-04-01 | 15 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 2284 | 2284 | 0 | 582 | 0 | 2018-03-09 |  | 2018-03-14 |  | YES |  |  |  |  | Signed QS | YES | Monthly Invoice | In progress |  | 2018-03-19 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06 | FIRST BASE SOLUTION
2018-04-01 | 16 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 4063 | 1967.1 | 2095.9 | 782 | 0 | 2018-01-29 | 2018-05-04 | 2018-01-29 |  | YES |  |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | Received inputs - Block_01 40 CM & Mpigi - 15CM | 2018-05-06 | Fmaps
2018-04-01 | 17 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1526 | 1526 | 0 | 1050 | 0 | 2017-12-26 |  | 2018-01-02 |  | YES | 2018-02-19 | 2018-02-13 |  |  | WO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06 | IBV KRANK
2018-04-01 | 18 | Langan | Piscataway | AT/Vector/Ortho | RASA | MVRA | 50 | 50 | 0 | 50 | 0 | 2018-02-22 |  | 2018-02-22 |  | YES |  | 2018-02-28 |  |  | No | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06 | XEOS Imaging
2018-04-01 | 19 | COWI AS | HxIP | Ortho | MADV | KSAB | 9867 | 6699 | 3168 | 176 | 3168 | 2018-04-19 | 2018-04-26 | 2017-12-18 |  | YES |  | 2017-07-13 | 2017-07-13 | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 14 | 14 | 0 | 0 | 0 |  | 2018-05-07 | Veris
2018-04-01 | 20 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 11219 | 10697 | 522 | 2971 | 1540 | 2018-04-28 | 2018-04-30 |  |  | YES |  | 2017-07-13 |  | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 3 | 0 | 17 | 17 | 0 | 0 | 0 |  | 2018-05-07 | CAS
2018-04-01 | 21 | Langan | Middletown | AT/Vector/Ortho | RASA | MVRA | 85 | 85 | 0 | 85 | 0 | 2018-03-07 |  | 2018-03-08 |  | YES |  |  |  |  | Signed QS | YES | To be invoiced | Delivered |  | 2018-03-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Need to submit the revised QS as there is an increment in image count | 2018-05-06 | Topocart
2018-04-01 | 22 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 2500 | 5442 | 2017-11-20 |  | 2017-11-21 |  | YES | 2017-11-14 | 2017-11-07 | 2017-12-21 | 2017-12-18 | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3D engine Tool availability by EOW- WK-16 | 2018-04-03 | Geoconsult
2018-04-01 | 23 | COWI AS | OSGB_Urban_2018_19 | Vector | MADV | RASA | 49690 | 8889 | 40801 | 8000 | [5 empty] | YES |  |  |  |  | ATR |  | Monthly Invoice | In progress | [11 empty] | 2018-03-23 | BSF-SPNO
2018-04-01 | 24 | COWI AS | OSGB_Rular_2018_19 | Vector | MADV | RASA | 44160 | 2905 | 41255 | 2200 | [5 empty] | YES |  |  |  |  | ATR |  | Monthly Invoice | In progress | [11 empty] | 2018-03-23 | Namibia
2018-04-01 | 25 | Opsia | GC170269_Hauts de France - Valenciennes | LiDAR | MADV | RRKN | 122 | 122 | 0 | 122 |  | 2018-03-21 |  | 2018-03-21 | 2018-03-21 | YES | 2018-03-21 | 2018-03-24 | 2018-03-29 |  | Signed QS |  | Invoiced | Delivered |  |  |  | 1 |  | 1 | [5 empty] | 2018-04-09
2018-04-01 | 26 | IBV KRANK | PROJECT 2018-1 | LiDAR | MADV | MVRA | 2200 | 0 | 2200 | 0 | 2200 |  | 2018-05-15 |  |  | NO |  |  |  |  | No | NO | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 27 | XEOS | PR2705 | LiDAR | RASA | MVRA | 240 | 0 | 200 | 0 | 200 |  | 2018-05-15 |  |  | NO |  |  |  |  | No | NO | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 28 | BSF Swissphoto | BSF NL 2018 | Ortho | MADV | MVRA | 3000 | 0 | 3000 | 0 | 3000 |  | 2018-05-07 |  |  | NO |  |  |  |  | No | NO | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 29 | BSF Swissphoto | BW LiDAR | LiDAR | MADV | RASA | 4100 | 0 | 4100 | 0 | 4100 |  | 2018-05-15 | [9 empty] | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-19
2018-04-01 | 30 | Langan | Franciscan University | AT/Vector/Ortho | RASA | MVRA | 243 | 243 | 0 | 243 | 0 | 2018-03-21 |  | 2018-03-21 |  | YES |  | 2018-03-21 |  |  | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 31 | Opsia | Cedex_BD500 | Vector | MADV | RRKN | 90 | 90 | 0 | 0 |  | 2018-03-20 | [8 empty] | Signed QS |  | To be invoiced | Delivered | [5 empty] | 2 | 1 | 1 |  |  |  | 2018-04-09
2018-04-01 | 32 | Rossi | Schio 5K Mapping | Vector | MADV | RRKN | 770 | 770 | 0 | 770 |  | 2018-03-05 |  | 2018-03-05 | 2018-03-23 |  | 2018-03-26 |  |  |  | Signed QS |  |  | In progress |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 2018-04-09
2018-04-01 | 33 | COWI DK | DK Coastal Kystdirektoratet | Lidar/Ortho | MADV | MVRA | 130 | 130 | 0 | 0 | 0 |  |  |  |  | NO |  |  |  |  | ATR | NO | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 34 | GROUPE DEGAUDE | Highway APRR | Vector | MADV | KMRE | 2900 | 2240 | 660 | 128 | 2112 | 2018-04-25 | 2018-05-25 | 2018-04-30 | 2018-04-26 | YES |  | 2018-04-27 |  |  | Signed QS | NO | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-30
2018-04-01 | 35 | GROUPE DEGAUDE | CRAIG ALLER | Lidar | MADV | SUHH | 931 | 931 | 0 | 0 | 0 |  |  |  |  | YES |  |  |  |  | Signed QS | NO | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-01
2018-04-01 | 36 | COWI AS | Registration_of_traffic_signs - Slagelse | Vector | MADV | RRKN | 726 | [13 empty] | ATR | YES |  | In progress | [11 empty] | 2018-04-09
2018-04-01 | 37 | COWI Norway | NordTrøndelagSør 2016_Part-2 | Vector | MADV | KMRE | 480 | 480 | 0 | 0 | 0 | 2018-04-04 |  |  |  | YES |  |  |  |  | No | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 38 | COWI Norway | Stavanger - Update mapping-2018 | AT/Vector/Ortho | MADV | KMRE | 2782 | 0 | 2782 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 39 | COWI Norway | Nordhordland-2018 | AT/Vector/Ortho | MADV | KMRE | 13365 | 0 | 13365 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 40 | COWI Norway | Marnadal Audnedal Sogndalen-2018 | AT/Vector/Ortho | MADV | KMRE | 4796 | 0 | 4796 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 41 | COWI Norway | Sunnfjord-2018 | AT/Vector/Ortho | MADV | KMRE | 7323 | 0 | 7323 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 42 | COWI Norway | Etne Kvinnherad-2018 | AT/Vector/Ortho | MADV | KMRE | 3464 | 0 | 3464 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04
2018-04-01 | 43 | BSF Swissphoto Norway | Storfjorden-2018 | AT/Vector/Ortho | MADV | MNJA | 2189 | 0 | 2189 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-04-01 | 44 | BSF Swissphoto Norway | Orkdal Meldal Froya-2018 | AT/Vector/Ortho | MADV | MNJA | 1893 | 0 | 1893 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-04-01 | 45 | BSF Swissphoto Norway | Namsos Vikna Nærøy-2018 | AT/Vector/Ortho | MADV | MNJA | 1014 | 0 | 1014 | 0 | 0 |  | Expecting June-18 | [7 empty] | No | NO |  | Expecting June-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-04-01 | 46 | COWI Sweeden | SE_Eskilstuna_2018_Mapping | AT/Ortho | MADV | SUHH | 280 | 0 | 280 |  |  |  | Expecting May-18 | [22 empty] | 2018-04-18
2018-04-01 | 47 | ASI | Titan & Aragorn | Lidar | RASA | SUHH | 75 | 75 | 0 | 75 |  | 2018-04-05 |  | 2018-04-06 |  | YES |  | 2018-04-06 |  |  | Signed QS | Yes | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2018-04-18
2018-04-01 | 48 | ASI | Oklahama mapping | 2D | RASA
2018-04-01 | 49 | ASI | Historical Ortho | AT/Ortho | RASA
2018-04-01 | 50 | TopGIS | Historical orthophoto Buskerud and Østfold | AT/Ortho | MADV | RRKN | 5000 | 2910 | 2090 | 2910 |  | 2018-04-27 |  | 2018-04-03 | 2018-04-05 | [5 empty] | Signed QS | YES |  | In progress |  |  |  | 13 |  | 5 | 1 |  |  |  |  | 2018-04-23
2018-04-01 | 51 | COWI Sweeden | Skåne Photo Summer-Batch 2 | AT/Ortho | MADV | SUHH | 134 | 132 |  | 29 | 0 | 2018-03-29 |  | 2018-03-29 |  | YES | 2017-11-23 | 2017-11-22 | 2017-11-27 | 2017-11-27 | ATR | YES | To be invoiced | In progress | [11 empty] | 2018-04-18
2018-04-01 | 52 | BSF Swissphoto | 7088_ALS_SachsenAnhalt | LiDAR | MADV | MVRA | 540 | 540 | 0 | 540 | 0 |  |  |  | 2018-03-29 | YES |  | 2018-03-29 |  |  | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 53 | COWI AS | Registration_of_traffic_signs - Skanderborg | Vector | MADV | RRKN | 815 | 815 | 0 | [11 empty] | ATR | YES |  | In progress | [11 empty] | 2018-04-09
2018-04-01 | 54 | Fmaps | Smitty One | AT/DTM | MADV | RRKN | 16.5 | 16.5 | 0 | 16.5 |  | 2018-04-10 | [8 empty] | Email |  | Invoiced | Delivered |  |  |  | 2 | [7 empty] | 2018-04-10
2018-04-01 | 55 | COWI AS | Registration_of_traffic_signs - Hillerød Kommune | Vector | MADV | RRKN | 618 | 618 | 0 | 618 |  | 2018-04-10 | [8 empty] | ATR | YES |  | In progress | [11 empty] | 2018-04-19
2018-04-01 | 56 | COWI | DDG 2018 | Vector | MADV | MNJA | 23000 | 0 | 23000 | 1000 | 22000 |  | 2018-05-07 | [21 empty] | Project Handover and Kickoff to be done Project Input -Output not applicable
2018-04-01 | 59 | Opsia | St Gaudens | Lidar | MADV | SUHH | 23 | 23 | 0 | 23 | 103 | 2018-04-17 | [8 empty] | Signed QS | YES | To be invoiced | Delivered | [11 empty] | 2018-04-18
2018-04-01 | 60 | PIE Services | SEWER & STORM GIS layer update | Vector | MADV | RRKN | 20 | 20 | 0 | 20 | 20 | 2018-04-02 | [8 empty] | Email |  | To be invoiced | Delivered |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 2018-04-19
2018-04-01 | 61 | COWI DK | Hässleholm - lidar | Lidar | MADV | RRKN | 80 |  | 80 | 80 | [10 empty] | ATR |  |  | To be started | [11 empty] | 2018-04-19
2018-04-01 | 62 | AAM | PRJ31205_23_BluescopeApr2018 | AT | MADV | MADV | 6 | 6 | 0 | 6 | 6 | 2018-04-19 |  | 2018-04-19 |  | YES |  |  |  |  | WO | NO |  | To be started | [11 empty] | 2018-04-20
2018-04-01 | 63 | COWI Norway | Østfold 2017 | Vector | MADV | KMRE | [17 empty] | Client corrections | [11 empty] | 2018-04-20
2018-04-01 | 64 | AAM | PRJ32362_02_Dunmore_Apr2018 | AT | MADV | MADV | 5 | 5 | 0 | 5 | 5 | 2018-04-20 |  | 2018-04-20 |  | YES |  |  |  |  | WO | NO |  | To be started | [11 empty] | 2018-04-20
2018-04-01 | 65 | INFORGEO | 2D Extraction Land cover | 2D | MADV | MYPZ | 49 | 49 | 0 | 49 |  | 2018-04-20 |  | 2018-04-20 | 2018-04-23
2018-04-01 | 66 | COWI DK | Stockholm photo 2018 | AT/Vector/Ortho | MADV |  | 2700
2018-04-01 | 67 | COWI DK | Stockholm laser 2018 | LiDAR | MADV |  | 1428
2018-04-01 | 68 | COWI DK | Horndal mapping | Vector/AT | MADV |  | 500
2018-04-01 | 69 | COWI DK | Trollhättan photo/3d modelling | Vector/AT/Ortho | MADV |  | 1270
2018-04-01 | 70 | COWI DK | Eskilstuna photo |  | MADV |  | 245
2018-04-01 | 71 | COWI DK | Lerum photo | Vector/AT/Ortho | MADV |  | 207
2018-04-01 | 72 | COWI DK | Sotenäs photo | Vector/AT/Ortho | MADV |  | 107
2018-04-01 | 73 | COWI DK | Helsingborg photo | Vector/AT/Ortho | MADV |  | 200
2018-04-01 | 74 | COWI DK | Hässleholm oblique | Vector/AT | MADV |  | 133
2018-04-01 | 75 | COWI DK | Höganäs photo | Vector/AT/Ortho | MADV |  | 218
2018-04-01 | 76 | ASI | Rattlesnake | LiDAR | RASA | MVRA | 150 | 150 | 0 | 75 | 0 | 2018-04-23 | [10 empty] | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 77 | VANSTEELANDT | Powerline | LiDAR | MADV | MVRA | 350 | 350 | 0 |  |  | 2018-04-05 | [10 empty] | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 78 | BSF Swissphoto | Weser | LiDAE | MADV | MVRA | 80 | 80 | 0 | [13 empty] | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-05-06
2018-04-01 | 79 | Opsia | Vector Mapping 1 500 scale | Vector | MADV | RRKN | 2144 | 2144 |  | 2144 |  | 2018-04-24 |  | 2018-04-25 | 2018-04-25 | YES |  | 2018-04-25 |  |  | Signed QS | NO |  | To be started
2018-04-01 | 80 | Fmaps | Romia 9 | AT/DTM | MADV | RRKN | 30 | 30 |  | 30 |  | 2018-04-24 |  |  |  | YES |  |  |  | 2018-04-24 | Email | NA | Invoiced | Delivered |  |  |  | 2
2018-04-01 | 81 | Opsia | GC170269_Hauts de France MARNE And AISNE | LiDAR | MADV | RRKN | 257 | 257 |  |  |  | 2018-04-27 |  | 2018-04-26 |  | YES |  | 2018-04-27 |  |  | Signed QS |  |  | To be started
2018-04-01 | 82 | COWI DK | Helsingborg | Vector/AT/Ortho | MADV | RRKN | 180 | 180 |  |  |  | 2018-04-26 |  | 2018-04-26 | [9 empty] | In progress
2018-04-01 | 82 | Opsia | 9904_Gapeau | LiDAR | MADV | RRKN | 140 | 140 |  | 140 |  | 2018-04-27 |  | 2018-04-27 | [6 empty] | Signed QS |  |  | In progress
2018-04-01 | 83 | Langan | Perth Amboy - Herbert Street | AT/Vector/Ortho | RASA | MVRA | 195 | 195 | 0 | [14 empty] | In progress
2018-03-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable Hours | Remaining Billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Input/Output Register | Project Handover Date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) - (AE + AF + AG) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2018-03-01 | 1 | Topocart | UR-10K | Vector | MADV | SKCY | 9702 | 4968 | 4734 | 3000 |  | 2018-04-05 | 2018-04-02 | 2018-03-07 |  | Yes | 2018-02-08 | YES | YES | Yes | PO | Yes | To be invoiced | In progress |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-02
2018-03-01 | 2 | CAS | CAS-AT, Ortho, Vector | Vector/AT/Ortho | RASA | SKCY | 8630 | 8630 | 0 | 2372 |  | 2018-03-26 |  | 2018-03-26 |  | YES | NA | YES | 2017-01-15 | 2017-01-15 | WO | Yes | Monthly Invoice | In progress |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-02
2018-03-01 | 3 | Topocart | UR-1K | Vector | MADV | SKCY | 2628 | 2628 | 0 | 162 |  | 2018-01-29 |  | 2018-01-30 |  | Yes | 2017-11-28 | 2017-11-08 | 2018-01-10 | 2018-01-11 | PO | Yes | To be invoiced | Delivered |  |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-02
2018-03-01 | 4 | PMC | NHFS | AT/Ortho | RASA | SKCY | 946 | 946 | 0 | 789 |  | 2018-02-05 |  | 2018-02-05 |  | Yes | 2018-02-20 | 2018-02-20 | 2018-02-23 | 2018-02-23 | PO | YES | To be invoiced | Delivered |  |  |  | 53 | 0 | 1 | 1 | 0 | 0 | 614 |  | 2018-04-02
2018-03-01 | 5 | PMC | Elkhorn | AT/Ortho | RASA | SKCY | 52 | 52 | 0 | 52 |  | 2018-03-22 |  | 2018-02-23 |  | Yes | NO | NO | NO | NO | PO | YES | To be invoiced | Delivered |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 40 |  | 2018-04-02
2018-03-01 | 6 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 136 | 0 | 2017-11-28 |  | 2017-12-21 |  | YES | 2018-01-23 | 2018-01-19 | 2018-01-22 | 2018-01-23 | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | * Feature Geometry Updation Complete, awaiting attribute update guideline to complete the project. | 2018-03-30
2018-03-01 | 8 | GROUPE DEGAUDE | SNCF Amberieu railway station | LiDAR | MADV | RRKN | 48 | 48 | 0 |  |  | 2018-03-21 | 2018-03-26 | 2018-03-21 | 2018-03-23 |  | 2018-03-21 |  |  |  | Signed QS | NA |  | In progress |  |  |  | 0 | [7 empty] | 2018-03-30
2018-03-01 | 9 | VERIS | Cranbrook | LiDAR | MADV | RRKN | 297 | 297 | 0 | 0 |  | 2018-02-15 |  | 2018-02-15 | 2018-02-16 | YES | 2018-02-15 | 2018-02-19 | 2018-02-22 | 2018-02-19 | PO |  | Invoiced | Delivered |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 2018-03-30
2018-03-01 | 10 | GROUPE DEGAUDE | Le Memont | LiDAR | MADV | RRKN | 2.7 | 0 | 2.7 |  |  |  | 2018-03-15 | [10 empty] | To be started | [10 empty] | Expected in 3rd week of March | 2018-03-30
2018-03-01 | 12 | Rossi | Schio 2K Mapping | Vector | MADV | RRKN | 2048 | 2048 | 0 |  |  | 2018-03-05 |  | 2018-03-05 | 2018-03-12 | YES | 2018-03-07 | 2018-03-19 | 2018-03-22 | 2018-03-07 | Signed QS | YES |  | In progress |  |  |  | 3 | 0 | 1 | 1 |  |  |  |  | 2018-03-30
2018-03-01 | 13 | COWI DK | NL_Hague_Thermal_2017 | Ortho | MADV | RRKN | 45 | 45 | 0 |  |  | 2018-03-05 | [8 empty] | ATR |  | Monthly Invoice | Delivered |  |  |  | 1 | [7 empty] | 2018-03-30
2018-03-01 | 14 | COWI AS | OSGB_Urban_2017_19 | Vector | MADV | RASA | 114019 | 114019 | 0 | 1500 | 0 | 2018-03-15 |  | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-06
2018-03-01 | 15 | COWI AS | OSGB_Rular_2017_19 | Vector | MADV | RASA | 52069 | 51469 | 0 | 1000 |  |  |  | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 16 | COWI AS | NCR Pilot | Vector | MADV | RASA | 1848 | 1848 | 0 | 1848 | 0 |  |  |  |  | YES | [7 empty] | In progress
2018-03-01 | 17 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6714 | 6714 | 0 | 950 | 0 | 2017-08-25 |  | 2017-08-25 |  | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 | Signed QS | YES | To be invoiced | In progress |  | 2018-03-19 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 18 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6714 | 5500 | 1214 | 634 | 0 | 2017-12-01 | 2018-08-01 | 2017-12-01 |  | YES | YES | 2017-12-05 | 2017-12-05 | 2017-12-05 | Signed QS | YES | To be invoiced | In progress |  | 2018-03-19 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Data received for 1323 Hours Only. AT is in Progress for Remaining Area
2018-03-01 | 19 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 80 | 0 | 2017-07-17 |  | 2017-07-17 |  | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 | Signed QS | YES | To be invoiced | Delivered | 2018-03-20 | 2018-03-19 |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-02-19
2018-03-01 | 20 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 0 | 0 | 2017-09-27 |  | 2017-09-28 |  | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 | Signed QS | YES | Invoiced | Delivered | 2018-03-20 | 2018-03-19 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-19
2018-03-01 | 21 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1095 | 1095 | 0 | 0 | 0 | 2017-07-12 |  | 2017-07-12 |  | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 | Signed QS | YES | To be invoiced | Delivered |  | 2018-03-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-19
2018-03-01 | 22 | COWI Norway | Historic Ortho-Phase3 | AT/Ortho | MADV | MNJA | 903 | 903 | 0 | 50 | 0 | 2017-12-08 |  | 2017-12-08 |  | YES | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | ATR | NA | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received
2018-03-01 | 23 | COWI DK | Zambia | Vector | MADV | MNJA | 1950 | 1950 | 0 | 1950 | 0 | 2018-02-22 |  | 2018-02-22 |  | YES |  |  |  |  | Signed QS |  | Monthly Invoice | Delivered |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 24 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | [17 empty] | Delivered |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 | 0
2018-03-01 | 25 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | [17 empty] | Delivered |  |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0
2018-03-01 | 26 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6655 | 4598 | 2057 | 513 |  | 2018-03-26 | 2018-04-16 |  |  | YES |  |  | 2017-08-10 |  | Signed QS | YES | To be invoiced | Delivered |  | 2018-03-19 | 2018-03-19 | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 27 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 2284 | 2284 | 0 | 582 |  | 2018-03-09 |  | 2018-03-14 |  | YES |  |  |  |  | Signed QS | YES | Monthly Invoice | In progress |  | 2018-03-19 |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 28 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 4063 | 1967.1 | 2095.9 | 782 |  | 2018-01-29 | 2018-04-01 | 2018-01-29 |  | YES |  |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Received inputs - Block_01 40 CM & Mpigi - 15CM | 2018-03-27
2018-03-01 | 29 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1526 | 1526 | 0 | 1050 |  | 2017-12-26 |  | 2018-01-02 |  | YES | 2018-02-19 | 2018-02-13 |  |  | WO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 30 | Langan | Piscataway | AT/Vector/Ortho | RASA | MVRA | 133 | 133 | 0 | 133 |  | 2018-02-22 |  | 2018-02-22 |  | YES |  | 2018-02-28 |  |  | No | YES | To be invoiced | Hold |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 31 | VERIS | Roadcon | LiDAR | MADV | RRKN | 45 | 45 |  | 45 |  | 2018-03-01 | [8 empty] | Email |  | Invoiced | Delivered |  |  |  | 3 | [7 empty] | 2018-03-30
2018-03-01 | 32 | Fmaps | Starling | AT/DTM | MADV | RRKN | 23 | 23 | 0 | 23 |  | 2018-03-06 | [8 empty] | Email |  | Invoiced | Delivered |  |  |  | 2 |  | 2 | 1 |  |  |  |  | 2018-03-30
2018-03-01 | 33 | COWI AS | HxIP | Ortho | MADV | KSAB | 9836 | 6435 | 3401 | 721.8 | 285.99 | 2018-03-19 | 2018-04-05 | 2017-12-18 |  | YES |  | 2017-07-13 | 2017-07-13 | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 6 | 0 | 4 | 4 | 0 | 0 | 0 |  | 2018-04-02
2018-03-01 | 34 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 10830 | 7462 | 3368 | 381 | 906.3 | 2018-03-23 | 2018-04-12 |  |  | YES |  | 2017-07-13 |  | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 5 | 0 | 16 | 15 | 1 | 0 | 0 | Received feedback from end customer for block GA_J (Total - 133 errors) | 2018-04-02
2018-03-01 | 35 | Langan | Middletown | AT/Vector/Ortho | RASA | MVRA | 85 | 85 | 0 | 85 | 0 | 2018-03-07 |  | 2018-03-08 |  | YES |  |  |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Need to submit the revised QS as there is an increment in image count | 2018-03-27
2018-03-01 | 36 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 3243 | 8685 | 2017-11-20 |  | 2017-11-21 |  | YES | 2017-11-14 | 2017-11-07 | 2017-12-21 | 2017-12-18 | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3D engine Tool availability by EOW- WK-16 | 2018-04-03
2018-03-01 | 37 | PMC | NASA-LFB | Ortho/Lidar | MADV | SKCY | [9 empty] | Yes | [6 empty] | To be invoiced | To be Started
2018-03-01 | 38 | COWI AS | OSGB_Urban_2018_19 | Vector | MADV | RASA | 49690 | 4800 | 44890 | 5000 |  | 2018-03-22 |  |  |  | YES |  |  |  |  | ATR |  | Monthly Invoice | In progress | [11 empty] | 2018-03-23
2018-03-01 | 39 | COWI AS | OSGB_Rular_2018_19 | Vector | MADV | RASA | 44160 | 1165 | 42995 | 1500 |  | 2018-03-22 |  |  |  | YES |  |  |  |  | ATR |  | Monthly Invoice | In progress | [11 empty] | 2018-03-23
2018-03-01 | 40 | Fmaps | Melton | AT/DTM | MADV | RRKN | 111 | 111 | 0 | 111 |  | 2018-03-14 |  |  |  | YES |  |  |  |  | Email |  | Invoiced | Delivered |  |  |  | 2 | [7 empty] | 2018-03-30
2018-03-01 | 41 | AAM | PRJ31205_17_BluescopeMar2018 | AT | MADV | MADV | 6 | 6 | 0 | 6 |  | 2018-03-15 | [11 empty] | In progress
2018-03-01 | 42 | Opsia | GC170269_Hauts de France - Valenciennes | LiDAR | MADV | RRKN | 122 | 122 | 0 | 122 |  | 2018-03-21 |  | 2018-03-21 | 2018-03-21 | YES | 2018-03-21 | 2018-03-24 | 2018-03-29 |  | Signed QS |  |  | In progress |  |  |  | 0 | [7 empty] | 2018-03-30
2018-03-01 | 43 | IBV KRANK | PROJECT 2018-1 | LiDAR | MADV | MVRA | 2200 | 0 | 2200 | 0 | 2200 |  | 2018-04-15 | [9 empty] | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 44 | XEOS | PR2705 | LiDAR | RASA | MVRA | 240 | 0 | 200 | 0 | 200 |  | 2018-04-15 | [9 empty] | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 45 | BSF Swissphoto | BSF NL 2018 | Ortho | MADV | MVRA | 3000 | 0 | 3000 | 0 | 3000 |  | 2018-04-15 | [9 empty] | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 46 | BSF Swissphoto | BW LiDAR | LiDAR | MADV | RASA | 4100 | 0 | 4100 | 0 | 4100 |  | 2018-04-15 | [9 empty] | To be invoiced | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-19
2018-03-01 | 47 | Langan | Franciscan University | AT/Vector/Ortho | RASA | MVRA | 243 | 243 | 0 | 243 | 0 | 2018-03-21 |  | 2018-03-21 |  | YES |  | 2018-03-21 |  |  |  |  | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 48 | Opsia | Cedex_BD500 | Vector | MADV | RRKN | 90 | 90 |  | 90 |  | 2018-03-20 | [10 empty] | To be invoiced | Delivered | [10 empty] | The Project is shelved | 2018-03-30
2018-03-01 | 49 | Rossi | Schio 5K Mapping | Vector | MADV | RRKN | 770 | 770 |  | 770 |  | 2018-03-05 |  | 2018-03-05 | 2018-03-23 |  | 2018-03-26 |  |  |  | Signed QS |  |  | In progress |  |  |  | 0 | [7 empty] | 2018-03-30
2018-03-01 | 50 | COWI AS | DK Coastal Directorate Lodbjerg Nymindegab | Lidar/Ortho | MADV | MVRA | 130 | 0 | 130 | 0 | 130 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-27
2018-03-01 | 52 | BSF | 2 jobs |  |  | MNJA
2018-03-01 | 53 | GROUPE DEGAUDE | Highway APRR | Vector |  | KMRE | 2900
2018-03-01 | 54 | GROUPE DEGAUDE | CRAIG ALLER | Lidar |  | MVRA | 1800 | 0 | 1800 | 0 | 1800 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 55 | COWI AS | Registration_of_traffic_signs - Slagelse | Vector | MADV | RRKN | 726 | [16 empty] | In progress | [11 empty] | 2018-03-30
2018-03-01 | 56 | COWI Sweeden | Varmdo | Vector | MADV | SUHH | 15 | 15 | 0 | 15 | 0 | 2018-03-15 |  |  | 2018-03-15 |  | 2018-03-15 |  |  |  | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 1 |  |  |  |  | 2018-03-23
2018-03-01 | 57 | COWI Norway | Stavanger - Update mapping - 2018 | AT/Vector/Ortho | MADV | KMRE | 1664
2018-03-01 | 58 | COWI Norway | Nordhordland-2018 | AT/Vector/Ortho | MADV | KMRE | 13365
2018-03-01 | 59 | COWI Norway | Marnadal Audnedal Sogndalen - 2018 | AT/Vector/Ortho | MADV | KMRE | 4796
2018-03-01 | 60 | COWI Norway | Sunnfjord - 2018 | AT/Vector/Ortho | MADV | KMRE | 7323
2018-03-01 | 61 | COWI Norway | Etne Kvinnherad - 2018 | AT/Vector/Ortho | MADV | KMRE | 3464
2018-03-01 | 62 | BSF Swissphoto Norway | Storfjorden-2018 | AT/Vector/Ortho | MADV | MNJA | 2189
2018-03-01 | 63 | BSF Swissphoto Norway | Orkdal Meldal Froya-2018 | AT/Vector/Ortho | MADV | MNJA | 1893
2018-03-01 | 64 | BSF Swissphoto Norway | Namsos Vikna Nærøy | AT/Vector/Ortho | MADV | MNJA | 1014
2018-03-01 | 65 | COWI Sweeden | SE_Eskilstuna_2018_Mapping | AT/Ortho | MADV | SUHH | 300 | 0 | 280
2018-03-01 | 66 | ASI |  | Lidar | RASA
2018-03-01 | 67 | ASI | Oklahama mapping | 2D | RASA
2018-03-01 | 68 | ASI | Historical Ortho | AT/Ortho | RASA
2018-03-01 | 69 | TopGIS | Historical orthophoto Buskerud and Østfold | AT/Ortho | MADV | RRKN | [17 empty] | In progress
2018-03-01 | 70 | COWI Sweeden | Skåne Photo Summer-Batch 2 | AT/Ortho | MADV | SUHH | 192 | 192 | 0 |  |  | 2017-11-28 | 2018-02-15 | 2017-11-28 |  | YES | 2017-11-23 | 2017-11-22 | 2017-11-27 | 2017-11-27 | ATR | YES | To be invoiced | To be started | [11 empty] | 2018-03-30
2018-03-01 | 71
2018-03-01 | 55 | BSF Swissphoto | 7088_ALS_SachsenAnhalt | LiDAR | MADV | MVRA | 540 | 540 | 0 | 540 | 0 |  |  |  | 2018-03-29 | YES |  | 2018-03-29 |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-02-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable Hours | Remaining Billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Input/Output Register | Project Handover Date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) - (AE + AF + AG) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2018-02-01 | 1 | Topocart | UR-10K | Vector | MADV | SKCY | 9702 | 8316 | 1386 | 700 | 9002 | 2018-03-07 | 2018-02-25 | 2018-02-09 |  | Yes | Yes | YES | NA | NA | NA | No | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-01
2018-02-01 | 2 | CAS | Various | Vector/AT/Ortho | RASA | SKCY | 6397 | 6397 | 0 | 3325 | 0 | 2018-05-24 |  | 2018-05-24 |  | YES | NA | YES | 2017-01-15 | 2017-01-15 | WO | Yes | Monthly Invoice | In progress |  |  |  | 40 | 0 | 2 | 2 | 0 | 0 | 0 |  | 2018-03-01
2018-02-01 | 3 | Topocart | UR-1K | Vector | MADV | SKCY | 2628 | 2628 | 0 | 749 | 0 | 2018-01-29 |  | 2018-01-30 |  | Yes | 2017-11-28 | 2017-11-08 | 2018-01-10 | 2018-01-11 | PO | Yes | To be invoiced | In progress |  |  |  | 18 | 0 | 8 | 8 | 0 | 0 | 0 |  | 2018-03-01
2018-02-01 | 4 | COWI Sweeden | Stockholm OP 2017 -Extension | AT/Ortho | NSPI | SUHH | 30 | 30 | 0 | 16 | 0 | 2018-01-24 |  | 2018-01-24 |  | YES | 2018-01-19 | 2017-08-02 | 2017-08-02 | 2017-08-02 | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-09
2018-02-01 | 5 | COWI AS | HxIP | Ortho | MADV | KSAB | 9777 | 5427 | 4350 | 354 | 1858.8 | 2018-02-19 | 2018-03-12 | 2017-12-18 |  | YES |  | 2017-07-13 | 2017-07-13 | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 9 | 9 | 0 | 0 | 0 |  | 2018-03-06
2018-02-01 | 6 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 11278 | 6174 | 5104 | 1619 | 4156.69 | 2018-02-15 | 2018-03-20 |  |  | YES |  | 2017-07-13 |  | YES | ATR | YES | Monthly Invoice | In progress |  |  |  | 7 | 6 | 13 | 10 | 3 | 0 | 0 | Received feedback from end customer for block SC_E (Seamline errors and Tonal issues), AL_I (Tonal Issues) and AL_G (Tonal Issues) | 2018-03-06
2018-02-01 | 7 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 6534 | 0 | 1500 | 0 | 2017-08-25 |  | 2017-08-25 |  | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-19
2018-02-01 | 8 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 5653 | 1323 | 0 | 250 | 0 | 2017-12-01 |  | 2017-12-01 |  | YES | YES | 2017-12-05 | 2017-12-05 | 2017-12-05 | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data received for 940 Hours Only. Remaining data shall be received as Phase 2 in next financial year | 2018-02-19
2018-02-01 | 9 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1095 | 1095 | 0 | 0 | 0 | 2017-07-12 |  | 2017-07-12 |  | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 | Signed QS | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Additional Cost has been negotiated with client for Tvedestrand | 2018-02-19
2018-02-01 | 10 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 80 | 0 | 2017-07-17 |  | 2017-07-17 |  | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | Vector Delivered. Ortho To be done | 2018-02-19
2018-02-01 | 11 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 0 | 0 | 2017-09-27 |  | 2017-09-28 |  | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 | Signed QS | YES | Invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delivered | 2018-02-19
2018-02-01 | 12 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5745 | 5745 | 0 | 1200 | 0 | 2017-10-13 |  | 2017-10-17 |  | 2017-10-23 | 2017-10-25 | 2017-10-23 | 2017-10-25 | 2017-10-25 | ATR | YES | Monthly Invoice | Delivered |  |  |  | 14 | 0 | 1 | 1 | 0 | 0 | 0 | All Data set Received | 2018-02-19
2018-02-01 | 13 | COWI Norway | Historic Ortho-Phase3 | AT/Ortho | MADV | MNJA | 903 | 903 | 0 | 750 | 0 | 2017-12-08 |  | 2017-12-08 |  | YES | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | ATR | NA | Monthly Invoice | In progress |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2018-02-19
2018-02-01 | 14 | COWI DK | Zambia | Vector | MADV | MNJA | [17 empty] | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is in Pilot Stage, All inputs shall be filled based on approval of Pilot Data | 2018-02-19
2018-02-01 | 15 | GS INT | OMAN | AT/Vector | MADV | MNJA | 580 | 580 | 0 | 580 | 0 | 2018-02-08 |  | 2018-02-09 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-19 | 2018-02-09 | Signed QS | YES | To be invoiced | Delivered |  | 2018-02-28 | 2018-03-06 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Project Is on Hold and may be stopped for further production | 2018-02-19
2018-02-01 | 16 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | [5 empty] | 2017-07-10 |  | 2017-07-10 |  | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 3 | 3 | 0 | 0 | 0 | All blocks delivered in the Month of November however we have received feedback in december | 2018-02-19
2018-02-01 | 17 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 180 | 0 | 2017-11-28 |  | 2017-12-21 |  | YES | 2018-01-23 | 2018-01-19 | 2018-01-22 | 2018-01-23 | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | * Feature Geometry Updation Complete, awaiting attribute update guideline to complete the project. | 2018-02-07
2018-02-01 | 18 | Digimaps | Digimapas_Cartography | Vector | NSPI | RRKN | 2459 | 0 | 2459 | 0 | 0 | [12 empty] | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Expected | 2018-02-07
2018-02-01 | 19 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 5500 | 12549 | 2017-11-20 |  | 2017-11-21 |  |  | 2017-11-14 | 2017-11-07 |  | 2017-12-18 | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3D engine Tool availability by EOW- WK-9 | 2018-02-22
2018-02-01 | 20 | COWI AS | OSGB_Urban_2017_19 | Vector | MADV | AISR | 111276 | 108776 | 0 | 8588 | 10657 | 2018-02-02 | 2018-02-16 | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 99 | 0 | 0 | 0 | 1 | 0 | 0 |  | 2018-02-22
2018-02-01 | 21 | COWI AS | OSGB_Rular_2017_19 | Vector | MADV | AISR | 51819 | 51219 | 0 | 3379 | 3979 | 2018-02-02 | 2018-02-17 | 2018-02-05 |  | Yes |  | YES |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-22
2018-02-01 | 22 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 | 0 | 0 | 0 | 2017-05-09 |  | 2017-05-09 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 23 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2712 | 2712 | 0 | 0 | 144 | 2017-05-09 |  | 2017-05-09 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 24 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9932.5 | 9932.5 | 0 | 250 | 565 | 2017-06-27 |  | 2017-06-27 |  | Yes | 2017-05-09 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 25 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 | 0 | 0 | 182 | 2017-05-27 |  | 2017-05-27 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Client corrections | 2018-01-02 |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 26 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9684 | 9684 | 0 | 1700 | 1745 | 2017-12-13 |  | 2017-12-13 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | In progress | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 27 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 | 0 | 0 | 483 | 2017-07-31 |  | 2017-07-31 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 28 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5921 | 5921 | 0 | 0 | 250 | 2017-05-24 |  | 2017-05-24 |  | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 29 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 0 | 0 | 0 | 2017-10-06 |  | 2017-10-09 |  | Yes | 2017-06-25 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 30 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 | 0 | 0 | 28 | 2017-07-07 |  | 2017-07-07 |  | Yes | 2017-09-12 | 2017-05-01 | Shared With TEGU | 2017-09-01 | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-20
2018-02-01 | 31 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6731 | 4090 | 2717 | 153 | 0 | 2018-01-15 | 2018-03-15 |  |  | YES |  |  | 2017-08-10 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Input received for 51 Tiles of Part-03 (reflown) | 2018-02-28
2018-02-01 | 32 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 1984 | 1984 | 0 | 686 | 0 | 2018-01-17 |  | 2018-01-17 |  | YES |  |  |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 9 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 33 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2925 | 1289 | 1636 | 1200 | 0 | 2018-01-29 |  | 2017-12-22 |  | YES |  |  |  |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 34 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 3920 | 3920 | 0 | 10 | 0 | 2017-12-24 |  | 2017-12-27 |  | YES |  | 2017-09-15 |  | 2017-09-15 | WO | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 35 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1526 | 1526 | 0 | 1526 | 0 | 2017-12-26 |  | 2018-01-02 |  | YES |  |  |  |  | WO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 36 | LANGAN | Monticello | AT/Vector/Ortho | NSPI | MVRA | 38 | 38 | 0 | 38 | 0 | 2018-01-30 |  | 2018-01-30 |  | YES |  |  |  |  | Email | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 37 | LANGAN | St Vincent | AT/Vector/Ortho | NSPI | MVRA | 67 | 67 | 0 | 67 | 0 | 2018-02-04 |  | 2018-02-05 |  | YES |  |  |  |  | Email | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-28
2018-02-01 | 33 | ASI |  |  | NSPI | [18 empty] | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-13
2018-02-01 | 34 | PMC | NHFS | AT/Ortho | NSPI | SKCY | 946 | 946 | 0 | 150 | 796 | 2018-02-05 |  | 2018-02-05 |  | Yes | 2018-02-20 | 2018-02-20 | 2018-02-23 | 2018-02-23 | PO | YES | To be invoiced | In progress |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-01
2018-02-01 | 35 | GROUPE DEGAUDE | SNCF Amberieu railway station | LiDAR | MADV | RRKN | 48 | 0 | 48 | [14 empty] | To be started | [10 empty] | * Data aquasition to be done again by the client & the client will update on input date in coming weeks. Scope may increase with 3D streo plotting | 2018-02-14
2018-02-01 | 36 | Fmaps | Alps | AT/DTM | MADV | RRKN | 39.5 | 39.5 | 0 |  |  | 2018-02-13 |  | 2018-02-13 |  | YES |  |  |  | 2018-02-13 | Email | NA | Invoiced | Delivered |  |  |  | 2 |  | 1 | [5 empty] | 2018-02-16
2018-02-01 | 37 | Fmaps | Te_Roroa | AT/DTM | MADV | RRKN | 42.5 | 42.5 | 0 |  |  | 2018-02-13 |  | 2018-02-13 |  | YES |  |  |  | 2018-02-13 | Email | NA | Invoiced | Delivered |  |  |  | 2 |  | 1 | [5 empty] | 2018-02-16
2018-02-01 | 38 | VERIS | Cranbrook | LiDAR | MADV | RRKN | 297 | 297 | 0 | 297 |  | 2018-02-15 |  | 2018-02-15 | 2018-02-16 |  | 2018-02-15 | 2018-02-19 | 2018-02-22 | 2018-02-19 | PO |  |  | Delivered |  |  |  | 1 | [7 empty] | 2018-02-27
2018-02-01 | 39 | GROUPE DEGAUDE | Le Memont | LiDAR | MADV | RRKN | 2.7 | 0 | 2.7 |  |  |  | 2018-03-15 | [10 empty] | To be started | [10 empty] | Expected in 3rd week of March | 2018-02-14
2018-02-01 | 40 | GROUPE DEGAUDE | CRAIG-LiDAR_2018 | LiDAR | MADV | RRKN | 234 | 0 | 234 |  |  |  | 2018-03-15 | [10 empty] | To be started | [10 empty] | Expected in 3rd week of March | 2018-02-14
2018-02-01 | 41 | AAM | PRJ32017_02_IllawarraCoal | AT | MADV | MADV | 4 | 4 |  | 4 |  | 2018-02-15 |  | 2018-02-15 |  | YES | NA | NA | NA | NA | PO | NA |  | To be started
2018-02-01 | 42 | AAM | PRJ31205_12_Bluescope | AT | MADV | MADV | 6 | 6 |  | 6 |  | 2018-02-15 |  | 2018-02-15 |  | YES | NA | NA | NA | NA | PO | NA |  | To be started
2018-02-01 | 43 | COWI_DK_SE | Inlandsbanan_Additional task | LiDAR | MADV | RRKN | 40 | 40 |  | 40 |  | 2018-02-19 |  |  |  |  | 2018-02-15 | NA | NA | 2018-02-19 | Email | NA | Monthly Invoice | In progress | [11 empty] | 2018-02-21
2018-02-01 | 44 | COWIDK-3D | JRC Tile cutting | Ortho | MADV | RRKN | 10 | 10 |  | 10 |  | 2018-02-21 |  |  |  | NA | NA | NA | NA | NA | ATR | NA | Monthly Invoice | Delivered |  |  |  | 2 | [7 empty] | 2018-02-27
2018-02-01 | 45 | PMC | Elkhorn | AT/Ortho | RASA | SKCY | 12 | 12 | 7 | 5 | 7 | 2018-02-23 |  | 2018-02-23 |  | NO | NO | NO | NO | NO | PO | NO | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-01
2018-02-01 | 46 | Langan | Piscataway | AT/Vector/Ortho | RASA | MVRA | 133 | 133 | 0 | 133 | 0 | 2018-02-22 |  |  |  | YES |  |  |  |  | Email | NO | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total hours differ from the mentioned - need to discuss | 2018-02-28
2018-02-01 | 47 | Rossi | Schio 2K Mapping | Vector | MADV | RRKN | 2362 | 170 | 2192 |  |  | 2018-03-05 | [22 empty] | Need to execute the Pilot first & then plan for Production based on mutual agreement on alloted scope & timeline | 2018-02-26
2018-02-01 | 48 | Fmaps | Donelley | AT/DTM | MADV | RRKN | 32 | 32 |  | 32 |  | 2018-02-26 |  |  |  | YES |  |  |  |  | Email | NA | To be invoiced | Delivered |  |  |  | 2 | [7 empty] | 2018-03-01
2018-01-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable Hours | Remaining billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Reception control date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) |  | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) - (AE + AF + AG) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2018-01-01 | 1 | Topocart | UR-1K | Vector | MADV | SKCY | 2628 | 2628 | 0 | 957 | 0 | 2018-01-29 |  | 2018-01-30 | Yes | 2017-11-28 | 2017-11-08 | 2018-01-10 | 2018-01-11 |  | PO | Yes | To be invoiced | In progress |  |  |  | 6 | 0 | 11 | 11 | 0 | 0 | 0 |  | 2018-02-02
2018-01-01 | 2 | ASI | PAW PAW | vector | NSPI | DPKR | 430 | 430 | 0 | 280 | 0 | 2017-12-19 |  | 2017-12-20 | YES | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-26 |  | PO | YES | Invoiced | Delivered | 2018-01-16 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 3 | ASI | Mt.Sterling | vector | NSPI | DPKR | 75 | 75 | 0 | 75 | 0 | 2018-01-02 |  | 2018-01-03 | YES | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | PO | NO | Invoiced | Delivered | 2018-01-15 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 4 | CAS | Various | AT/Vector/Ortho | NSPI | SKCY | 2930 | 2930 | 0 | 3590 | 0 | 2018-01-30 |  | 2018-01-30 | YES | NA | YES | 2017-01-15 | 2017-01-15 |  | WO | YES | Monthly Invoice | In progress |  |  |  | 27 | 3 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-02
2018-01-01 | 5 | PMC | NH - forest | Ortho | NSPI | SKCY | 222 | 222 | 0 | 198 | 198 | 2017-12-20 |  |  | YES | [5 empty] | PO | Yes |  | Hold | [11 empty] | 2018-02-02
2018-01-01 | 6 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 580 | 0 | 2017-11-28 |  | 2017-12-21 | YES | 2018-01-23 | 2018-01-19 | 2018-01-22 | 2018-01-23 |  | ATR | YES | Monthly Invoice | In progress | [10 empty] | Pilot To Be submitted to the Client on 5th Jan 2018 - Go ahead on feature geometry updation , hence starting the production with Feature updation, attribute update after clarifications are received. | 2018-02-01
2018-01-01 | 7 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6655 | 4014 | 2641 | 508 | 0 | 2018-01-15 | 2018-02-15 |  | YES |  |  | 2017-08-10 |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 8 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 1099 | 1099 | 0 | 536 | 0 | 2018-01-17 |  | 2018-01-17 | YES | [5 empty] | Signed QS | YES | To be invoiced | In progress |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 9 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2925 | 1267 | 1658 | 55 | 0 | 2018-01-29 |  | 2017-12-22 | YES | [5 empty] | ATR | YES | To be invoiced | In progress |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 10 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 3920 | 3920 | 0 | 340 | 0 | 2017-12-24 |  | 2017-12-27 | YES |  | 2017-09-15 |  | 2017-09-15 |  | WO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 11 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1526 | 1526 | 0 | 1526 | 0 | 2017-12-26 |  | 2018-01-02 | YES | [6 empty] | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 12 | XEOS | PR2574 - Breaklines and DTM | Vector | NSPI | MVRA | 154 | 154 | 0 | 45 | 0 | 2017-12-21 |  | 2017-12-14 | YES | 2017-12-20 |  |  |  |  | Email | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 2 | 2 | 0 | 0 | 0 | Customer has identified artefacts in delivered GeoTiff (DTM) out of the AOI | 2018-02-01
2018-01-01 | 13 | XEOS | PR2462 - Breaklines and DTM | Vector | NSPI | MVRA | 139 | 139 | 0 | 139 | 0 | 2017-12-31 |  | 2018-01-02 | YES | [5 empty] | Email | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 14 | VANSTEELANDT | R8 Mapping | Vector | MADV | MVRA | 100 | 100 | 0 | 64 | 0 | 2017-12-22 |  | 2018-01-02 | YES | [5 empty] | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 15 | FIRST BASE SOLUTION | Oakville | Vector | NSPI | MVRA | 641 | 641 | 0 | 45 | 0 | 2017-09-17 |  | 2017-09-18 | YES | 2017-10-23 | 2017-10-28 | 2017-11-07 |  |  | PO | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | Correction on 'missing building height points' received from customer (1% of total building points) | 2018-02-01
2018-01-01 | 16 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 | 0 | 0 | 0 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 17 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2712 | 2712 | 0 | 386 | 530 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress | 2018-01-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 18 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9932.5 | 9932.5 | 0 | 0 | 565 | 2017-06-27 |  | 2017-06-27 | Yes | 2017-05-09 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 19 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 | 0 | 0 | 182 | 2017-05-27 |  | 2017-05-27 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 20 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9684 | 9684 | 0 | 923 | 2668 | 2017-12-13 |  | 2017-12-13 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 21 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 | 0 | 132 | 615 | 2017-07-31 |  | 2017-07-31 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 22 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5921 | 5921 | 0 | 107 | 357 | 2017-05-24 |  | 2017-05-24 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Client corrections | 2018-01-02 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 23 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 0 | 0 | 0 | 2017-10-06 |  | 2017-10-09 | Yes | 2017-06-25 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 24 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 | 0 | 0 | 28 | 2017-07-07 |  | 2017-07-07 | Yes | 2017-09-12 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered | 2018-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 25 | COWI AS | HxIP | Ortho | MADV | KSAB | 9462 | 5094 | 4368 | 265.7979 | 4632.9 | 2018-01-30 | 2018-02-10 | 2017-12-18 | YES |  | 2017-07-13 | 2017-07-13 | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 5 | 1 | 4 | 4 |  |  |  |  | 2018-01-31
2018-01-01 | 26 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 11363 | 6299.62 | 5063.38 | 2330.3026 | 5664.25 | 2018-01-22 | 2018-02-05 |  | YES |  | 2017-07-13 |  | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 4 | 1 | 9 | 7 | 2 |  |  | Received feedback from end customer for SC_F and GA_G blocks. Major feedbacks are DTM errors, Seamline errors and Tonal issues. | 2018-01-31
2018-01-01 | 27 | COWI Sweeden | Skåne Laser Summer | LiDAR | NSPI | SUHH | 651 | 651 | 0 | 0 | 0 | 2017-11-09 |  | 2017-11-09 | YES | 2017-10-10 | 2017-11-09 | 2017-11-22 | 2017-11-22 |  | ATR | YES | To be invoiced | Approved |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Batch 2 is rejected by GC due to Major errors | 2018-01-30
2018-01-01 | 28 | COWI Sweeden | Skåne Photo Summer | AT/Ortho | NSPI | SUHH | 560 | 368 | 192 | 201 | 0 | 2017-11-28 | 2018-02-15 | 2017-11-28 | YES | 2017-11-23 | 2017-11-22 | 2017-11-27 | 2017-11-27 |  | ATR | YES | To be invoiced | Approved |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Remaining input hours is uncertain as flying is not done | 2018-01-30
2018-01-01 | 29 | COWI Sweeden | Lerum LiDAR additional | Vector/LiDAR | NSPI | SUHH | 805 | 805 | 0 | 393 | 0 | 2017-12-13 |  | 2017-12-15 | YES | 2017-12-12 | 2017-12-23 | 2017-12-29 | 2017-12-29 |  | ATR | YES | To be invoiced | Approved |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 30 | LANGAN | Fordham Road | AT/Vector/Ortho | MADV | MVRA | 63 | 0 | 63 | 0 | 63 | 2018-01-12 | [9 empty] | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 31 | COWI AS | TZ - Dar Es Salaam 2016_Additional | Ortho | MADV | PSRA | 50 | 50 | 0 | 50 | 0 | 2018-01-01 |  | 2018-01-01 | YES | 2018-01-01 | 2018-01-01 |  |  |  | ATR | NA | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 32 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 4500 | 17100 | 2017-11-20 | 2018-01-15 | 2017-11-21 |  | 2017-11-14 | 2017-11-07 |  | 2017-12-18 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3D engine Tool availability by EOW- WK-6 | 2018-02-02
2018-01-01 | 33 | COWI AS | OSGB_Urban_2017_19 | Vector | MADV | AISR | 111276 | 90000 | 21276 | 10869 | 21957 | 2018-01-26 | 2018-02-16 | 2018-01-29 | Yes |  | YES |  |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-02
2018-01-01 | 34 | COWI AS | OSGB_Rular_2017_19 | Vector | MADV | AISR | 54511 | 50412 | 4099 | 3700 | 10776.55 | 2018-01-26 | 2018-02-17 | 2018-01-29 | Yes |  | YES |  |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-02
2018-01-01 | 35 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 6534 | 0 | 3000 | 2000 | 2017-08-25 |  | 2017-08-25 | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 36 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 940 | 940 | 0 | 800 | 0 | 2017-12-01 |  | 2017-12-01 | YES | YES | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data received for 940 Hours Only. Remaining data shall be received as Phase 2 in next financial year | 2018-01-30
2018-01-01 | 37 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1095 | 1095 | 0 | 500 | 0 | 2017-07-12 |  | 2017-07-12 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 795 | Additional Cost has been negotiated with client for Tvedestrand | 2018-01-30
2018-01-01 | 38 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 80 | 0 | 2017-07-17 |  | 2017-07-17 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vector Delivered Ortho To be done | 2018-01-30
2018-01-01 | 39 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 150 | 0 | 2017-09-27 |  | 2017-09-28 | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 |  | Signed QS | YES | To be invoiced | Delivered |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Delivered | 2018-01-30
2018-01-01 | 40 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5745 | 5745 | 0 | 2000 | 3200 | 2017-10-13 |  | 2017-10-17 | 2017-10-23 | 2017-10-25 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2018-01-30
2018-01-01 | 41 | COWI Norway | Historic Ortho-Phase3 | AT/Ortho | MADV | MNJA | 903 | 903 | 0 | 150 | 753 | 2017-12-08 |  | 2017-12-08 | YES | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | ATR | NA | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2018-01-30
2018-01-01 | 42 | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MADV | MNJA | 225 | 225 | 0 | 92 | 0 | 2017-07-11 |  | 2017-07-11 | 2017-07-12 | 2017-07-24 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | Signed QS | NA | Invoiced | Delivered |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 80 | All data set delivered | 2018-01-25
2018-01-01 | 43 | Digimaps | Digimapas_Cartography | Vector | NSPI | RRKN | 2459 | 0 | 2459 | 0 | 0 | [12 empty] | To be started | [10 empty] | Project Expected in Week 3 - Update Awaited From Sales Team on Contract Status | 2018-02-01
2018-01-01 | 44 | COWI AS | DK Satellitfoto Telezoner 2017 | Ortho | MADV | PSRA | 120 | 120 | 0 | 120 | 0 | 2018-01-10 |  | 2018-01-10 | YES | 2018-01-10 | 2018-01-10 |  |  |  | ATR | NO | To be invoiced | Delivered |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 45 | [5 empty] | 50 | 30 | 20 | 50 | 0 | 2018-01-01 |  | 2018-01-01 | YES
2018-01-01 | 46 | VANSTEELANDT | HIT Dendre Occi | LiDAR | MADV | MVRA | 50 | 50 | 0 | 50 | 0 | 2018-01-09 |  | 2018-01-09 | [6 empty] | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 47 | AAM | PRJ31490_02_Jellinbah_ATWI | AT | MADV | MADV | 20 | 20 |  | 20 |  | 2018-01-05 |  | 2018-01-05 | YES | [8 empty] | Delivered
2018-01-01 | 48 | AAM | PRJ31564_04_Cloudbreak_ATWI | AT | MADV | MADV | 10 | 10 |  | 10 |  | 2018-01-09 |  | 2018-01-09 | YES | [8 empty] | Delivered
2018-01-01 | 49 | AAM | PRJ31326_Burton | AT | MADV | MADV | 18 | 18 |  | 18 |  | 2018-01-16 |  | 2018-01-16 | YES | [7 empty] | Monthly Invoice
2018-01-01 | 50 | AAM | PRJ31318_Goonyella_SouthWalker_Dragline | AT | MADV | MADV | [8 empty] | YES
2018-01-01 | 51 | AAM | PRJ31491_Middlemount | AT | MADV | MADV | [8 empty] | YES
2018-01-01 | 52 | AAM | PRJ31698_03_Moorvale_ATWI | AT | MADV | MADV | 6 | 6 |  | 6 |  | 2018-01-09 |  | 2018-01-09 | YES | [8 empty] | Delivered
2018-01-01 | 53 | VANSTEELANDT | R8 Kortrijk Classification | LiDAR | MADV | MVRA | 30 | 30 | 0 | 30 | 0 | 2018-01-11 |  | 2018-01-11 | YES | [5 empty] | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-01
2018-01-01 | 54 | [19 empty] | PO |  | Monthly Invoice | Delivered
2018-01-01 | 55 | AAM | PRJ31576_02_WAMC_Dec2017_AT | AT | MADV | MADV | 10 | 10 |  | 10 |  | 2018-01-02 |  | 2018-01-02 | YES | [5 empty] | PO |  | Monthly Invoice | Delivered
2018-01-01 | 56 | [19 empty] | PO |  | Monthly Invoice | Delivered
2018-01-01 | 57 | [19 empty] | PO |  | Monthly Invoice | Delivered
2018-01-01 | 58 | SPS - Arail Remote Sensing | IR Ortho Mosaic | Ortho | MADV | DPKR | 106 | 106 | 0 | 106 | 0 | 2018-01-16 |  | 2018-01-17 | YES | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  | Signed QS | NO | Invoiced | Delivered | 2018-01-25 | 2018-01-31 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-31
2018-01-01 | 59 | AAM | PRJ31205_07_Bluescope_Jan2018_AT | AT | MADV | MADV | 6 | 6 |  |  |  | 2018-01-17 |  | 2018-01-17 | YES | [5 empty] | PO |  | Monthly Invoice | In progress
2018-01-01 | 60 | Fmaps | Trelour | AT/DTM | MADV | DPKR | 18 | 18 | 0 | 18 | 0 | 2018-01-19 |  | 2018-01-22 | YES | 2018-01-23 | 2018-01-22 | 2018-01-23 | 2018-01-23 |  | Email | NO | To be invoiced | Delivered | 2018-01-25 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-30
2018-01-01 | 61 | AAM | PRJ31318_02_GoonyellaSthWalker_Jan2018_AT | AT | MADV | MADV | 25 | 25 |  |  |  | 2018-01-19 |  | 2018-01-19 | YES | [5 empty] | PO |  | Monthly Invoice
2018-01-01 | 62 | AAM | PRJ31653_02_Northparkes_AT | AT | MADV | MADV | 28 | 28 |  |  |  | 2018-01-19 |  | 2018-01-19 | [6 empty] | PO |  | Monthly Invoice
2018-01-01 | 63 | COWI
2018-01-01 | 64 | COWI Sweeden | Stockholm OP 2017 -Extension | AT/Ortho | NSPI | SUHH | 30 | 30 | 0 | 14 | 16 | 2018-01-24 |  | 2018-01-24 | YES | 2018-01-19 | 2017-08-02 | 2017-08-02 | 2017-08-02 |  | ATR | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-05
2018-01-01 | 65 | LANGAN | Monticello | AT/Vector/Ortho | NSPI | MVRA | 38 | 38 | 0 | 38 | 0 | 2018-01-30 | [9 empty] | NO | To be invoiced | To be started | [11 empty] | 2018-02-01
2017-12-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable hours | Remaining billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Reception control date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) |  | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed Deliveries | Customer Feedbacks (count of feedbacks) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2017-12-01 | 1 | Topocart | UR-10K | Vector | MADV | SKCY | 2944 | 2944 | 0 | 250 | 0 | 2017-10-11 |  | 2017-10-11 | Yes | 2017-10-12 | 2017-10-05 | 2017-10-23 | 2017-10-13 |  | PO | YES | Invoiced | Delivered |  |  |  | 9 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-01-11
2017-12-01 | 2 | Topocart | UR-1K | Vector | MADV | SKCY | 918 | 918 | 0 | 918 | 0 | 2017-11-28 |  | 2017-11-28 | Yes | 2017-11-28 | 2017-11-08 | 2017-12-05 | 2017-11-28 |  | PO | YES | To be invoiced | In progress |  |  |  | 10 | 0 | 3 | 2 | 1 | 0 | 0 |  | 2018-01-11
2017-12-01 | 3 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 | 0 | 0 | 0 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | Delivered to COWI Norway | 2018-01-03
2017-12-01 | 4 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2712 | 2712 | 0 | 132 | 530 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 5 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9932.5 | 9932.5 | 0 | 0 | 520.5 | 2017-06-27 |  | 2017-06-27 | Yes | 2017-05-09 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 6 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 | 0 | 0 | 249.5 | 2017-05-27 |  | 2017-05-27 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 7 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9684 | 9684 | 0 | 796 | 2668 | 2017-12-13 |  | 2017-12-13 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 8 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 | 0 | 420 | 615 | 2017-07-31 |  | 2017-07-31 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 9 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5564 | 5564 | 0 | 0 | 0 | 2017-05-24 |  | 2017-05-24 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Client corrections |  |  |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 10 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 0 | 0 | 0 | 2017-10-06 |  | 2017-10-09 | Yes | 2017-06-25 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 11 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 | 0 | 0 | 28 | 2017-07-07 |  | 2017-07-07 | Yes | 2017-09-12 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 12 | AAM | PRJ31156_Hail_Creek Mapping | Vector | MADV | KMRE | 370 | 370 | 0 | 370 | 0 | 2017-11-30 |  | 2017-11-30 | YES | 2017-12-04 | 2017-12-04 | 2017-12-05 | 2017-12-05 |  | PO | YES | To be invoiced | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 250 | Received positive feedback | 2018-01-03
2017-12-01 | 13 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 4589 | 20915 | 2017-11-20 | 2018-01-15 | 2017-11-21 |  | 2017-11-14 | 2017-11-07 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 6 | 0 | 6 | 1 | 1 | 0 | 0 | RCL of VIC006 segment redelivered to client + Minor Corrections VIC004 | 2018-01-12
2017-12-01 | 14 | FIRST BASE SOLUTION | 1737ESSX | Vector | NSPI | RRKN | 207 | 207 | 0 | 207 | 0 | 2017-11-24 |  | 2017-11-03 | YES | 2017-11-09 | 2017-11-08 | 2017-11-24 | 2017-11-10 |  | PO | YES | To be invoiced | Delivered | 2017-12-20 | 2017-12-12 | 2017-12-14 | 1 | 0 | 2 | 2 | 0 | 0 | 0 |  | 2018-01-02
2017-12-01 | 15 | COWI Sweeden | SE_Inlandsbanan_production-DK_2017_Mapping | AT/DTM/LiDAR/Ortho | NSPI | RRKN | 991 | 991 | 0 | 851 | 0 | 2017-12-12 |  | 2017-11-15 | 2017-11-15 | 2017-11-08 | 2017-11-15 | 2017-11-23 | 2017-11-23 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-02
2017-12-01 | 16 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 100 | 500 | 2017-11-28 |  | 2017-12-21 | NO | [5 empty] | ATR | YES |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pilot To Be submitted to the Client on 2nd Jan 2018 | 2018-01-02
2017-12-01 | 17 | COWI AS | HxIP | Ortho | MADV | KSAB | 9462 | 7043 | 2419 | 731.214 | 4747.9 | 2017-12-18 | 2018-01-08 | 2017-12-18 | YES |  | 2017-07-13 | 2017-07-13 | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 7 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2018-01-09
2017-12-01 | 18 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 11363 | 3592.68 | 7770.32 | 1306.98 | 8019.9 | 2017-12-22 | 2018-01-08 |  | YES | 2017-10-06 | 2017-07-13 |  | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 3 | 0 | 0 | 0 |  | 2018-01-09
2017-12-01 | 19 | ASI | Quarry Mapping | Vector | NSPI | DPKR | 490 | 490 | 0 | 190 | 0 | 2017-11-17 |  | 2017-11-23 | YES | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-28 |  | Signed QS | YES | To be invoiced | Delivered |  | 2017-12-18 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-18
2017-12-01 | 20 | ASI | Racine WI | Lidar/2d vector | NSPI | DPKR | 100 | 100 | 0 | 100 | 0 | 2017-12-01 |  | 2017-12-01 | YES | 2017-12-04 | 2017-12-04 | 2017-12-05 | 2017-12-04 |  | Signed QS | NA | To be invoiced | Delivered |  | 2017-12-18 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-18
2017-12-01 | 21 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 6534 | 0 | 953 | 953 | 2017-08-25 | 2017-12-20 | 2017-08-25 | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 |  | Signed QS | NO |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-28
2017-12-01 | 22 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 450 | 6084 | 0 | 6534 | 2017-12-01 | 2018-01-05 | 2017-12-01 | YES | YES | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | Signed QS | NO |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Partial AT result received. Issues in AT result for remaining area. as of now on Risk | 2017-12-28
2017-12-01 | 23 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1095 | 1095 | 0 | 337 | 337 | 2017-07-12 |  | 2017-07-12 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-28
2017-12-01 | 24 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 104 | 104 | 2017-07-17 |  | 2017-07-17 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vector Delivered Ortho To be done | 2017-12-28
2017-12-01 | 25 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 429 | 429 | 2017-09-27 |  | 2017-09-28 | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-12-28
2017-12-01 | 26 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5745 | 5745 | 0 | 2000 | 3200 | 2017-10-13 |  | 2017-10-17 | 2017-10-23 | 2017-10-25 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2017-12-28
2017-12-01 | 27 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | [5 empty] | 2017-07-10 |  | 2017-07-10 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | All blocks delivered in the Month of November however we have received feedback in december | 2017-12-28
2017-12-01 | 28 | COWI Norway | Historic Ortho-Phase3 | AT/Ortho | MADV | MNJA | 903 | 903 | 0 | 150 | 753 | 2017-12-08 |  | 2017-12-08 | YES | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 |  | ATR | NA |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2017-12-28
2017-12-01 | 29 | JRC17010 | JRC17010 | Ortho | NSPI | MNJA | 31 | 31 | 0 | 31 |  | 2017-09-01 | [5 empty] | 2017-09-05 | 2017-09-05 |  | Email | NA | To be invoiced | Delivered | [10 empty] | 7.5 CM resolution data delivered | 2017-12-28
2017-12-01 | 28 | FIRST BASE SOLUTION | Oakville | Vector | NSPI | MVRA | 641 | 641 | 0 | 45 | 0 | 2017-09-17 |  | 2017-09-18 | YES | 2017-10-23 | 2017-10-28 | 2017-11-07 |  |  | PO | NO | To be invoiced | In progress |  | 2017-10-10 | 2017-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data delivered and feedback awaited; final DTM polygons to receive for contour generation | 2018-01-02
2017-12-01 | 29 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6655 | 3647 | 3008 | 953 | 0 | 2017-12-21 | 2018-01-22 | 2017-11-06 | YES | 2017-10-11 | 2017-07-25 | 2017-08-10 | 2017-09-15 |  | Signed QS | YES | Monthly Invoice | In progress |  | 2017-12-07 |  | 1 | 0 | 2 | 2 | 0 | 0 | 0 | Minor corrections pertaining to vegetation, error points close to the ground. Corrected tiles resubmitted. | 2018-01-02
2017-12-01 | 30 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 809 | 809 | 0 | 809 | 0 | 2017-12-12 |  | 2017-11-14 | YES | 2016-11-04 | 2016-04-13 |  | 2016-10-08 |  | Signed QS | YES | Monthly Invoice | In progress |  | 2017-10-12 | 2017-10-12 | 6 | 0 | 1 | 1 | 0 | 0 | 0 | Minor corrections regarding 'Recovered' ano was due to new person joined at customer's end and we tried to have a skype session however could not materialized. | 2018-01-02
2017-12-01 | 31 | BSF-SWISSPHOTO | M7016 DOP Luzern 2017 | Ortho | MADV | MVRA | 3909 | 3909 | 0 | 0 | 0 | 2017-10-12 |  | 2017-10-12 | YES | 2017-08-30 | 2017-08-29 | 2017-08-30 | 2017-08-29 |  | Signed QS | YES | Invoiced | Delivered | 2017-12-12 | 2017-12-07 | 2017-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Count of deliverables refers blocks | 2018-01-02
2017-12-01 | 32 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2925 | 2925 | 0 | 145 | 0 | 2017-11-20 | 2017-12-20 | 2017-11-20 | YES | 2016-08-16 | 2016-08-16 |  | 2016-08-16 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Input for Four towns of 15 cm received and input for 8 more towns will be received by next week This project started a year and half ago hence details of some of the key documents status not updated in this sheet | 2018-01-02
2017-12-01 | 33 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 3920 | 3477 | 443 | 33 | 0 | 2017-11-04 | 2018-01-16 | 2017-11-06 | YES |  | 2017-09-15 |  | 2017-09-15 |  | WO | YES | Invoiced | Delivered |  | 2017-12-07 | 2017-12-14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Customer has confirmed ~ 600 hours by 22-Dec; And probably this may be the last set of input data for PR2341 project This project started a year and half ago hence details of some of the key documents status not updated in this sheet | 2018-01-02
2017-12-01 | 34 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1526 | 0 | 1526 | 0 | 1526 |  | 2018-01-05 |  | YES | [6 empty] | YES |  | To be started | [10 empty] | Input data is expected in this week | 2018-01-02
2017-12-01 | 35 | COWI Sweeden | Norrtalje | Vector | NSPI | SUHH | 2298 | 2298 | 0 | 40 | 0 | 2017-10-06 |  | 2017-10-09 | YES | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | ATR | YES | To be invoiced | Delivered |  |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2018-01-12
2017-12-01 | 36 | COWI Sweeden | Skåne Laser Summer | LiDAR | NSPI | SUHH | 651 | 651 | 0 | 555 | 0 | 2017-11-09 |  | 2017-11-09 | YES | 2017-10-10 | 2017-11-09 | 2017-11-22 | 2017-11-22 |  | ATR | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Batch 2 is rejected by GC due to Major errors | 2018-01-12
2017-12-01 | 37 | COWI Sweeden | Skåne Photo Summer | AT/Ortho | NSPI | SUHH | 560 | 368 | 192 | 167 | 201 | 2017-11-28 | 2018-01-15 | 2017-11-28 | YES | 2017-11-23 | 2017-11-22 | 2017-11-27 | 2017-11-27 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Remaining input hours is uncertain as flying is not done | 2018-01-12
2017-12-01 | 38 | CAS | Various | AT/Vector/Ortho | NSPI | NSPI | 2783 | 2783 | 0 | 261.9716 | 0 | 2017-12-23 |  | 2017-12-23 | YES | NA | YES | 2017-01-15 | 2017-01-15 |  | WO | YES | Monthly Invoice | In progress |  | 2017-12-13 |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-26
2017-12-01 | 39 | Geograma | Image Blur | Other | MADV | RRKN | 80 | 80 | 0 | 80 | 0 | 2017-12-06 |  | 2017-12-06 | YES | 2017-12-09 | YES | 2017-12-11 | 2017-12-11 |  | Signed QS | NA | To be invoiced | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-02
2017-12-01 | 40 | COWI AS | OSGB_Urban_2017_19 | Vector | MADV | AISR | 111350 | 82122 | 29228 | 8500 | 20728 | 2017-12-01 | 2018-02-01 | 2017-12-04 | Yes |  | YES |  |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 69 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-12
2017-12-01 | 41 | COWI AS | OSGB_Rular_2017_19 | Vector | MADV | AISR | 52124 | 39222 | 12902 | 5500 | 7402 | 2017-12-01 | 2018-02-17 | 2017-12-04 | Yes |  | YES |  |  |  | ATR |  | Monthly Invoice | In progress |  |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-12
2017-12-01 | 42 | XEOS | PR2574 - Breaklines and DTM | Vector | NSPI | MVRA | 154 | 154 | 0 | 154 | 0 | 2017-12-13 |  | 2017-12-14 | YES | 2017-12-20 | [5 empty] | YES |  | In progress | [11 empty] | 2018-01-02
2017-12-01 | 43 | COWI Sweeden | Lerum LiDAR additional | Vector/LiDAR | NSPI | SUHH | 805 | 805 | 0 | 412 | 393 | 2017-12-13 |  | 2017-12-15 | YES | 2017-12-12 | 2017-12-23 | 2017-12-29 | 2017-12-29 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-12
2017-12-01 | 44 | COWI DK | Madrid Ortho | Ortho | MADV | RRKN | 300 | 300 | 0 | 230 | 0 | 2017-12-12 |  | 2017-12-12 | YES | NA |  | 2017-12-14 | 2017-12-12 |  | ATR | NA | Monthly Invoice | Delivered |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-02
2017-12-01 | 45 | COWI AS | DK Satellitfoto Telezoner 2017 | AT/Ortho | MADV | PSRA | 425 | 36 | 0 | 36 | 0 | 2017-09-27 |  | 2017-09-27 | YES | 2017-09-27 | 2017-08-10 | 2017-09-27 | 2017-09-27 |  | ATR | NO | To be invoiced | Delivered |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-21
2017-12-01 | 46 | ASI | PAW PAW | vector | NSPI | DPKR | 430 | 430 | 0 | 150 | 0 | 2017-12-19 |  | 2017-12-20 | YES | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-26 |  | PO | NO | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-23
2017-12-01 | 47 | PMC | NH - forest | Ortho | NSPI | SKCY | 222 | 222 | 0 | 24 | 0 | 2017-12-20 | 2017-12-31 |  | YES | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-23 |  | PO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2018-01-03
2017-12-01 | 48 | AAM | PRJ3074501_NelsonCC | AT | MADV | MADV | 50 | 50 |  | 50 |  | 2017-12-22
2017-12-01 | 49 | AAM | PRJ3081601_Tasman2017 | AT | MADV | MADV | 22 | 22 |  | 22 |  | 2017-12-23
2017-12-01 | 50 | AAM | PRJ31205_02_Bluescope | AT | MADV | MADV | 8 | 8 |  | 8 |  | 2017-12-15
2017-12-01 | 51 | XEOS | PR2462 - Breaklines and DTM | Vector | NSPI | MVRA | 139 | 139 | 0 | 139 | 0 | 2017-12-31 |  | 2018-01-02 | [9 empty] | To be started | [11 empty] | 2018-01-02
2017-12-01 | 52 | VANSTEELANDT | R8 Mapping | Vector | MADV | MVRA | 100 | 100 | 0 | 100 | 0 | 2017-12-23 |  | 2018-01-02 |  |  | 2017-12-28 | [6 empty] | In progress | [11 empty] | 2018-01-02
2017-11-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable hours | Remaining billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Reception control date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) |  | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2017-11-01 | 1 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 | 0 | 0 | 0 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 2 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2712 | 2712 | 0 | 294 | 956 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 3 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9932.5 | 9932.5 | 0 | 16 | 536.5 | 2017-06-27 |  | 2017-06-27 | Yes | 2017-05-09 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 4 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 | 0 | 0 | 249.5 | 2017-05-27 |  | 2017-05-27 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 5 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9684 | 9384 | 300 | 1965 | 6037 | 2017-09-26 | 2017-12-20 | 2017-09-29 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 6 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 | 154 | 189 | 1070 | 2017-07-31 | 2017-12-12 | 2017-07-31 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 7 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5564 | 5564 | 0 | 0 | 0 | 2017-05-24 |  | 2017-05-24 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 8 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 0 | 455 | 455 | 2017-10-06 |  | 2017-10-09 | Yes | 2017-06-25 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 3 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 9 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 | 0 | 250 | 278 | 2017-07-07 |  | 2017-07-07 | Yes | 2017-09-12 | 2017-05-01 | Shared With TEGU | 2017-09-01 |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 5 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2017-11-30
2017-11-01 | 10 | COWI AS | DK Satellitfoto Telezoner 2017 | AT/Ortho | MADV | PSRA | 425 | 100 | 0 | 64 | 36 | 2017-09-27 |  | 2017-09-27 | YES | 2017-09-27 | 2017-08-10 | 2017-09-27 | 2017-09-27 |  | ATR | NO | To be invoiced | In progress |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-11-01 | 11 | CAS | Various | AT/Vector/Ortho | NSPI | NSPI | 1416 | 1416 | 0 | 1416 | 0 | 2017-11-29 |  | 2017-11-30 | 2017-01-15 | NA | YES | 2017-01-15 | 2017-01-15 |  | WO | YES | Monthly Invoice | In progress |  |  |  | 18 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2017-12-05
2017-11-01 | 12 | COWI AS | VICTORIA | Vector | MADV | AISR | 21104 | 21104 | 0 | 189 | 21104 | 2017-11-20 | 2017-12-15 | 2017-11-21 |  | 2017-11-14 | 2017-11-07 |  |  |  | ATR | NO | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-01
2017-11-01 | 13 | COWI DK | Dar-Morogoro | AT/Ortho/Vector/Lidar | MADV | AISR | 3767 | 4011 | 0 | 1017 | 1017 | 2017-08-31 |  | 2017-09-04 | 2017-10-09 | 2017-09-04 | 2017-09-28 | 2017-09-14 | 2017-09-06 |  | ATR | YES | Monthly Invoice | Delivered | 2017-11-16 |  |  | 9 | 1 | 0 | 0 | 0 | 0 | 0 | Prioirty 6B of Ortho Delayed | 2017-12-01
2017-11-01 | 14 | FIRST BASE SOLUTION | Oakville | Vector | NSPI | MVRA | 438 | 438 | 0 | 391 | 0 | 2017-09-17 |  | 2017-09-18 | YES | 2017-10-23 | 2017-10-28 | 2017-11-07 |  |  | PO | NO | To be invoiced | In progress |  | 2017-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Data delivered and feedback awaited; final DTM polygons to receive for contour generation | 2017-11-28
2017-11-01 | 15 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6655 | 3176 | 3479 | 482 | 482 | 2017-11-22 | 2018-01-22 | 2017-11-06 | YES | 2017-10-11 | 2017-07-25 | 2017-08-10 |  |  | Signed QS | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 1 | 14 | 0 | 0 | 0 | Received Part-07 for 482 hours on 21-Nov-17 And uncertain on time frame for remaining input data (may be between Jan-18 and Apr-18) | 2017-11-28
2017-11-01 | 16 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 904 | 904 | 0 | 904 | 0 | 2017-11-14 |  | 2017-11-14 | YES |  | 2016-04-13 |  |  |  |  | YES | Monthly Invoice | In progress |  | 2017-10-12 | 2017-10-12 | 5 | 0 | 1 | 0 | 1 | 0 | 0 | This project started a year and half ago hence details of some of the key documents status not updated in this sheet Final delivery of GRB63_27_10_Schilde was on 23-Sep-17 and disapproval received on 10-Nov-17 | 2017-11-28
2017-11-01 | 17 | BSF-SWISSPHOTO | M7016 DOP Luzern 2017 | Ortho | MADV | MVRA | 3909 | 3909 | 0 | 1021 | 0 | 2017-10-12 |  | 2017-10-12 | YES | 2017-08-30 | 2017-08-29 | 2017-08-30 |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 12 | 0 | 10 | 8 | 0 | 0 | 0 | Count of deliverables refers blocks | 2017-11-28
2017-11-01 | 18 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2925 | 2925 | 144 | 258 | 0 | 2017-11-20 | 2017-12-07 | 2017-11-20 | YES | 2016-08-16 | 2016-08-16 |  | 2016-08-16 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Input for Four towns of 15 cm received and input for 8 more towns will be received by next week This project started a year and half ago hence details of some of the key documents status not updated in this sheet | 2017-11-28
2017-11-01 | 19 | FIRST BASE SOLUTION | 1737ESSX | Vector | NSPI | RRKN | 207 | 207 | 0 | 0 | 0 | 2017-11-24 |  | 2017-11-03 | YES | 2017-11-09 | 2017-11-08 | 2017-11-24 | 2017-11-10 |  | PO | YES | To be invoiced | In progress |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Final Delivery Planned on 6th Dec 2017 | 2017-11-29
2017-11-01 | 20 | XEOS | PR2572 | LiDAR | NSPI | MVRA | 458 | 458 | 0 | 458 | 0 | 2017-11-11 |  | 2017-10-28 | YES |  | 2017-11-09 | 2017-11-13 |  |  | WO | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Delivered | 2017-11-28
2017-11-01 | 21 | IBV KRANK | Project 2017-2 | LiDAR | MADV | MVRA | 25 | 25 | 0 | 25 | 0 | 2017-10-28 |  | 2017-10-28 | YES | [5 empty] | No | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Small project of 25 hours; Feedback awaited | 2017-11-28
2017-11-01 | 22 | VANSTEELANDT | HIT-Saint Martin | LiDAR | MADV | MVRA | 70 | 70 | 0 | 5 | 0 | 2017-10-19 |  | 2017-10-23 | [6 empty] | No |  | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Strip adjustment done (by MEKS) with inappropriate values; Resubmitted after re-adjustment; No WO/Signed QS, agreed on mail | 2017-11-28
2017-11-01 | 23 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 3920 | 2396 | 1524 | 583 | 0 | 2017-11-04 | 2017-12-22 | 2017-11-06 | YES | [5 empty] | WO |  | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Customer has confirmed ~ 600 hours by 22-Dec; And probably this may be the last set of input data for PR2341 project This project started a year and half ago hence details of some of the key documents status not updated in this sheet | 2017-11-28
2017-11-01 | 24 | DIGIMAPAS | San Fabian LiDAR | LiDAR | MADV | MVRA | 20 | 20 | 0 | 20 | 0 | 2017-11-17 | [8 empty] | Signed QS |  | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | The customer has initially rejected the data for minor errors (classification of 1 or 2 points) and later accepted the same data without any corrections | 2017-11-28
2017-11-01 | 25 | BSF-SWISSPHOTO | M4006162-NL-AT Test | AT | MADV | MVRA | 70 | 70 | 0 | 70 | 0 | 2017-10-23 |  | 2017-10-24 |  | 2017-10-10 |  |  |  |  | Signed QS |  | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | AT results were not satisfactory according to customer; redoing with new APM | 2017-11-28
2017-11-01 | 26 | Geoconsult | Mauritania | AT/DTM/DSM/Ortho | MADV | MNJA | 2000 | 2000 | 0 | 70.53 | 0 | 2017-06-19 |  | 2017-06-19 | 2017-06-23 | 2017-06-19 | 2017-06-23 | 2017-06-23 | 2017-06-23 |  | Signed QS | YES | Invoiced | Delivered | 2017-11-21 | 2017-11-13 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Delivered | 2017-11-29
2017-11-01 | 27 | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MADV | MNJA | 110 | 110 | 0 | 0 | 25 | 2017-07-11 |  | 2017-07-11 | 2017-07-12 | 2017-07-24 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | Signed QS | NA | Invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 10 |  | 2017-11-29
2017-11-01 | 28 | Geoconsult | Senegal | AT/DTM/Ortho | MADV | MNJA | 0 | 0 | 0 | 0 | 0 | [12 empty] | Hold |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On Hold | 2017-11-29
2017-11-01 | 29 | Geoconsult | Algeria | AT/DTM/DSM/Ortho | MADV | MNJA | 75 | 75 | 0 | 50 | 0 | 2017-10-26 |  | 2017-10-26 | 2017-10-26 | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | Signed QS | NA | Invoiced | Delivered | 2017-11-21 | 2017-11-13 |  | 1 | 0 | 0 | 0 | 0 | 0 | 17 | Delivered | 2017-11-29
2017-11-01 | 30 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 1750 | 4784 | 953 | 953 | 2017-08-25 | 2017-12-08 | 2017-08-25 | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 |  | Signed QS | NO |  | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Received approval on to Produce AT in CIL. Submitted cost is approved For available data Production will remain continue | 2017-11-29
2017-11-01 | 31 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 0 | 6534 | 0 | 6534 |  |  |  | YES | [5 empty] | Signed QS | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Partial AT result received. Issues in AT result for remaining area. as of now on Risk | 2017-11-29
2017-11-01 | 32 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1095 | 1095 | 0 | 419 | 419 | 2017-07-12 |  | 2017-07-12 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 33 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 220 | 220 | 2017-07-17 |  | 2017-07-17 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 |  | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 0 | 2 | 0 | 0 | 0 | Delivered | 2017-11-29
2017-11-01 | 34 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 548 | 548 | 2017-09-27 |  | 2017-09-28 | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 |  | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 35 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | 3993.0003 | 3993 | 0.00034091 | 1700 | 1700 | 2017-07-10 |  | 2017-07-10 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 36 | 0 | 1 | 0 | 0 | 0 | 0 | All Data set Received | 2017-11-29
2017-11-01 | 36 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5745 | 5745 | 0 | 2164 | 5745 | 2017-10-13 |  | 2017-10-17 | 2017-10-23 | 2017-10-25 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2017-11-29
2017-11-01 | 37 | COWI DK | Zambia | 2D Vector | MADV | MNJA | 604 | 604 | 0 | 254 | 0 | 2017-08-31 |  | 2017-08-31 | 2017-09-01 | 2017-09-04 | 2017-09-01 | 2017-09-06 | 2017-09-04 |  | ATR | NA | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project can be considered as closed. If revised input received it will be considered as fresh ATR | 2017-11-29
2017-11-01 | 38 | COWI Sweeden | SE_Inlandsbanan_production-DK_2017_Mapping | AT/DTM/LiDAR/Ortho | NSPI | RRKN | 1073 | 783 | 290 | 376 | 407 | 2017-12-01 | 2017-12-12 | 2017-11-15 | 2017-11-15 | 2017-11-08 | 2017-11-15 | 2017-11-23 | 2017-11-23 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 6 | [6 empty] | 31st OCT : Partial Input 10% is expected By 1st week of Nov 3rd NOV : Not Sure, as Data Collection has happened for only 10%. Still trying on Data acquisition 7th NOV : Around 150km X 120 m LiDAR Data to be processed at CIL, but no update when will the data be provided to CIL 15th NOV : Recieved some LiDAR data for processing on 15. Quantum will be updated once the data is downloaded and checked 22nd NOV : All Inputs of LiDAR will Be Available till 12 Dec 2017. | 2017-12-01
2017-11-01 | 39 | COWI AS | HxIP | Ortho | MADV | KSAB | 5449 | 5332.7 | 116.3 | 1428 | 1290 | 2017-11-15 |  |  | YES |  | 2017-07-13 | 2017-07-13 | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 10 | 0 | 0 | 10 | 0 | 0 | 0 |  | 2017-12-01
2017-11-01 | 40 | COWI Sweeden | Skane_Spring | AT/Ortho/LiDAR/Contours | NSPI | KSAB | 2545 | 2545 | 0 | 76 | 0 | 2017-07-21 |  | 2017-07-21 | YES | 2017-08-09 | 2017-08-07 | 2017-09-11 | YES |  | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-15
2017-11-01 | 41 | SDFE | SDFE | LiDAR | MADV | SUHH | 185 | 185 | 0 | 185 | 0 | 2017-10-13 |  | 2017-10-13 | YES | 2017-10-31 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 42 | COWI Sweeden | Norrtalje | Vector | NSPI | SUHH | 2298 | 2298 | 0 | 2298 | 0 | 2017-10-06 |  | 2017-10-09 | YES | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | ATR | YES | To be invoiced | In progress |  |  |  | 2 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 43 | COWI Sweeden | Skåne Laser Summer | LiDAR | NSPI | SUHH | 651 | 651 | 0 | 96 | 555 | 2017-11-09 |  | 2017-11-09 | YES |  | 2017-11-09 | 2017-11-22 | 2017-11-22 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 44 | COWI Sweeden | Skåne Photo Summer | AT/Ortho | NSPI | SUHH | 560 | 368 | 192 | 42 | 326 | 2017-11-28 | 2017-12-31 | 2017-11-28 | YES | 2017-11-23 | 2017-11-22 | 2017-11-27 | 2017-11-27 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Remaining input hours is uncertain as flying is not done | 2017-11-29
2017-11-01 | 45 | COWI Sweeden | Skåne laser spring - additional task | LiDAR | NSPI | SUHH | 463 | 463 | 0 | 463 | 0 | 2017-10-23 |  | 2017-10-24 | YES | 2017-08-09 | 2017-08-07 | 2017-11-09 | 2017-11-08 |  | ATR | YES | To be invoiced | Approved |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 46 | Topocart | UR-10K | Vector | MADV | SKCY | 2944 | 2944 | 0 | 2344 | 2594.2 | 2017-10-11 |  | 2017-10-11 | Yes | 2017-10-12 | 2017-10-05 | 2017-10-23 | 2017-10-13 |  | PO | YES | To be invoiced | In progress |  |  |  | 3 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2017-11-28
2017-11-01 | 47 | Topocart | UR-1K | Vector | MADV | SKCY | 918 | 918 | 0 | 0 | 918 | 2017-11-08 |  | 2017-11-08 | Yes |  | 2017-11-08 |  |  |  | No | No | To be invoiced | To be Started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-28
2017-11-01 | 48 | Fmaps | Peka Mai | AT/DTM | MADV | DPKR | 63 | 63 | 0 | 63 | 0 | 2017-11-09 |  | 2017-11-09 | YES | 2017-11-13 | YES | 2017-11-13 | 2017-11-14 |  | Email | No | To be invoiced | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-15
2017-11-01 | 49 | Fmaps | Tiropai | AT/DTM | MADV | DPKR | 56 | 56 | 0 | 56 | 0 | 2017-11-13 |  | 2017-11-13 | YES | 2017-11-15 | YES | 2017-11-15 | 2017-11-15 |  | Email | No | To be invoiced | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-20
2017-11-01 | 50 | COWI Norway | Historic Ortho-Phase3 |  |  | MNJA | [6 empty] | 2017-11-30 |  | NO | [8 empty] | To be started | [10 empty] | Data is expected by 30th November | 2017-11-29
2017-11-01 | 51 | COWI Sweeden | Lerum Contours | Vector | NSPI | SUHH | 437 | 437 | 0 | 437 | 0 | 2017-10-23 |  | 2017-10-24 | YES | 2017-11-20 | 2017-11-11 | 2017-11-22 | 2017-11-22 |  | ATR | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-29
2017-11-01 | 52 | COWI AS | HxIP (QSI) | Ortho | MADV | KSAB | 11081.36 | 2433.89 | 8647.47 | 986 | 9091.29 | 2017-11-29 |  |  | YES | 2017-10-06 | 2017-07-13 |  | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2017-12-01
2017-11-01 | 53 | ASI | Quarry Mapping | Vector | NSPI | DPKR | 481 | 481 | 0 | 198 | 0 | 2017-11-17 |  | 2017-11-23 | YES | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-28 |  |  | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 delivered,client has given revised AOI so,we are redelivring the data by todau as per new AOI | 2017-12-01
2017-11-01 | 54 | TERRAQUEST | Niagara County LiDAR Processing | LiDAR | NSPI | MVRA | 1320 | 0 | 1320 | 0 | 1320 |  | 2017-11-30 | [10 empty] | To be started | [10 empty] | Input data is expected in this week | 2017-11-28
2017-11-01 | 55 | COWI DK | DK Silkeborg 3D update | Vector | MADV | RRKN | 600 | 600 | 0 | 0 | 600 | 2017-11-28 |  |  | NO | [19 empty] | Workflow Finalization inprogress | 2017-11-29
2017-11-01 | 56 | COWI Sweeden | Krangfors_Sweref99_2015 | Vector | NSPI | SUHH | 25 | 25 | 0 | 25 | 0 | 2017-11-24 |  | 2017-11-24 | YES | 2017-11-27 | 2017-11-27 | 2017-12-01 | 2017-12-01 |  | ATR | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-12-01
2017-10-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable hours | Remaining billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Reception control date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) |  | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks | Last date of Update/Review by PM
2017-10-01 | 1 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 | 0 |  | 0 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 2 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2712 | 2712 | 0 | 480 | 956 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 3 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9932.5 | 9932.5 | 0 | 2555.5 | 536.5 | 2017-06-27 |  | 2017-06-27 | Yes | 2017-05-09 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 4 | 0 | 0 | 4 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 4 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 | 0 | 621.5 | 249.5 | 2017-05-27 |  | 2017-05-27 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 5 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9684 | 9384 | 300 | 712 | 6037 | 2017-09-26 | 2017-11-20 | 2017-09-29 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 6 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 | 154 | 508 | 1070 | 2017-07-31 | 2017-11-15 | 2017-07-31 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 7 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5564 | 5564 | 0 |  | 0 | 2017-05-24 |  | 2017-05-24 | Yes | 2017-05-16 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 8 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 0 | 58 | 455 | 2017-10-06 |  | 2017-10-09 | Yes | 2017-06-25 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 9 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 | 0 | 338 | 278 | 2017-07-07 |  | 2017-07-07 | Yes | 2017-09-12 | 2017-05-01 | Shared With TEGU |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-01
2017-10-01 | 10 | FIRST BASE SOLUTION | Oakville | Vector | MADV | MVRA | 438 | 438 | 0 | 28 | 410 | 2017-09-17 |  | 2017-09-18 | NO | 2017-10-23 | 2017-10-28 |  |  |  | PO | NO | To be invoiced | In progress |  | 2017-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-18
2017-10-01 | 11 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6251 | 1010 | 4639 | 600 | 4039 | 2017-10-10 | 2017-11-07 | 2017-10-10 | YES | 2017-10-11 |  |  |  |  | Signed QS | YES | Monthly Invoice | In progress |  |  |  | 3 | 0 | 2 | 2 | 0 | 0 | 0 | Delivered Part04 priority 1 &2 and Part05 priority 1 of Project-2017-1
2017-10-01 | 12 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 316 | 316 | 0 | 316 | 0 | 2017-09-28 |  | 2017-09-28 | YES | [6 empty] | YES | Monthly Invoice | In progress |  | 2017-10-12 | 2017-10-12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | Feedback awaited
2017-10-01 | 13 | BSF-SWISSPHOTO | M7016 DOP Luzern 2017 | Ortho | MADV | MVRA | 4300 | 4300 | 0 | 1500 | 0 | 2017-10-12 |  | 2017-08-23 | YES | 2017-08-30 |  |  |  |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 11 | 0 | 9 | 6 | 0 | 0 | 0 | Count of deliveries as per the blocks defined for internal convenience
2017-10-01 | 14 | UGANDA_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2819 | 2819 | 0 | 2739 | 0 | 2017-09-18 |  | 2017-09-21 | YES | 2016-08-16 | 2016-08-16 |  | 2016-08-16 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 15 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 3920 | 0 | 1523 | 0 | 1523 |  | 2017-11-06
2017-10-01 | 16 | Topocart | CE | Vector | MADV | SKCY | 2337 | 0 | 0 | 0 | 0 | 2017-06-30 |  | 2017-06-30 | Yes | 2017-07-08 | 2017-07-04 | 2017-07-07 | 2017-07-07 |  | PO | YES | Invoiced | Delivered | 2017-10-26 | 2017-10-12 | 2017-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 17 | ROSSI | RIM-5K mapping | Vector | MADV | SKCY | 610 | 610 | 0 | 610 | 0 | 2017-10-03 |  | 2017-10-04 | Yes | 2017-10-09 | 2017-10-05 | 2017-10-10 | 2017-10-10 |  | Signed QS | Yes | Invoiced | Delivered | 2017-10-31 | 2017-10-31 | 2017-11-02 | 2 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 18 | ROSSI | RIM-1K mapping | Vector | MADV | SKCY | 430 | 430 | 0 | 180 | 0 | 2017-09-21 |  | 2017-09-21 | YES | 2017-09-23 | 2017-09-20 | 2017-09-25 | 2017-09-27 |  | Signed QS | YES | Invoiced | Delivered | 2017-10-31 | 2017-10-31 | 2017-11-02 | 2 | 0 | 2 | 1 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 19 | CAS | Various | AT/Vector/Ortho | NSPI | NSPI | 466 | 466 | 0 | 466 | 0 | 2017-10-31 |  | 2017-10-31 | 2017-01-15 | NA | YES | 2017-01-15 | 2017-01-15 |  | WO | YES | Monthly Invoice | In progress |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 20 | SDFE | Geosjaelland | Vector | MADV | NSPI | 12498 | 12498 | 0 | 3000 | 0 | 2017-06-18 |  | 2017-06-20 | 2017-06-08 | 2017-06-09 | YES | 2017-06-10 | 2017-06-10 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 5 | 0 | 3 | 1 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 21 | COWI AS | VICTORIA | Vector | MADV | NSPI | 21104 | 0 | 21104 | 0 | 21104 |  | 2017-11-20 | [7 empty] | ATR | NO | Monthly Invoice | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A3 images received on 30-Oct | 2017-11-02
2017-10-01 | 22 | SDFE | SDFE | LiDAR | MADV | SUHH | 185 | 185 | 0 | 31 | 154 | 2017-10-13 |  | 2017-10-13 | YES | 2017-10-31 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 23 | Groupe DEGAUD | PAYS de MONTBELIARD | AT | MADV | SUHH | 995 | 995 | 0 | 929 | 0 | 2017-09-18 |  | 2017-09-18 | YES | 2017-09-26 | 2017-09-25 | 2017-10-06 | 2017-10-06 |  | Signed QS | YES | To be invoiced | Delivered |  | 2017-11-24 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-29
2017-10-01 | 24 | COWI DK | Dar-Morogoro | AT/Ortho/Vector/Lidar | MADV | AISR | 3767 | 3767 | 0 | 2794 | 773 | 2017-08-31 |  | 2017-09-04 | 2017-10-09 | 2017-09-04 | 2017-09-28 | 2017-09-14 | 2017-09-06 |  | YES | YES | Monthly Invoice | In progress |  |  |  | 15 | 1 | 0 | 0 | 0 | 0 | 0 | Vector Mapping Priority 3 Delay | 2017-11-02
2017-10-01 | 25 | Geoconsult | Lebenon | Vector | MADV | AISR | 100 | 100 | 0 | 100 | 100 | 2017-09-29 |  | 2017-09-30 | 2017-10-10 | 2017-10-06 | 2017-10-08 | 2017-10-10 | 2017-10-10 |  | YES | NA | To be invoiced | Delivered |  |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | Still discussion ongoing 1st feedback , which should not be considered as major feedback due to requirements unclear | 2017-11-02
2017-10-01 | 26 | Geoconsult | Mauritania | AT/DTM/DSM/Ortho | MADV | MNJA | 2000 | 2000 | 0 | 133 | 74 | 2017-06-19 |  | 2017-06-19 | 2017-06-23 | 2017-06-19 | 2017-06-23 | 2017-06-23 | 2017-06-23 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Received data for all 13 Blocks | 2017-11-02
2017-10-01 | 27 | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MADV | MNJA | 135 | 110 | 25 | 23 | 23 | 2017-07-11 | 2017-11-09 | 2017-07-11 | 2017-07-12 | 2017-07-24 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | Signed QS | NA | Invoiced | In progress |  |  |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | GCP description sheet for 1 block is remaining | 2017-11-02
2017-10-01 | 28 | Geoconsult | Senegal | AT/DTM/Ortho | MADV | MNJA | [17 empty] | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Go ahead from end client is yet to receive - Pipeline | 2017-11-02
2017-10-01 | 29 | Geoconsult | Algeria | AT/DTM/DSM/Ortho | MADV | MNJA | 58 | 58 | 0 | 25 | 0 | 2017-10-26 |  | 2017-10-26 | 2017-10-26 | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 |  | Signed QS | NA |  | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 30 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 1750 | 4784 | 500 | 6534 | 2017-08-25 | 2017-11-02 | 2017-08-25 | 2017-10-12 | 2017-10-13 | 2017-10-12 | 2017-10-16 | 2017-10-13 |  | Signed QS | NO |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AT results for North area received, Currently Test area can be initiated and then production for North Area. Data is not available for South Area. Remaining area can be availabe from 24th October | 2017-11-02
2017-10-01 | 31 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 0 | 6534 | 0 | 6534 |  | 2017-12-28 | [7 empty] | Signed QS | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 Flight lines missing hence no Input received. Production plan can be planned from new Year | 2017-11-02
2017-10-01 | 32 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1031 | 1031 | 0 | 200 | 741 | 2017-07-12 |  | 2017-07-12 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-04 | 2017-09-04 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 33 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 200 | 836 | 2017-07-17 |  | 2017-07-17 | 2017-09-04 | 2017-09-05 | 2017-09-04 | 2017-09-21 | 2017-09-05 |  | Signed QS | YES |  | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 34 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 500 | 579 | 2017-09-27 |  | 2017-09-28 | 2017-09-29 | 2017-10-03 | 2017-09-29 | 2017-10-16 | 2017-10-03 |  | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 35 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | 3993.0003 | 3993 | 0.00034091 | 958 | 1200 | 2017-07-10 |  | 2017-07-10 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | All Data set Received | 2017-11-02
2017-10-01 | 36 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5745 | 2164 | 3581 | 0 | 5745 | 2017-10-13 | 2017-12-01 | 2017-10-17 | 2017-10-23 | 2017-10-25 | 2017-10-23 | 2017-10-25 | 2017-10-25 |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1) Pilot Block: - Input data for all 8 pilot blocks are available in CIL 2) Till date in CIL 40% of the data is available. HDD containing 30% data is being dispatched from Norway and available in CIL by First week of November 3) Remaining 30% of the data will be available in CIL by End of December or January First week | 2017-11-02
2017-10-01 | 37 | COWI DK | Zambia | 2D Vector | MADV | MNJA | 604 | 604 | 0 | 254 | 0 | 2017-08-31 |  | 2017-08-31 | 2017-09-01 | 2017-09-04 | 2017-09-01 | 2017-09-06 | 2017-09-04 |  | ATR | NA | Monthly Invoice | Delivered |  |  |  | 8 | 2 | 0 | 0 | 0 | 0 | 0 | Project Delivered however not closed as additional data to be received in the Month of November | 2017-11-02
2017-10-01 | 38 | ASI | 4410_Quarries | DTM | NSPI | SUHH | 60 | 60 | 0 | 60 | 0 | 2017-10-04 |  | 2017-10-05 | YES | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 |  | Signed QS | YES | To be invoiced | Delivered |  | 2017-10-17 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 39 | Fmaps | Tassenberg | AT/DTM | MADV | DPKR | 43 | 43 | 0 | 43 | 0 | 2017-10-06 |  | 2017-10-06 | YES | 2017-10-09 | YES | 2017-10-09 | 2017-10-09 |  | NO | NO | Invoiced | Delivered |  | 2017-10-16 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-13
2017-10-01 | 40 | COWI AS | HxIP | Ortho | MADV | KSAB | 16955 | 5993 | 10962 | 1369 | 0 |  |  |  | YES | [5 empty] | ATR | YES | Monthly Invoice | In progress |  |  |  | 6 | 0 | 0 | 6 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 41 | COWI Sweeden | Gothenburg | AT/Ortho/LiDAR | NSPI | KSAB | 1010 | 1010 | 0 | 188 | 0 | 2017-06-16 |  | 2017-06-16 | YES | 2017-07-04 | 2017-07-01 | 2017-07-02 | YES |  | WO | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 188 | Increase in hours is due to Bridge correction in Stereo & PS with reference to vector data | 2017-10-28
2017-10-01 | 42 | COWI Sweeden | ParLerÖck | AT/Ortho | NSPI | KSAB | 361 | 361 | 0 | 83 | 0 | 2017-06-16 |  | 2017-06-16 | YES | 2017-07-04 | 2017-07-01 | 2017-07-08 | YES |  | WO | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 8 | Increase in hours is due to Bridge correction in Stereo & PS with reference to vector data | 2017-10-28
2017-10-01 | 43 | COWI Sweeden | ParLerÖck - Lerum | LiDAR | NSPI | KSAB | 984 | 984 | 0 | 886 | 0 | 2017-06-29 |  | 2017-06-29 | YES | 2017-09-01 | 2017-08-31 | 2017-09-11 | YES |  | WO | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-10-28
2017-10-01 | 44 | COWI Sweeden | Stockholm | AT/Ortho/LiDAR/Contours | NSPI | KSAB | 5142 | 5142 | 0 | 859 | 0 | 2017-07-31 |  | 2017-07-31 | YES | 2017-07-04 | 2017-07-02 | 2017-07-05 | YES |  | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-10-28
2017-10-01 | 45 | COWI Sweeden | Skane_Spring | AT/Ortho/LiDAR/Contours | NSPI | KSAB | 2545 | 2545 | 0 | 800 | 0 | 2017-07-21 |  | 2017-07-21 | YES | 2017-08-09 | 2017-08-07 | 2017-09-11 | YES |  | ATR | YES | To be invoiced | In progress |  |  |  | 2 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2017-10-28
2017-10-01 | 46 | Topocart | UR-10K | Vector | MADV | SKCY | 2944.2 | 2944.2 | 0 | 350 | 2594.2 | 2017-10-11 |  | 2017-10-11 | Yes | 2017-10-12 | 2017-10-05 | 2017-10-23 | 2017-10-13 |  | PO | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 47 | COWI AS | DK Satellitfoto Telezoner 2017 | AT/Ortho | MADV | PSRA | 425 | 197 | 0 | 97 | 100 | 2017-09-27 |  | 2017-09-27 | YES | 2017-09-27 | 2017-08-10 | 2017-09-27 | 2017-09-27 |  | ATR | NO | To be invoiced | In progress |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 150 |  | 2017-11-01
2017-10-01 | 48 | WOODS | Kaikoura MLS Road Mapping - Zone-4 | LiDAR | NSPI | MVRA | 30 | 30 | 0 | 30 | 0 | 2017-10-09 |  | 2017-10-10 | YES | 2017-09-19 |  |  |  |  | Signed QS | NO | To be invoiced | Delivered |  | 2017-10-05 |  | 1 | 0 | 1 | 1 | 0 | 0 | 0
2017-10-01 | 49 | LANGAN | Mexico | AT/DTM/Ortho | NSPI | MVRA | 105 | 105 | 0 | 105 | 0 | 2017-10-04 |  | 2017-10-04 | YES | 2017-10-06 | 2017-10-06 |  |  |  | Signed QS | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 50 | COWI Sweeden | Norrtalje | Vector | NSPI | SUHH | 2298 | 2298 | 0 | 1850 | 448 | 2017-10-06 |  | 2017-10-09 | YES | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-12 |  | ATR | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-10-31
2017-10-01 | 51 | XEOS | PR2637 | LiDAR | NSPI | MVRA | 4 | 4 | 0 | 4 | 0 | 2017-10-11 |  | 2017-10-11 | YES | [5 empty] | No | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | It is only 4 hours job
2017-10-01 | 52 | VANSTEELANDT | SEL212_Powerline | LiDAR | MADV | MVRA | 15 | 15 | 0 | 15 | 0 | 2017-10-12 | [10 empty] | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Feedback awaited
2017-10-01 | 53 | Fmaps | Nilsson | AT/DTM | MADV | DPKR | 13 | 13 | 0 | 13 | 0 | 2017-10-23 |  | 2017-10-23 | YES | 2017-10-23 | 2017-10-23 | 2017-10-24 | 2017-10-24 |  | NO | NO | To be invoiced | Delivered |  | 2017-10-27 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 54 | VANSTEELANDT | Namur_Citadelle | LiDAR | MADV | MVRA | 4 | 4 | 0 | 4 | 0 | 2017-10-23 | [10 empty] | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | It is only 4 hours job
2017-10-01 | 55 | VANSTEELANDT | HIT-Saint Martin | LiDAR | MADV | MVRA | 70 | 70 | 0 | 70 | 0 | 2017-10-19 |  | 2017-10-23 | [8 empty] | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 56 | WOODS | Kaikoura MLS Road Mapping - Zone-2 | LiDAR | NSPI | MVRA | 50 | 50 | 0 | 50 | 0 | 2017-10-18 |  | 2017-10-18 | YES | [7 empty] | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
2017-10-01 | 57 | XEOS | PR2646 | LiDAR | NSPI | MVRA | 40 | 40 | 0 | 40 | 0 | 2017-10-12 | [10 empty] | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 58 | Fmaps | Horne | AT/DTM | MADV | DPKR | 56 | 56 | 0 | 56 | 0 | 2017-10-25 |  | 2017-10-25 | YES | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 |  |  | NO | To be invoiced | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2017-11-02
2017-10-01 | 59 | COWI Sweeden | SE_Inlandsbanan_production-DK_2017_Mapping | AT/DTM/LiDAR/Ortho | NSPI | RRKN | 1934 | 0 | 1934 | 0 | 1934 | [23 empty] | Input is expected By 1st week of Nov | 2017-10-31
2017-10-01 | 60 | FIRST BASE SOLUTION | 1737ESSX | Vector | NSPI | MVRA | 207 | 0 | 207 | 0 | 207 | [23 empty] | Input is expected by 01-Nov-17
2017-10-01 | 62 | XEOS | PR2572 | LiDAR | NSPI | MVRA | 458 | 229 | 229 | 30 | 199 | 2017-10-28 | 2017-11-03 | 2017-10-28 | [6 empty] | WO | NO | To be invoiced | To be started | [10 empty] | Query raised regarding minimum water body size for classification, answer awaited
2017-10-01 | 63 | IBV KRANK | Project 2017-2 | LiDAR | MADV | MVRA | 25 | 25 | 0 | 0 | 0 | 2017-10-28 | 2017-10-30 | 2017-10-28 | [6 empty] | No | NO | To be invoiced | To be started | [10 empty] | Tile grid is not available
2017-10-01 | 64 | VANSTEELANDT | ELIA CLAS | LiDAR | MADV | MVRA | 20 | 20 | 0 | 20 | 0 | 2017-10-25 |  | 2017-10-26 | [6 empty] | No | NO | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | S.NO | Client Name | Project Name | Servicelines | PFM | PM | Project Billable hours | Available Hours of Received Input | Pending Hours of Not Received Input | Month Billable hours | Remaining billable hours | Date of Input Reciept | Expected date of input(for partial and not available inputs) | Reception control date | Defined AQLs | KoM Date | WF/GL available (Date) | Project Plan with Customer (Date) | Project Plan in CIPM (Date) |  | Form of Agreed Project Contract | Risk log updated | Invoice | Project Status | Project Closure meeting (Date) | Customer Satsifaction Survey (CSS) Sent Date | CSS feedback receipt date | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks
2017-09-01 | 1 | CAS | Various | AT/Vector/Ortho | NSPI | NSPI | 238 |  | 0 | 238 |  | 2017-09-12 |  | 2017-09-12 | 2017-01-15 | NA | YES | NA | 2017-01-15 |  | NA | YES | Monthly Invoice | In progress |  |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | Status meetings-based on project requirements
2017-09-01 | 2 | SDFE | Geosjaelland | Vector | MADV | NSPI | 12498 |  | 0 | 3200 |  | 2017-06-18 |  | 2017-06-20 | 2017-06-08 | 2017-06-09 | YES | 2017-06-10 | 2017-06-10 |  | NA | YES | Monthly Invoice | In progress | IP | IP | IP | 4 | 0 | 4 | 0 | 0 | 0 | 0 | Weekly status update to the customer via Email
2017-09-01 | 3 | COWI AS | KCDK | Vector | MADV | NSPI | 3220 |  | 0 | 822 |  | 2017-06-21 |  | 2017-06-27 | 2017-07-17 | 2017-07-20 | YES | 2017-07-21 | 2017-07-21 |  | NA | YES | Monthly Invoice | In progress | IP | IP | IP | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Weekly status update to the customer via Email
2017-09-01 | 4 | BSF-Swissphoto | Telleborg | AT/Ortho | MADV | AISR | 1300 | 0 | 0 | 0 | 0 | 2017-06-06 |  | 2017-06-06 | YES | 2017-06-16 | YES | 2017-08-10 | 2017-06-16 |  | YES | YES | Invoiced | Delivered |  | 2017-09-14 | 2017-10-09 | 0 | 0 | 0 |  | 0 |  | 0 | Full invoiced raised on 13/09
2017-09-01 | 5 | FBS | Ottawa | AT/Ortho | NSPI | AISR | 307 | 78 | 0 | 78 | 0 | 2017-08-15 |  | 2017-08-16 | YES | 2017-07-26 | YES | 2017-08-31 | 2017-08-18 |  | YES | YES | Invoiced | Delivered | 2017-09-15 | 2017-09-14 | 2017-09-14 | 3 | 0 | 3 | NA | 0 |  | 0
2017-09-01 | 6 | COWI DK | Dar-Morogoro | AT/Ortho/Vector/Lidar | MADV | AISR | 3249 | 1700 | 1549 | 200 | 1349 | 2017-08-31 | 2017-10-15 | 2017-09-04 | YES | 2017-09-04 | YES | 2017-09-14 | 2017-09-06 |  | YES | YES |  | In progress |  |  |  | 3 | 0 | 3 | NA | 0 |  | 0 | Inputs will be available in segmentation due to weather conditions and flying issues
2017-09-01 | 7 | Geoconsult | Mauritania | AT/DTM/DSM/Ortho | MADV | MNJA | 2000 | 1821 | 179 | 180 | 179 | 2017-06-19 | 2017-10-11 | 2017-06-19 | Yes | YES | YES | 2017-06-23 | 2017-06-23 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Inputs still awaited for GCP's discription sheet in block "Atar" & request for revised GCP's in block "Akjoujt"
2017-09-01 | 8 | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MADV | MNJA | 135 | 95 | 40 | 0 | 40 | 2017-07-11 |  | 2017-07-11 | Yes | YES | YES | 2017-07-12 | 2017-07-12 |  | Signed QS | NA | Invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Input received in phase, Currently GCP sheet for 2 twon is not received due to area flodded as informed by client
2017-09-01 | 9 | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 0 | 6534 | 0 | 6534 | 2017-08-25 | 2017-10-10 | 2017-08-25 | YES | [5 empty] | Signed QS | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Input Received in phases, Work description and AT result is not received. AT pending for Gloppen area. Test area pending due to AT inputs are not available.
2017-09-01 | 10 | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MADV | MNJA | 6534 | 0 | 6534 | 0 | 6534 |  | 2017-10-30 |  | YES | [5 empty] | Signed QS | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 Flight lines missing hence no Input received. Flying is delayed due to rain
2017-09-01 | 11 | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MADV | MNJA | 1031 | 1031 | 0 | 71 | 960 | 2017-07-12 |  | 2017-07-12 | Yes |  |  | 2017-09-04 | 2017-09-04 |  | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
2017-09-01 | 12 | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1070 | 1070 | 0 | 718 | 352 | 2017-07-17 |  | 2017-07-17 | Yes | [5 empty] | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
2017-09-01 | 13 | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MADV | MNJA | 1109 | 1109 | 0 | 0 | 1109 | 2017-09-27 |  | 2017-09-28 | YES | [5 empty] | Signed QS | YES |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 14 | Digital Globe | Nigeria Oil Theft Analysis | Vector | NSPI | MNJA | 325 | 325 | 0 | 0 | 0 | 2017-07-24 |  | NA | Yes | YES | YES | 2017-08-04 | 2017-08-04 |  | Signed QS | NA | To be invoiced | Delivered |  | 2017-09-13 | 2017-09-13 | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 15 | COWI Norway | Historical Orthophoto-2017_Hordaland-P1 | AT/Ortho | MADV | MNJA | 3993.0003 | 3600 | 393.0003 | 958 | 3000 | 2017-07-10 | 2017-10-23 | 2017-07-10 | Yes | YES | YES | YES | YES |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Input received in phases - approx 1 month
2017-09-01 | 16 | COWI Norway | Historical Orthophoto-2017_Oppland_and_Hedemark-P2 | AT/Ortho | MADV | MNJA | 5410 | 0 | 5410 | 0 | 5410 |  | 2017-10-10 |  | YES | [5 empty] | ATR | NO | Monthly Invoice | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 17 | COWI DK | Zambia | 2D Vector | MADV | MNJA | 604 | 604 | 0 | 350 | 254 | 2017-08-31 |  | 2017-08-31 | Yes | YES | YES | YES | YES |  | NO | NA | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | All the input data received
2017-09-01 | 18 | JRC | 17010 | AT/Ortho | NSPI | MNJA | 63 | 63 | 0 | 63 | 0 | 2017-09-01 |  | NA | Yes | YES | YES | 2017-09-05 | 2017-09-05 |  | Signed QS | NA | To be invoiced | Delivered |  | 2017-09-19 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Small project Reception not shared, discussion completed via email, CSS form not filled by client. Comment received via email
2017-09-01 | 19 | JRC | Miligan | AT | NSPI | MNJA | 44 | 44 | 0 | 44 | 0 | 2017-09-01 |  | NA | NA | NA | NA | NA | YES |  | NO | NA | To be invoiced | Delivered |  | 2017-09-20 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Small project Reception not shared, discussion completed via email, CSS form not filled by client. Comment received via email
2017-09-01 | 20 | ASI | Westwood | AT/Ortho | NSPI | SUHH | 690 | 230 | 0 | 230 | 0 | 2017-08-10 |  | 2017-08-10 | Yes | 2017-07-12 | YES | 2017-07-12 | 2017-07-12 |  | PO | YES | Invoiced | Delivered |  | 2017-09-15 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 21 | Groupe DEGAUD | PAYS de MONTBELIARD | Strip adjustment/LiDAR | MADV | SUHH | 834 | 784 | 0 | 784 | 0 | 2017-08-16 |  | 2017-08-16 | Yes | 2017-09-07 | YES | 2017-09-06 | 2017-09-08 |  | Signed QS | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 22 | COWI AS | HxIP | Ortho | MADV | KSAB | 14199 | 1031 | 0 | 388.6 | 0 | 2017-09-08 |  | NA | YES | YES | YES | YES | YES |  | No | YES | Monthly Invoice | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | All the input data received, Issues in SGM filtration
2017-09-01 | 23 | COWI Sweeden | ParLerÖck | AT/Ortho | NSPI | KSAB | 353 | 353 | 0 | 140 | 0 | 2017-06-16 |  | 2017-06-16 | YES | 2017-07-04 | 2017-07-01 | 2017-07-08 | YES |  | WO | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 24 | COWI Sweeden | ParLerÖck - Lerum | LiDAR | NSPI | KSAB | 593 | 593 | 0 | 98 | 0 | 2017-06-29 |  | 2017-06-29 | YES | 2017-09-01 | 2017-08-31 | 2017-09-11 | YES |  | WO | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 405 | Increase in hours is due to Scpoe as per Swedish contract was different from what we have executed as per WO received for Lerum -LiDAR
2017-09-01 | 25 | COWI Sweeden | Stockholm | AT/Ortho/LiDAR | NSPI | KSAB | 4927 | 4927 | 0 | 996 | 0 | 2017-07-31 |  | 2017-07-31 | YES | 2017-07-04 | 2017-07-02 | 2017-07-05 | YES |  | No | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
2017-09-01 | 26 | COWI Sweeden | Kungsbacka | AT/Ortho | NSPI | KSAB | 429 | 429 | 0 | 239 | 0 | 2017-07-21 |  | 2017-07-21 | YES | 2017-08-21 | 2017-07-28 | 2017-08-25 | YES |  | ATR | YES | To be invoiced | Delivered |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 27 | COWI Sweeden | Skane | AT/Ortho/LiDAR | NSPI | KSAB | 2242 | 2242 | 0 | 1028 | 573 | 2017-07-21 | 2017-10-03 | 2017-07-21 | YES | 2017-08-09 | 2017-08-07 | 2017-09-11 | YES |  | No | YES | To be invoiced | In progress |  |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 218 | Approved Images are getting uploaded. Change in scope and water classification for FID08 to FID11 added additional hours.
2017-09-01 | 28 | PMC | SW-PA-orthophoto warping | Ortho | NSPI | SKCY | 120 | 0 | 0 | 50 | 0 | 2017-07-13 |  | 2017-07-15 | Yes | 2017-07-27 | 2017-07-25 | 2017-07-27 | 2017-07-27 |  | PO | YES | Invoiced | Delivered | 2017-09-15 | 2017-09-15 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 29 | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MADV | MVRA | 6251 | NO | 5226 | 1025 |  | PARTIAL | 2017-11-01 | NO | Weekly | YES | YES | YES | YES |  | YES | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Part wise inputs are being received; 650 / 2536 Sq Km received so far
2017-09-01 | 30 | VANSTEELANDT | GRB | Vector | MADV | MVRA | 345 | NO | 0 | 345 |  | PARTIAL | Continuous | NO | Weekly | NA | YES | YES | YES |  | YES | YES | Monthly Invoice | In progress |  | 2017-10-12 | 2017-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Two more phases expected; one in Oct and another in Nov
2017-09-01 | 31 | XEOS | PR2341 | LiDAR | NSPI | MVRA | 483 | NO | 0 | 483 |  | PARTIAL | Mid of Nov-17 | NO | Weekly | NA | YES | NA | YES |  | YES | YES | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 32 | BSF-Swissphoto | M7016 DOP Luzern 2017 | Ortho | MADV | MVRA | 4590 | YES | 0 | 1500 |  | YES |  | 16-Aug-17 & 23-Aug-17 | Weekly | YES | YES | YES | YES |  | YES | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 33 | VANSTEELANDT | ELIA Classification | LiDAR | MADV | MVRA | 35 | NO | 0 | 35 |  | YES |  | NO | NA | NA | NA | NA | NA |  | YES | NA | To be invoiced | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 34 | COWI Norway | Nord-Trondelag2016-SOR-Snasa_Steinkjer | Vector | MADV | KMRE | 0 | 0 |  | 0 | [13 empty] | Delivered |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 35 | COWI Norway | Østfold 2017 | AT/Vector/Ortho | MADV | KMRE | 1100 | 1100 |  | 170 | 0 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0
2017-09-01 | 36 | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV | KMRE | 2672 | 2672 |  | 1102 | 1500 | 2017-05-09 |  | 2017-05-09 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 37 | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV | KMRE | 9433 | 9433 |  | 2152 | 3369 | 2017-06-27 |  | 2017-06-27 | Yes | 2017-05-09 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 4 | 0 | 0 | 2 | 0 | 0 | 0
2017-09-01 | 38 | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV | KMRE | 9367 | 9367 |  | 1538 | 1106 | 2017-05-27 |  | 2017-05-27 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 5 | 0 | 0 | 5 | 0 | 0 | 0
2017-09-01 | 39 | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV | KMRE | 9353 | 9353 | 1000 | 0 | 6749 | 2017-09-26 |  | 2017-09-29 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Part1 is ready for AT
2017-09-01 | 40 | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV | KMRE | 3510 | 3510 |  | 308 | 1696 | 2017-07-31 |  | 2017-07-31 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 41 | COWI Norway | Oppland FKB-C 2017 | Vector | MADV | KMRE | 5921 | 5921 |  | 5 | 0 | 2017-05-24 |  | 2017-05-24 | Yes | 2017-05-16 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | Delivered |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 42 | COWI Norway | Midthordland 2017 | AT/Ortho | MADV | KMRE | 513 | 513 | 513 | 0 | 513 |  | 2017-10-06 |  | Yes | [5 empty] | ATR | YES | Monthly Invoice | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 43 | COWI Norway | Oslo Update - 2017 | Vector | MADV | KMRE | 816 | 816 |  | 0 | 816 | 2017-07-07 |  | 2017-07-07 | Yes | 2017-09-12 | 2017-05-01 |  |  |  | ATR | YES | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 44 | Fmaps | Koromiko | AT/DTM | MADV | DPKR | 29 | 0 | 0 | 20 | 0 | YES | YES | YES | YES | YES | YES | YES | YES |  | NA | NO | Invoiced | Delivered |  | 2017-09-05 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 45 | Fmaps | Titoki | AT/DTM | MADV | DPKR | 205 | 0 | 0 | 205 | 0 | YES | YES | YES | YES | YES | YES | YES | YES |  | NA | NO | To be invoiced | Delivered |  | 2017-09-15 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 46 | FBS | 1737HALT | Vector | NSPI | MVRA | 588 | NO | 0 | 588 |  | YES |  | NO | Daily | YES | YES | YES | YES |  | NO | NO | To be invoiced | Delivered |  | 2017-10-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 47 | VANSTEELANDT | A11-Calibration+Classification | LiDAR | MADV | MVRA | 28 | NO | 0 | 28 |  | YES |  | NO | NA | NA | NA | NA | NA |  | YES | NA | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 48 | Uganda_MLHUD | Uganda_WB | AT/DTM/Ortho | MADV | MVRA | 2819 | NA | 0 | 340 |  | PARTIAL | Mid of Sep-17 | 14-09-17 (missing img) | Weekly | YES | YES | YES | YES |  | NO | NO | Monthly Invoice | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | south part images are missing
2017-09-01 | 49 | Topocart | SCS | Vector | MADV | SKCY | 2009 | 0 | 0 | 0 | 0 | 2017-06-15 |  | 2017-06-15 | Yes | 2017-06-22 | 2017-06-16 | 2017-06-26 | 2017-06-22 |  | PO | YES | Invoiced | Delivered |  |  |  | 1 | 0 | 2 | 2 | 0 | 0 | 0 | Client corrections
2017-09-01 | 50 | Topocart | CE | Vector | MADV | SKCY | 2337 | 0 | 0 | 0 | 0 | 2017-06-30 |  | 2017-06-30 | Yes | 2017-07-08 | 2017-07-04 | 2017-07-07 | 2017-07-07 |  | PO | YES | To be invoiced | Client corrections |  |  |  | 1 | 0 | 4 | 0 | 4 | 2 | 0 | Client corrections
2017-09-01 | 51 | Groupe DEGAUD | PAYS de MONTBELIARD | AT | MADV | SUHH | 995 | 995 | 0 | 66 | 929 | 2017-09-18 |  | 2017-09-18 | YES | 2017-09-26 | YES | 2017-10-06 | 2017-10-06 |  | Signed QS | YES | To be invoiced | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 53 | ROSSI | RIM-5K mapping | Vector | MADV | SKCY | 230 | 230 | 0 | 0 | 230 | 2017-10-03 |  |  | No | [5 empty] | No | NO |  | To be started |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 54 | ROSSI | RIM-1K mapping | Vector | MADV | SKCY | 430 | 430 | 0 | 250 | 180 | 2017-09-21 |  | 2017-09-19 | YES | 2017-09-23 | 2017-09-20 |  |  |  | Signed QS | YES |  | In progress |  |  |  | 1 | 0 | 1 | 1 | 0 | 0 | 0
2017-09-01 | 55 | COWI AS | VICTORIA | Vector | MADV | NSPI | 21104
2017-09-01 | 56 | FBS | Oakville | Vector | MADV | PSRA | 358 | 0 | 358 | 358 | 0 | 2017-10-02 | 2017-10-17 |  | YES |  | 2017-10-02 |  |  |  | PO | NO |  | Hold |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | input not recieved
2017-09-01 | 57 | Geoconsult | Lebenon | Vector | MADV | AISR | 100 |  |  | 0 | 100
2017-09-01 | 58 | WOODS | Kaikoura MLS Road Mapping | Vector | NSPI | MVRA | 70 | 70 | 0 | 70 | 0 | 2017-09-15 |  |  | YES | 2017-09-19 | 2017-09-19 | 2017-09-21 | 2017-09-21 |  | Signed QS | YES | To be invoiced | Delivered |  | 2017-10-05 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0
2017-08-01 |  | Client Name | Project Name | Servicelines | PM | Project Billable hours | Month Billable hours | Price | Currency | Signed QS available | Signed ATR available | Signed WO/PO available | Project Plan with Customer | Project Plan in CIPM | KoM / CIPM | WF/GL available | Risk log updated | Invoice | Project Status | [8 empty] | Deliveries | Delayed deliveries | Customer Feedbacks (count of feedbacks) | Minor corrections | Fail | Double Fail | Increase turnover (in hours) | Remarks
|  | Topocart | SCS | Vector | SKCY | 2009 | 2009 | 20088.78 | USD | NO | NA | YES | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 5 | 0 | 1 | 1 | 0 | 0 | 0
|  | Topocart | CE | Vector | SKCY | 2337 | 2337 | 23371.31 | USD | NO | NA | YES | Yes | Yes | YES | YES | YES |  | In progress | [8 empty] | 6 | 0 | 6 | 2 | 4 | 3 | 55 | Additional hours negotiated for density issues
|  | IBV KRANK | GZ5042-Project 2017-1 | LiDAR | MVRA | 6251 | 671 | 62510 | EURO | NO | NA | NA | YES | YES | NO | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0
|  | BSF-Swissphoto | Telleborg | AT/Ortho | AISR | 1300 | 300 | 13000 | EURO | YES | NA | YES | YES | YES | YES | YES | YES | To be invoiced | Delivered | [8 empty] | 5 | 0 | 5 |  | 0 |  | 0
|  | COWI AS | OSGB-DPN | Vector | AISR | 5092 | 2941 | 322069 | DKK | NO | YES | YES | NA | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 14 | 0 | 13 |  | 1 |  | 0 | Park "Broads" rejected due to scope change
|  | FBS | Ottawa | AT/Ortho | AISR | 307 | 229 | 4375 | CAD | YES | NA | YES | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 1 |  | 1 |  | 0 | Pilot Redelivered due to projections co-ordinates issue and some requested DTM corrections
|  | CAS | Various | AT/Vector/Ortho | NSPI | 497 | 497 | 4970 | USD | NA | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 33 | 0 | 1 |  | 0 |  | 0 | All the jobs delivered which are planned planned in the month of August
|  | SDFE | Geosjaelland | Vector | NSPI | 12498 | 3200 | 224000 | DKK | NA | YES | NA | YES | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 3 | 0 | 3 |  | 0 |  | 0 | All the planned municiaplaities are delivered
|  | BSF-Swissphoto-AG | BW 2017 | LiDAR | NSPI | 4378 | 1378 | 13780 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 2 | 0 | 2 |  | 0 |  | 0
|  | COWI AS | KCDK | Vector | NSPI | 3220 | 1220 | 85400 | DKK | NA | NO | NA | YES | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 5 | 0 | 0 |  | 0 |  | 0 | All the planned municiaplaities are delivered
|  | First Base Solutions | 1737DURH | Vector | MVRA | 589 | 589 | 8250 | CAD | NA | NA | YES | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0
|  | VANSTEELANDT | GRB | Vector | MVRA | 346 | 346 | 2340 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 6 | 0 | 0 |  | 0 |  | 0
|  | PMC | SW-PA-orthophoto warping | Ortho | SKCY | 120 | 70 | 1200 | USD | NO | NA | Yes | YES | YES | YES | YES | YES | To be invoiced | Delivered | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 40 | Additional hours obtained from client on PAMAPS work
|  | Geoconsult | Mauritania | AT/DTM/DSM/Ortho | MNJA | 2000 | 338.8 | 20000 | USD | YES | YES | YES | YES | YES | YES |  | YES |  | In progress | [8 empty] | 4 | 0 | 0 |  | 0 |  | 0
|  | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MNJA | 135 | 66.63 | 950 | USD | YES | YES | YES | YES | YES | YES |  | NA |  | In progress | [8 empty] | 3 | 0 | 0 |  | 0 |  | 40
|  | BSF-SPNO | Tvedestrand and Lillesand | Vector/Ortho | MNJA | 1031 | 24.5 | 126765 | NOK | NA | NA | NA | NO | NO | NO | NO | NO |  | To be started | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0 | Project Plan is in Progress
|  | Digital Globe | Nigeria Oil Theft Analysis | Vector | MNJA | 325 | 170 | 3250 | USD | YES |  | YES | NO | YES | NA | NA | NA |  | In progress | [8 empty] | 6 | 0 | 2 |  | 0 |  | 0
|  | COWI Norway | Historical Orthophoto | AT/Ortho | MNJA | 3993.0003 | 610 | 351380 | NOK | YES | YES | YES | YES | YES | NA | YES | YES |  | In progress | [8 empty] | 6 | 0 | 0 |  | 0 |  | 70
|  | COWI AS | HxIP | Ortho | KSAB | 14199 | 286.8 | 21796.8 | DKK | NO | NO | NO | YES | YES | NO | YES | YES | Monthly Invoice | In progress | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Sweeden | Gothenburg | AT/Ortho/LiDAR | KSAB | 822 | 367 | 27892 | DKK | NO | NO | YES | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 2 | 0 | 0 | 1 | 1 | 0 | 33
|  | COWI Sweeden | ParLerÖck | AT/Ortho | KSAB | 353 | 80 | 6080 | DKK | NO | NO | YES | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Sweeden | Stockholm | AT/Ortho/LiDAR | KSAB | 4927 | 3181 | 241756 | DKK | NO | NO | NO | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Sweeden | Leksand | AT/Ortho/Vector | KSAB | 210 | 194 | 14744 | DKK | NO | YES | NO | YES | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 2 | 0 | 0 | 1 | 0 | 0 | 50
|  | COWI Sweeden | Kungsbacka | AT/Ortho | KSAB | 429 | 190 | 14440 | DKK | NO | YES | NO | YES | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Sweeden | Skane | AT/Ortho/LiDAR | KSAB | 2242 | 641 | 48716 | DKK | NO | NO | NO | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Nord-Trondelag2016-SOR-Snasa_Steinkjer | Vector | KMRE |  |  |  | NOK | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Østfold 2017 | AT/Vector/Ortho | KMRE | 1100 | 25 | 12496 | NOK | NA | YES | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | KMRE | 2672 | 117 | 235136 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | KMRE | 9433 | 1278 | 714296 | NOK | NA | YES | NA | YES | NO | YES | YES | NO |  | In progress | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | KMRE | 9367 | 2786 | 824296 | NOK | NA | YES | NA | YES | NO | YES | YES | YES |  | In progress | [8 empty] | 3 | 0 | 0 | 1 | 0 | 0 | 0
|  | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | KMRE | 9353 |  | 669715.2 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | Hold | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | KMRE | 3510 |  | 191488 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Oppland FKB-C 2017 | Vector | KMRE | 5921 | 432 | 484220 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Midthordland 2017 | AT/Ortho | KMRE | 614 |  | 54032 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | To be started | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | COWI Norway | Oslo Update - 2017 | Vector | KMRE | 792 |  | 69696 | NOK | NA | YES | NA | NO | NO | NO | YES | NO |  | To be started | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PMC | NHFS | Ortho | SKCY | 145 | 10 | 100 | USD | NO | NA | YES | NA | NA | NA | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10 | Additional work on NHFS
|  | XEOS | PR2624 | LiDAR | MVRA | 5 | 5 | 65 | CAD | NO | NA | NA | NA | NA | YES | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0
|  | XEOS | PR2634 | LiDAR | MVRA | 10 | 10 | 140 | CAD | NO | NA | NA | NA | NA | NA | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0
|  | Block Box Consulting | Thompson and Cedar II | LiDAR | MVRA | 75 | 75 | 750 | USD | NO | NA | NO | NA | NO | NO | YES | YES | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0
|  | XEOS | PR2341 | LiDAR | MVRA | 310 | 310 | 4340 | CAD | NO | NA | YES | NO | NO | NO | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0
|  | ASI | Westwood | AT/Ortho | SUHH | 690 | 115 | 1150 | USD | NO | NA | YES | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 1 delivered.
|  | Groupe DEGAUD | PAYS de MONTBELIARD | Strip adjustment/LiDAR | SUHH | 834 | 50 | 500 | USD | Yes | NA | NA | YES | YES | NO | YES | YES |  | Approved | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Strip adjustment approved
|  | BSF-Swissphoto | M7016 DOP Luzern 2017 | Ortho | MVRA | 3769 | 628 | 37688 | EURO | NO | NA | NA | YES | NO | NO | NO | NO | To be invoiced | To be started | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0
|  | VANSTEELANDT | ErpeMere | LiDAR | MVRA | 35 | 35 | 350 | EURO | YES | NA | NA | NA | NA | NO | NO | NA | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0
|  | Fmaps | Koromiko | AT/DTM | DPKR | 29 | 9 | 400 | NZD | NA | NA | NO | YES | YES | NA | NA | NO |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0 | AT delivered
|  | COWI AS | Hillerød municipality | Ortho | PSRA | 43 | 43 | 2975 | DKK | YES | NO | NA | YES | YES | NO | YES | NO | To be invoiced | Approved | [8 empty] | 1 | 0 | 0 |  | 0 |  | 0 | hours uploaded to cockpit
2018-07-01 |  | Client Name | Project Name | Servicelines | PM | Project Billable hours | Month Billable hours | Price | Currency | Signed QS available | Signed ATR available | Signed WO/PO available | Project Plan with Customer | Project Plan in CIPM | KoM / CIPM | WF/GL available | Risk log updated | Invoice | Project Status | [8 empty] | Deliveries | Delayed deliveries | Client Feedbacks |  | Fail | Increase turnover (in hours) | Remarks
2018-07-01 |  | BSF-Swissphoto | 7014 DOP NL 2017 - Block-06 | AT/Ortho | PSRA | 683 | 0 | 3020 | EURO | YES | NA | NA | YES | YES | NO | NO | YES | To be invoiced | Client corrections | [8 empty] | 1 | 0 | 2 |  | 0 | 20
2018-07-01 |  | BSF-Swissphoto | 7014 DOP NL 2017 - Block-10 | AT/Ortho | PSRA | 671 | 460 | 6714 | EURO | YES | NA | NA | YES | YES | NO | NO | YES | To be invoiced | Client corrections | [8 empty] | 1 | 0 | 1 |  | 0 |  | awaiting feedback on ortho
2018-07-01 |  | COWI AS | Hillerød municipality | Ortho | PSRA | 43 | 43 | 2975 | DKK | YES | NO | NA | YES | YES | NO | YES | NO |  | Hold | [14 empty] | released for GC
2018-07-01 |  | COWI AS | HxIP | Ortho | KSAB | 14199 | 574.6 | 43669.6 | DKK | NO | NO | NO | YES | YES | NO | YES | YES | Monthly Invoice | In progress | [8 empty] | 4 | 0 | 0 |  | 0 | 0
2018-07-01 |  | IBV-KRANK | PRJ-1351-Project-2-Part-06 | LiDAR | MVRA | 753 | 192 | 1920 | EURO | NO | NA | NO | YES | YES | NO | YES | YES | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-07-01 |  | VANSTEELANDT | GRB | Vector | MVRA | 274 | 504 | 5040 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 6 | 0 | 0 |  | 1 | 0
2018-07-01 |  | COWI AS | Uganda WB | AT/DTM/Ortho | MVRA | 0 | 2609 | 187848 | DKK | NA | YES | NA | YES | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-07-01 |  | BSF-Swissphoto-AG | BW 2017 | Lidar | NSPI | 4378 | 1500 | 43784 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 2 | 0 | 2 |  | 0 | 0 | Project moved to August month
2018-07-01 |  | CAS | Various | AT/Vector/Ortho | NSPI | 3401 | 3401 | 34010 | USD | NA | NA | NA | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 20 | 1 | 0 |  | 0 | 0
2018-07-01 |  | SDFE | Geosjaelland | Vector | NSPI | 12498 | 2400 | 899844 | DKK | NA | NO | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 2 | 0 | 2 |  | 0 | 0 | Project moved to August month
2018-07-01 |  | COWI AS | KCDK | Vector | NSPI | 3220 | 1000 | 225400 | DKK | NA | NO | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 1 | 0 | 0 |  | 0 | 0 | Project moved to August month
2018-07-01 |  | COWI Sweeden | Gothenburg | AT/Ortho/LiDAR | KSAB | 789 | 315 | 23940 | DKK | NO | NO | YES | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 1 | 0 | 1 |  | 0 | 0
2018-07-01 |  | COWI Sweeden | ParLerÖck | AT/Ortho | KSAB | 353 | 58 | 4408 | DKK | NO | NO | YES | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0
2018-07-01 |  | COWI Sweeden | Stockholm | AT/Ortho/LiDAR | KSAB | 3575 | 106 | 8056 | DKK | NO | NO | NO | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 5 | 0 | 0 |  | 3 | 0
2018-07-01 |  | Topocart | SCS | Vector | SKCY | 2009 | 700 | 20088.78 | USD | YES | NA | YES | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 1 |  | 0 | 0
2018-07-01 |  | Topocart | CE | Vector | SKCY | 2337 | 1800 | 23371.31 | USD | NO | NA | YES | Yes | Yes | Yes | YES | YES |  | In progress | [8 empty] | 2 | 0 | 1 |  | 1 | 0 | LimerodoNorte failure due to poor production quality from outsourced work
2018-07-01 |  | ASI | Westwood | AT/Ortho | SUHH | 690 | 345 | 3450 | USD | NO | NA | YES | YES | YES | YES | YES | YES |  | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0 | Phase 1 delivered. Phase 2 inputs awaited
2018-07-01 |  | BSF-Swissphoto | Telleborg | AT/Ortho | AISR | 1300 | 377 | 13000 | EURO | Yes | NA | YES | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 1 |  | 0 | 0
2018-07-01 |  | Geoconsult | Mauritania | AT/DTM/DSM/Ortho | MNJA | 2000 | 1084.75 | 20000 | USD | YES | YES | YES | YES | YES | YES |  | YES |  | In progress | [8 empty] | 2 | 0 | 0 |  | 0 | 807 | Excellent Productivity in the Month of July
2018-07-01 |  | Geoconsult | Guinea DAM | AT/DTM/DSM/Ortho | MNJA | 95 | 15 | 950 | USD | YES | YES | YES | YES | YES | YES |  | NA |  | In progress | [8 empty] | 2 | 0 | 0 |  | 0 |  | Project Plan is in Progress
2018-07-01 |  | BSF-SPNO | Jølster Eid Gloppen-2017 | AT/Vector/Ortho | MNJA | 6534 | [10 empty] | NO |  | To be started | [14 empty] | Project Plan is in Progress
2018-07-01 |  | BSF-SPNO | Hardanger_2017 | AT/Vector/Ortho | MNJA | 6534 | [10 empty] | NO |  | To be started | [14 empty] | Project Plan is in Progress
2018-07-01 |  | BSF-SPNO | Tvedestrand and Lillesand | AT/Vector/Ortho | MNJA | 1031 | [10 empty] | NO |  | To be started | [14 empty] | Project Plan is in Progress
2018-07-01 |  | BSF-SPNO | Setesdal 2017 | AT/Vector/Ortho | MNJA | 1070 | [10 empty] | NO |  | To be started | [14 empty] | Project Plan is in Progress
2018-07-01 |  | BSF-SPNO | Lærdal 2017 | AT/Vector/Ortho | MNJA | 1109 | [10 empty] | NO |  | To be started | [14 empty] | Project Plan is in Progress
2018-07-01 |  | Digital Globe | Nigeria Oil Theft Analysis | Vector | MNJA | 325 | 18 | 3250 | USD | YES |  | YES | NO | YES |  |  | NA |  | In progress
2018-07-01 |  | COWI Norway | Historical Orthophoto | AT/Ortho | MNJA | 3993.0003 | 71 | 351380 | NOK | YES | YES | YES | YES | YES | NA | YES | YES |  | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | Project Plan is in Progress
2018-07-01 |  | COWI Norway | Østfold 2017 | AT/Vector/Ortho | KMRE | 1100 | 147 | 12496 | NOK | NA | YES | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 1
2018-07-01 |  | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | KMRE | 2672 | 0 | 235136 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | To be started
2018-07-01 |  | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | KMRE | 9433 | 10 | 714296 | NOK | NA | YES | NA | YES | NO | YES | YES | NO |  | In progress
2018-07-01 |  | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | KMRE | 9367 | 2848 | 824296 | NOK | NA | YES | NA | YES | NO | YES | YES | YES |  | In progress
2018-07-01 |  | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | KMRE | 9353 | 90 | 669715.2 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress
2018-07-01 |  | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | KMRE | 3510 | 0 | 191488 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress
2018-07-01 |  | COWI Norway | Oppland FKB-C 2017 | Vector | KMRE | 5921 | 448 | 484220 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | In progress | [8 empty] | 1 |  | 1
2018-07-01 |  | COWI Norway | Midthordland 2017 | AT/Ortho | KMRE | 614 | 0 | 54032 | NOK | NA | YES | NA | NO | NO | YES | YES | NO |  | To be started
2018-07-01 |  | COWI Norway | Oslo Update - 2017 | Vector | KMRE | 792 | 0 | 69696 | NOK | NA | YES | NA | NO | NO | NO | YES | NO |  | To be started
2018-07-01 |  | Block Box Consulting | Mobile LiDAR Classification | LiDAR | MVRA | 35 | 35 | 350 | USD | YES | NA | NA | NA | NA | NO | NO | NO | To be invoiced | Delivered | [8 empty] | 1 | 1 | 0 |  | 0 | 0 | Delay due to ambiguity in the scope and customer has changed the requirement
2018-07-01 |  | TRIG Spatial Information Ltd | JOB 105417 | DTM/Vector | MVRA | 75 | 75 | 750 | USD | YES | NA | NA | NA | NA | NA | NO | NO | To be invoiced | Delivered | [8 empty] | 1 | 1 | 0 |  | 1 | 0 | No proper planning nor accountability; quality issues; resubmitted and got rejected
2018-07-01 |  | PMC | SW-PA-orthophoto warping | Ortho | SKCY | 80 | 20 | 800 | USD | NO | NA | Yes | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0
2018-07-01 |  | IBV-KRANK | GZ5042-Project 2017-1 | LiDAR | MVRA | 6251 | 200 | 62510 | EURO | NO | NA | NA | NO | NO | NO | NO | NO | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | 338 hours to spill over to Aug'17
2018-07-01 |  | COWI AS | OSGB-DPN | Vector | AISR | 2966 | 1600 |  |  | Yes | NA | YES | NA | YES | YES | YES | YES |  | In progress | [8 empty] | 2 | 0 | 1 |  | 0 | 0
2018-07-01 |  | GC-Italia | Powerline mapping | LiDAR | NSPI | 550 | 550 | 5500 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 4 | 0 | 1 |  | 0 | 0
2018-07-01 |  | VANSTEELANDT | ErpeMere | LiDAR | MVRA | 10 | 10 | 100 | EURO | YES | NA | NA | NA | NA | NA | NA | NA | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-07-01 |  | ATS | CA St Landfill | Vector | NSPI | 120 | 120 | 1200 | USD | NA | NA | YES | NA | NA | NA | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-07-01 |  | F Maps | Olsen | AT/Vector | DPKR | 28 | 28 | [5 empty] | YES | YES | NA | YES | NA | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-07-01 |  | COWI Sweeden | Leksand | AT/Ortho/Vector | KSAB | 162 | 16 | 1216 | DKK | NO | YES | NO | YES | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | Client Name | Project Name | Servicelines | PM | Project Billable Hours | Month Billable Hours | Price | Currency | Signed QS available | Signed ATR available | Signed WO/PO available | Project Plan with Customer | Project Plan in CIPM | KoM / CIPM | WF/GL available | Risk log updated | Invoice | Project Status | [8 empty] | Deliveries | Delayed deliveries | Client Feedbacks |  | Fail | Increase turnover (in hours) | Remarks
2018-06-01 |  | COWI AS | Hillerød municipality | Ortho | PSRA | 42 | 42 | 2975 | DKK | NO | NO | NA | NO | NO | NO | NO | NO | [10 empty] | 0 | 0 | 0 |  | 0 | 0
2018-06-01 |  | BSF-Swissphoto-AG | BW 2017 | Lidar | NSPI | 4378 | 1500 | 43784 | EURO | NO | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | BSF-Swissphoto-AG | Sachsen | Lidar | NSPI | 1250 | 1108 | 12500 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | To be invoiced | Delivered | [8 empty] | 5 | 0 | 1 |  | 0 | 0 | Invoice details sent to MIS
2018-06-01 |  | CAS | Various | AT/Vector/Ortho | NSPI | 2331 | 2331 | 27972 | USD | NA | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 30 | 4 | 5 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | SDFE | Geosjaelland | Vector | NSPI | 12498 | 1400 | 899844 | DKK | NA | NO | NO | YES | NO | NO | NO | NO | Monthly Invoice | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | Geocart | Powerline mapping | Vector | NSPI | 1849 | 1849 | 18490 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 5 | 0 | 0 |  | 0 | 0 | Invoice details sent to MIS
2018-06-01 |  | Geocart | Highway | Lidar | NSPI | 3465 | 1386 | 34650 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Invoiced | Delivered | [8 empty] | 4 | 0 | 0 |  | 0 | 0 | Invoice details sent to MIS
2018-06-01 |  | COWI AS | HxIP | Ortho | DPKR | 14199 | 518 | 36689.94 | DKK | NO | NO | NO | YES | YES | NO | YES | YES | Monthly Invoice | In progress | [8 empty] | 5 | 0 | 0 |  | 0 | 0
2018-06-01 |  | FMAPS | Kiteroa | AT/DTM | DPKR | 282 | 282 |  | NZD | NO | NO | NO | YES | NO | NO | NO | NA | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | Aerial Services Inc | Phase 2 | Vector | DPKR | 75 | 75 | 750 | USD | YES | NO | YES | NO | No | NO | NO | NO | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0 | contingency 32
2018-06-01 |  | VANSTEELANDT | GRB | Vector | MVRA | 708 | 478 | 4689 | EURO | YES | NA | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 2 | 0 | 0 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | VANSTEELANDT | HIT Lobbes | Lidar | MVRA | 60 | 36 | 600 | EURO | YES | NA | NA | NO | NA | NO | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 0 | 1 |  | 0 | 0
2018-06-01 |  | IBV-KRANK | PRJ-1351-Project-2-Part-06 | Lidar | MVRA | 753 | 515 | 7530 | EURO | NO | NO | NA | NO | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | XEOS | PR2559 | Lidar | MVRA | 493 | 289 | 5000 | CAD | NO | NA | YES | NO | NO | NO | NO | NA | To be invoiced | Delivered | [8 empty] | 1 | 1 | 0 |  | 0 | 0
2018-06-01 |  | XEOS | PR2561 | Lidar | MVRA | 52 | 13 | 620 | EURO | NO | NA | NO | NO | NA | NO | NA | NA | Invoiced | Delivered | [8 empty] | 1 | 1 | 1 |  | 0 | 0
2018-06-01 |  | XEOS | PR2610 | Lidar | MVRA | 50 | 21 | 70 | EURO | NO | NA | NO | NO | NA | NO | NA | NO | Invoiced | Delivered | [8 empty] | 1 | 1 | 1 |  | 0 | 0
2018-06-01 |  | COWI AS | Uganda WB | AT/Vector/Ortho | MVRA | 11042 | 1025 | 71750 | DKK | NA | YES | NA | YES | YES | YES | YES | YES | Monthly Invoice | In progress | [8 empty] | 1 | 0 | 0 |  | 0 | 0 | Moved to July sheet with balance billable hours
2018-06-01 |  | COWI AS | Uruguay Forestry | AT/Lidar/Ortho | MVRA | 2573 | 118 | 180110 | DKK | NA | YES | NA | YES | YES | YES | YES | YES | Monthly Invoice | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | GEODEZIA | Highway Mapping | Vector | MVRA | 1470 | 63 | 14703 | EURO | YES | NA | NO | YES | YES | YES | YES | YES | To be invoiced | Delivered | [8 empty] | 2 | 0 | 1 |  | 0 | 0
2018-06-01 |  | BSF-Swissphoto | 7014 DOP NL 2017 - Block-06 | AT/Ortho | PSRA | 683 | 302 | 3020 | EURO | YES | NA | NA | YES | YES | NO | NO | YES | To be invoiced | Client corrections | [8 empty] | 1 | 0 | 2 |  | 0 | 20
2018-06-01 |  | JR Canadian Mapping Ltd. | JRC-Corridor-Corridor-17005 | Vector | MNJA | 676 | 296 | 8115 | CAD | Yes | NA | Yes | Yes | Yes | NA |  | YES | Invoiced | Approved | [8 empty] | 4 | 0 | 2 |  | 0
2018-06-01 |  | AAC | Georgia DTM | DTM | MNJA | 1105 | 1105 | 11050 | USD | Yes | NA | Yes | Yes | Yes | NA |  | YES | Invoiced | Approved | [8 empty] | 4 | 0 | 1 |  | 0
2018-06-01 |  | Digital Globe | Nigeria Oil | 2D Vector | MNJA | 120 | 8.6 | 1200 | USD | Yes | NA | Yes | Yes | Yes | NA |  | NA | Invoiced | Approved | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | BSF-Swissphoto | Telleborg | AT/Ortho | AISR | 1300 | 623 | 13000 | EURO | Yes | NA | YES | YES | YES | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 1 |  | 1 | 0 | Pilot delivery not upto mark
2018-06-01 |  | PMC | NH-Forest Society | Ortho | SKCY | 145 | 135 | 1348.75 | USD | NA | NA | YES | YES | Yes | YES | YES | YES | To be invoiced | Delivered | [8 empty] | 3 | 0 | 0 |  | 1 | 0 | Tiff format delivered instad of MrSID on 1st delivery
2018-06-01 |  | Geoconsult | Mauritania | AT/Vector/Ortho | MNJA | 2000 | 143 | 20000 | USD | YES | YES | YES | YES | YES | YES |  | YES |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0
2018-06-01 |  | FIRST BASE SOLUTIONS | FBS | 1737BRNT | PSRA | 570 |  | 6850 | CAD | YES |  | YES | YES | YES | YES | YES |  | Invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | COWI Sweeden | Gothenburg | AT/Ortho/LiDAR | KSAB | 789 | 140 | 9800 | DKK | NO | NO | YES | YES | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0
2018-06-01 |  | TOPOCART | SCS | Vector | SKCY | 2009 | 620 | 20088.78 | USD | YES | NA | YES | YES | Yes | YES | YES | Yes |  | In progress | [8 empty] | 0 | 0 | 0 |  | 0 | 0 | Deliveries will start from July-17
2018-06-01 |  | BSF-Swissphoto | 7014 DOP NL 2017 - Block-10 | AT/Ortho | PSRA | 671 | 211 | 6714 | EURO | YES | NA | NA | YES | YES | NO | NO | YES | To be invoiced | In progress | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | COWI AS | OSGB-DI (Pilot) | Vector | AISR |  |  |  |  | Yes | NA | YES | YES | YES | NA | YES | YES |  | In progress | [8 empty] | 2 | 0 | 2 |  | 0 | 0
2018-06-01 |  | COWI AS | OSGB-DPN (Pilot) | Vector | AISR |  |  |  |  | Yes | NA | YES | YES | YES | NA | YES | YES |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0 | 0
2018-06-01 |  | COWI Norway | Østfold 2017 | AT/Vector/Ortho | KMRE | 1100 | 142 | 12496 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | KMRE | 2672 | 2672 | 235136 | NOK | NA | NO | NA | NO | NO | YES | YES | NA |  | To be started | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Buskerud_sør 2017 | AT/Vector/Ortho | KMRE | 9433 | 8117 | 714296 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Haugalandet 2017 | AT/Vector/Ortho | KMRE | 9367 | 9367 | 824296 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | KMRE | 9353 | 7610.4 | 669715.2 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 1 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | KMRE | 3510 | 2176 | 191488 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Oppland FKB-C 2017 | Vector | KMRE | 5921 | 5502.5 | 484220 | NOK | NA | NO | NA | NO | NO | YES | YES | YES |  | In progress | [8 empty] | 5 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Midthordland 2017 | AT/Ortho | KMRE | 614 | 614 | 54032 | NOK | NA | NO | NA | NO | NO | YES | YES | NA |  | To be started | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Oslo Update - 2017 | Vector | KMRE | 792 | 792 | 69696 | NOK | NA | NO | NA | NO | NO | NO | YES | NA |  | To be started | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI Norway | Historical Orthophoto | AT/Ortho | KMRE | 3993.0003 | 3993.0003 | 351380 | NOK | NA | NO | NA | NO | NO | NO | YES | NA |  | To be started | [8 empty] | 0 | 0 | 0 |  | 0
2018-06-01 |  | COWI AS | DK Satellitfoto Telezoner 2017 | AT/Ortho | PSRA | 275 | 200 | 18900 | DKK | NA | NO | NO | YES | YES | YES | YES | YES | To be invoiced | In progress | [8 empty] | 10 | 7 | 2 |  | 1 | 100
2018-06-01 |  | XEOS | PR2625 | Lidar | MVRA | 6 | 6 | 60 | CAD | NO | NA | NA | NA | NA | NA | NA | NA | To be invoiced | Delivered | [8 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Client Name | False Name | Project Name | Serviceline | PM | Month of Execution | Billable hours | Price | currency | QS / Signed | ATR / Signed | WO / Signed | QP with Customer | QP in CIPM | KoM / CIPM | Remarks | Invoice | [9 empty] | Deliveries | Delayed deliveries | Client Feedbacks |  | Fail | Increase turnover (in hours) | Remarks
May-before |  | Atlis Geo | Hudson | Wetland | Vector | DPKR | March | 5879 | ?? | USD | Yes/No | NA | Yes/Yes | Yes | Yes | No | Project closed | to be invoiced | [9 empty] | 22 | 3 | 22 |  | 22 | 0
May-before |  | COWI DK | COWIDK_HIP | HxIP | Ortho | DPKR | May | 4476 |  | DKK | No | No | Yes/Yes | Yes | Yes | Yes | Shared the signed agreement (SCA),DMCIII 4 blocks received | Monthly invoiced
May-before |  | COWI NO | Norway | NDH-2015 | LiDAR | NSPI | 2017-05-01 | NA | NA | NA | NA | Yes | Yes | Yes | Yes | No | Production in progress | Monthly Invoice | [9 empty] | 6 | 0 | 0 |  | 0 | 452
May-before |  | Aerial Services Inc | KIM | 6755 | LiDAR | NSPI |  |  |  |  | Yes/Yes |  | Yes/No | Yes | Yes | No | Project Closed | Invoice raised | [9 empty] | 5 | 0 | 0 |  | 0
May-before |  | Aerial Services Inc | KIM | 6715 | LiDAR | NSPI |  |  |  |  | Yes/No |  | Yes/No | Yes | Yes | No | Project Closed | Invoice raised | [9 empty] | 5 | 0 | 0 |  | 0
May-before |  | COWI DK | UAV_Drone | Nakabolwe | Ortho |  |  | 10 | NO: Yes/No; NO: Yes; NO: No; NA: Project Closed
May-before |  | COWI DK | COWIDK-2D | Uruguay Forestry | LiDAR, Ortho | MVRA |  | 1565 | 106420 | DKK | NA | Yes/No | NA | Yes | Yes | Yes/Yes | In Progress | Monthly invoice
May-before |  | COWI DK | COWIDK-2D | Motala | LiDAR | MVRA |  | 600 | 40800 | DKK | Yes/No | Yes/Yes | NA |  | Yes | No | Project Closed | Invoice raised
May-before |  | Cooper Aerial Surveys Co | CAS | CAS | Vector, Ortho | NSPI | 2017-05-01 | 444 | NA | USD | NA | NA | NA | Yes | Yes | Yes | Production in progress | Monthly Invoice | [9 empty] | 131 | 8 | 4 |  | 3
May-before |  | VANSTEELANDT | AWV | GRB | Vector | MVRA |  | Continous | 13.1 | Euro | Yes/Yes | NA | NA | Yes | Yes | Yes | Signed QS received from the customer | Invoice details provided to KLGA for approved 5 municipalities | [9 empty] | 10 | 0 | 0 |  | 0 | 0 | Approval awaited
May-before |  | VANSTEELANDT | AWV | Walibi - Mapping (Part-1 & 2) | LiDAR | MVRA |  | 50 | 500 | Euro | Yes/No | NA | NA | Yes | NA | NA | Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | VANSTEELANDT | AWV | Walibi - Classification | LiDAR | MVRA |  | 20 | 200 | Euro | No/No | NA | NA | Yes | NA | NA | Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | VANSTEELANDT | AWV | Lierek - Classification | LiDAR | MVRA |  | 50 | 500 | Euro | No/No | NA | NA | Yes | NA | NA | Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | XEOS | XEOS | Xeos | LiDAR | MVRA |  | 970 | 11638 | CAD | Yes/No | NA | Yes/Yes | Yes | Yes | No | Project Closed | Invoice raised | [9 empty] | 2 | 0 | 2 |  | 0 | 0
May-before |  | IBV-KRANK | Ronaldo | Ronaldo-Project2-Part4 | LiDAR | MVRA |  | 329 | 3285 | Euro | Yes/No | NA |  | Yes | Yes | No | Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | COWI Swiss Topo | COWI_Swiss_Topo | Swiss Topo | Vector | OSK |  |  | NA: Need to check with OSK: Project Closed | ???
May-before |  | COWI DK | Uganda_WB | UGANDA WB | AT, DTM, Ortho | MVRA |  | 17213.9559 | 1170549 | DKK | Yes/No | Yes/Yes | NA | NA | Yes | Yes | In Progress | Monthly invoice
May-before |  | COWI | COWI | Herning Holstebro | AT-Ortho | MVRA |  | 64.7059 | NZD: 4400; NO: DKK; NO: Yes/Yes; NA: Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | GEODEZIA | Geo D | Road Mapping | Vector | MVRA |  | 1050 | 10250 | Euro | Yes/No |  |  |  | Yes | Yes | In Progress | [10 empty] | 17 | 0 | 2 |  | 0 | 3.5 Hours / KM
May-before |  | COWI A/S | COWI A/S | ThermomosaicUtrecht | Ortho | [5 empty] | NA | Yes | NA | NA | NA | NA | Awaiting countersignatures, sent request to SVSC | [10 empty] | 1 | 0 | 0 |  | 0
May-before |  | COWI A/S | COWI A/S | OSGB-Urban | Vector | VTSA |  |  |  |  | NA | Yes | NA | Yes | Yes | Yes | In Progress
May-before |  | COWI A/S | COWI A/S | OSGB-Rural | Vector | DVCH |  |  |  |  | NA | Yes | NA | Yes | Yes | Yes | In Progress
May-before |  | SDFE | SDFE | FOT Nordjylland-2016 | Vector | NSPI |  |  |  |  | NA | Yes | NA | Yes | Yes | Yes | Project Closed | Invoice raised | [9 empty] | 11 | 4 | 11 |  | 4
May-before |  | SDFE | SDFE | FOT-Designated Update-2016 | Vector | NSPI | 2017-03-01 |  |  |  | NA | Yes | NA | Yes | Yes | Yes | Project Closed | 93% invoice raised | [9 empty] | 86 | 26 | 86 |  | 3
May-before |  | COWI NO | COWI NO | Norway | Vector | KMRE |  |  |  |  | NA | Yes | NA | Yes | Yes | Yes
May-before |  | Swiss photo | Swiss photo | Swissphoto - SPNO | Vector/Ortho | KMRE |  |  |  |  | Yes/Yes | NA | NA | Yes | Yes | Yes | [11 empty] | 1 | 0 | 0 |  | 0
May-before |  | COWI A/S | COWI A/S | Dar Es salam | DTM, Ortho | PSRA |  | 3534 |  |  | NA | No | NA | Yes | Yes | Yes | PSRA/MADV share the comments to Bente | acceptance for AT invoice | [9 empty] | 5 | 0 | 0 |  | 0
May-before |  | JR Canadian Mapping Ltd. | JRC | Corridor mapping | Vector | NSPI |  |  |  |  | No | NA | NA | Yes | Yes | No | Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 1
May-before |  | Geo FIT | Geo FIT | Anceneis Carenes | AT/DEM/Ortho | MADV | 2017-04-01 | 4800 | 480000 | Euro | Yes/Yes | NA | NA | Yes | Yes | Yes | Project completed and delivered | 20%+AT+50% DEM and Ortho raised on prorate basis | [9 empty] | 2 | 0 | 2 |  | 0 | 0
May-before |  | COWI A/S | Goteborg | SE_Göteborg_Flygfoto_2017 -Ortho | AT/Ortho | PSRA |  |  |  |  | NA | Yes/Yes | NA | NO | NO | NO | Send to SRJ for signatures: Yet to start
May-before |  | COWI A/S | Zurich | Zurich | Ortho | PSRA |  | 200 | NO: NA; NO: Yes/No; YES: NA; NO: Yes; NO: Yes | [10 empty] | 1 | 0 | 0 |  | 0
May-before |  | COWI A/S | DDO radiometry | DDO radiometry | Ortho | PSRA |  | 25 | NO: NA; NO: No; YES: NA; NO: Yes; NO: Yes | Raised invoice by NSPI | [9 empty] | 1 | 0 | 0 |  | 0
May-before |  | JR Canadian Mapping Ltd. | JRC | Harrington | DTM/Ortho | NSPI |  |  | NO: Yes/No; NO: NA; NO: NA; NA: Project Closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0
May-before |  | COWI | COWI | SDG 2017 | ImageBlur | MADV |  |  | NO: NA; NO: A078052-036; NO: NA; NO: NA; NO: NA
May-before |  | AAM | AAM | 26920C02_illawarraCoal_AT | AT | MADV |  |  | NA: Framework agreement shared. Awaiting Hans return | [10 empty] | 1 | 0 | 0 |  | 0
May-before |  | AAM | AAM | 27131_17_Bluescope_Feb2017_AT | AT | MADV | [21 empty] | 1 | 0 | 0 |  | 0
May-before |  | COWI | COWI | SDG 2016 | Vector | MADV
May-before |  | Geocart | GC-Italia | Power line mapping | Lidar | NSPI | 2017-05-01 | 1600 | NA | Euro | Yes | NA | NA | Yes | Yes | Yes | Production in progress | Monthly Invoice | [9 empty] | 8 | 3 | 3 |  | 0
May-before |  | Geocart | GC-Italia | Highway | Vector | NSPI | 2017-05-01 | 3465 | NA | Euro | Yes | NA | NA | Yes | Yes | Yes | Production in progress | Monthly Invoice | [9 empty] | 4 | 2 | 2 |  | 1
May-before |  | COWI A/S | COWI A/S | DK Satellitfoto Telezoner 2017 | Ortho | PSRA |  | 275 |  |  | NA | yes | NA | Yes | Yes | yes | ATR in review | [10 empty] | 5 | 0 | 2 |  | 0
May-before |  | Aerial Services Inc | KIM | 3171260091XXXO_Bryan_County | Ortho | SUHH |  | 300 |  |  | Yes | NA | NA | Yes | Yes |  | Project Closed | To be invoiced | [9 empty] | 2 | 0 | 1 |  | 0 | 0
May-before |  | Aerial Services Inc | KIM | 6715_Windfarms | DTM/Ortho/Vector | SUHH |  | 2025 |  |  | No | NA | NA | Yes | Yes |  | Project Closed | To be invoiced | [9 empty] | 4 | 0 | 0 |  | 0 | 0
May-before |  | COWI AS | Dubai | Dubai | Vector | MADV |  |  | NO: Yes/No; NA: Workflow under construction
May-before |  | BSF | BSF | BSF-NL-Block6 | AT\Ortho | PSRA/NSPI |  | 663 | 6634 | Euro | yes/no | NA | NA | Yes | Yes | Yes | documents prepared-
May-before |  | BSF | BSF | NRW-Lidar | Lidar | NSPI/SUHH |  |  | NA: Expected in end of April and will be executed in BLR
May-before |  | COWI | Norway | Voss Fusa Samnager 2016 | AT/Vector/Ortho | MADV/KMRE |  | 3606 |  |  | NA | Yes | Yes | Yes | Yes | Yes | Only contours are pending. Rest all delivered from all service lines. | 90% invoice raised | [11 empty] | 1
May-before |  | COWI | Norway | Nord Trøndelag Sør 2016 - FKB-C | Vector | MADV/KMRE |  | 1426 |  |  | NA | Yes | Yes | Yes | Yes | Yes | [11 empty] | 2 | 0 | 0 |  | 0 | 91 | Estimation missed from AOI. (Mistake from customer)
May-before |  | COWI | Norway | Østfold 2017 | AT/Vector/Ortho | MADV/KMRE |  | 1165 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | COWI | Norway | Porsgrunn Larvik 2017 | AT/Vector/Ortho | MADV/KMRE |  | 2647 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | COWI | Norway | Buskerud_sør 2017 | AT/Vector/Ortho | MADV/KMRE |  | 9626 |  |  | Yes/No | NO | NO | NO | NO | NO | FKB-C area - Production in progress. | [10 empty] | 2 |  |  |  |  | 400 | Tractor road edge are newly captured.
May-before |  | COWI | Norway | Haugalandet 2017 | AT/Vector/Ortho | MADV/KMRE |  | 9466 |  |  | Yes/No | NO | NO | NO | NO | NO | Image processing completed
May-before |  | COWI | Norway | Vinje Seljord Tokke 2017 | AT/Vector/Ortho | MADV/KMRE |  | 9854 |  |  | Yes/No | NO | NO | NO | NO | NO | Flight mission yet to start for FKB-B Production in progress for FKB-C
May-before |  | COWI | Norway | Notodden Hjartdal 2017 | AT/Vector/Ortho | MADV/KMRE |  | 3641 |  |  | Yes/No | NO | NO | NO | NO | NO | Flight mission yet to start for FKB-B Production in progress for FKB-C
May-before |  | COWI | Norway | Oppland FKB-C 2017 | Vector | KMRE |  | 5671 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | COWI | Norway | Midthordland 2017 | AT/Ortho | KMRE |  | 614 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | COWI | Norway | Oslo Update - 2017 | Vector | KMRE |  | 792 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | BSF-Swissphoto | SPNO | Jølster Eid Gloppen-2017 | Vector/Ortho | MADV/KMRE |  | 8499 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | BSF-Swissphoto | SPNO | Hardanger_2017 | Vector/Ortho | MADV/KMRE |  | 7846 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | BSF-Swissphoto | SPNO | Tvedestrand and Lillesand | Vector/Ortho | MADV/KMRE |  | 1393 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | BSF-Swissphoto | SPNO | Setesdal 2017 | Vector/Ortho | MADV/KMRE |  | 1283 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | BSF-Swissphoto | SPNO | Lærdal_FKB-B 2017 | Vector/Ortho | MADV/KMRE |  | 1664 |  |  | Yes/No | NO | NO | NO | NO | NO
May-before |  | COWI DK | COWIDK_HIP-2017 | HxIP | Ortho | DPKR | May | 14199 |  | DKK | No | No | No | Yes | No | No | project inprogress,esimated to 158 hours | Monthly invoiced | [9 empty] | 4 | 0 | 0 |  | 0 | 0 | 310 hrs we spent on may month
May-before |  | Geoconsult | GS-INT | Togo - Satellite Imagery | AT/DTM/DSMOrtho | PSRA |  | 440 | 440 | USD | Yes | NA | NA | Yes | Yes | yes |  | Raised invoice | [9 empty] | 8 | 0 | 1 |  | 0
May-before |  | COWI A/S | COWI A/S | JRC | Ortho | PSRA |  | 60 |  | DKK | NA | NO | NA | Yes | Yes |  | Sent request to LHEN for ATR | [10 empty] | 11 | 0 | 0 |  | 0
May-before |  | Aero Tech Surveys | ATS | CG golf course | AT/Vector/Ortho | NSPI |  | 180 | 1800 | USD | Yes | NA | Yes | Yes | Yes | No | Project Closed | To be invoiced | [9 empty] | 1 | 0 | 1 |  | 0 | 90
May-before |  | COWI DK | Gradient | Gradient Project | Vector | MVRA | 2017-04-01 | 102 | 7000 | DKK | Yes/Yes | No | NA | NA | NA | NA | Project Closed | To be invoiced | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | Aero Tech Surveys | ATS | Cleghorn | Vector | DPKR | April | 24 | 240 | USD | Yes | NA | No | Yes | Yes | No | Project closed | to be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Aerial Services Inc | KIM | 6715_Windfarms 250' Buffer rework | Ortho | SUHH | April | 30 | 300 | USD | NA | NA | Yes | Yes | Yes | Yes | Project closed | To be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Aerial Services Inc | KIM | Dallas County Roads 2017 | Vector | DPKR | May | 79 | 790 | USD | Yes | NA | Yes | Yes | Yes | Yes | Project Closed | Invoiced | [9 empty] | 3 | 0 | 1 |  | 0 | 0 | revised AOI
May-before |  | Aerial Services Inc | KIM | Frienship Village Mapping | Vector | DPKR | May | 25 | 250 | USD | Yes | No | No | No | No | No | Project Closed
May-before |  | Fmaps | Fmaps | Parata | AT/DTM | DPKR | May | 108 | 1575 | NZD | No | No | No | Yes | Yes | No | Project Closed | to be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Fmaps | Fmaps | Mangaiti | AT/DTM | DPKR | May | 146 | 2075 | NZD | Yes | No | No | Yes | Yes | No | Project Closed | [10 empty] | 0 | 0 | 0 |  | 0 | 0
May-before |  | Gerhard Sehnalek | PMC | Black forest | AT/ORTHO | DPKR | May | 5 | 50 | USD | NA | NA | Yes | Yes | No | No | Project closed | to be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Aerial Services Inc | KIM | Montana 2017- Task Order 002 | Ortho | SUHH\PSRA |  | 193 | 1885 | USD | Yes | NA | NA | Yes | Yes | No | Project closed | To be invoiced | [9 empty] | 1 | 0 | 0 |  | 0
May-before |  | Aerial Services Inc | KIM | Mason City | Ortho/2D vector | SUHH |  | 450 | 6000 | USD | No | NA | No | Yes | Yes | No | Project closed | To be invoiced | [9 empty] | 2
May-before |  | Groupe DEGAUD | CRAIG-LiDAR | 63-CRAIG-LiDAR | Lidar | SUHH |  | 114 | 991 | Euro | Yes | NA | No | Yes | Yes | No | Project Closed | [10 empty] | 9 | 0 | 1 |  | 0 | 0
May-before |  | IBV-KRANK | Ronaldo | Ronaldo-Project2-Part5 | LiDAR | MVRA | 2017-05-01 | 444 | 4442 | Euro | No/No | NA | No | No | No | No | Delivered | Invoice raised | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | Aerial Services Inc | KIM | 6755-Prj23 | Lidar | SUHH |  | 17 | 170 | USD | NA | NA | Yes | Yes | Yes | Yes | Project Closed | To be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 4
May-before |  | Aero Tech Surveys | ATS | BSS Mapping | Vector | DPKR | May | 18 | 180 | USD | Yes | No | Yes | Yes | Yes | No | Project closed | to be invoiced | [9 empty] | 1 | 0 | 0 |  | 0 | 0
May-before |  | JR Canadian Mapping Ltd. | JRC | JRC-Corridor-Corridor-16005 | Vector | MNJA | 2017-05-01 | 68 | 1095 | CAD | Yes | NA | Yes | Yes | Yes | NA | Project closed | Invoice raised | [9 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | JR Canadian Mapping Ltd. | JRC | JRC-Corridor-Corridor-17005 | Vector | MNJA | 2017-05-01 | 676 | 8115 | CAD | Yes | NA | Yes | Yes | Yes | NA
May-before |  | Geo-International | Geo-International | Togo - ???? | Ortho | PSRA | bar: NO to NO
May-before |  | COWI SE | COWI SE | Stockholm 2017 - Lidar | Lidar/Ortho | HSSG/MVRA
May-before |  | COWI SE | COWI SE | Skone | Lidar/Ortho/Vector | HSSG/MVRA
May-before |  | COWI SE | COWI SE | SE_Motala_2017_Mapping-Lidar | Lidar | SVSC/MVRA
May-before |  | COWI SE | COWI SE | SE_ParLerÖck_DOP2017 | Ortho | SVSC/MVRA
May-before |  | COWI SE | COWI SE | Skåne 2017- Ortho-Lidar |  | MVRA/????
May-before |  | COWI DK | COWI DK | DAR-Morogoro-Lidar |  | MNJA
May-before |  | COWI SE | COWI SE | Stockholm 3d model- Vector |  | MADV
May-before |  | COWI DK | COWI DK | Corys-Roy Hill Rio Tinto-Vector |  | NSPI/????
May-before |  | COWI DK | COWI DK | FOT-Sjalland-2017 |  | NSPI/MADV
May-before |  | COWI DK | COWI DK | CM-2017 |  | NSPI/MADV
May-before |  | BSF-Zurich | BSF-Zurich | Sachsen-BSF-Zurich |  | SUHH/NSPI | 2017-05-01 | 1250 | 12500 | Euro | Yes | NA | NA | Yes | Yes | Yes | In Progress | [10 empty] | 2 | [5 empty] | 183hrs excluding vendor
May-before |  | COWI DK | COWI DK | KCDK-2017 |  | ALTH/NSPI |  | 3000
May-before |  | COWI SE | COWI SE | SE- Kungsbacka | Ortho | HSSG/PSRA
May-before |  | COWI SE | COWI SE | SE_Leksand_2017_Mapping |  | HSSG
May-before |  | VANSTEELANDT | AWV | HIT_Lobbes | LiDAR | MVRA | 2017-05-01 | 60 | 600 | Euro | No | NA | NA | No | No | No | Delivered | To be invoiced
May-before |  | VANSTEELANDT | AWV | ELIA_UL219 | LiDAR | MVRA | 2017-05-01 | 76 | 760 | Euro | Yes/Yes | NA | NA | No | No | No | In Progress
May-before |  | First Base Solutions | FBS | 1737BRNT | AT | PSRA |  | 570 | 6850 | CAD | yes/no | NA | yes | NO | NO | NO | [11 empty] | 1
May-before |  | AAC | AAC | Georgia DTM | DTM | MNJA | 2017-05-01 | 1105 | 11050 | USD | Yes | NA | Yes | Yes | Yes | NA | MNJA prepares the QP | [10 empty] | 1 | 0 | 1 |  | 0 | 0
May-before |  | Digital Globe | DG | Nigeria Oil | 2D Vector | MNJA | 2017-05-01 | 120 | 1200 | USD | Yes | NA | Yes | Yes | Yes | NA | QP shared with Michael
May-before |  | XEOS | XEOS | PR2610 | LiDAR | MVRA | 2017-05-01 | 5 | 70 | CAD | No | NA | NA | No | No | No | Delivered | To be invoiced
May-before |  | XEOS | XEOS | PR2561 | LiDAR | MVRA | 2017-05-01 | 48.2759 | 700 | CAD | No | NA | NA | No | No | No | In Progress
May-before |  | IBV-KRANK | Ronaldo | Ronaldo-Project2-Part6 | LiDAR | MVRA | 2017-05-01 | 753 | 7530 | Euro | No | NA | NA | No | No | No | Yet to start
Formulas:
Input/Output Register = [Date of Input Reciept]
Note on K1: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M1: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N1: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O1: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on R1: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on S1: This cell will accept date from today to 150 days before
Note on T1: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on U1: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V1: Sayak Chakraborty: Mail option
Note on Z1: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA1: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB1: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ1: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on M18: Shastry: Input is still being received
Note on Y19: Shastry:Project has been cancelled from customer and we will receive payment delivered AT
Note on Q23: Akhil Sharma: Ongoing finalization of AQL
Note on H39: K.Murali Mohan Reddy: Except Options
Note on H40: K.Murali Mohan Reddy: Except Options
Note on H41: K.Murali Mohan Reddy: Except Options
Note on H42: K.Murali Mohan Reddy: Except Options
Note on H43: K.Murali Mohan Reddy: Except Options
Note on H44: K.Murali Mohan Reddy: Except Options
Note on H45: K.Murali Mohan Reddy: Except Options
Note on H46: K.Murali Mohan Reddy: Except Options
Note on K84: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M84: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N84: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O84: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on R84: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on S84: This cell will accept date from today to 150 days before
Note on T84: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on U84: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V84: Sayak Chakraborty: Mail option
Note on Z84: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA84: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB84: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ84: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on Z92: Will Be done on 4th Apr
Note on O102: Shastry: For received inputs so far till 02-Jan
Note on M111: Shastry: Input is still being received
Note on Q118: Akhil Sharma: Ongoing finalization of AQL
Note on H138: K.Murali Mohan Reddy: Except Options
Note on H139: K.Murali Mohan Reddy: Except Options
Note on H140: K.Murali Mohan Reddy: Except Options
Note on H141: K.Murali Mohan Reddy: Except Options
Note on H142: K.Murali Mohan Reddy: Except Options
Note on H143: K.Murali Mohan Reddy: Except Options
Note on H144: K.Murali Mohan Reddy: Except Options
Note on H145: K.Murali Mohan Reddy: Except Options
Note on K154: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M154: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N154: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O154: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on R154: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on S154: This cell will accept date from today to 150 days before
Note on T154: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on U154: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V154: Sayak Chakraborty: Mail option
Note on Z154: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA154: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB154: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ154: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on O165: Shastry: For received inputs so far till 02-Jan
Note on Q173: Akhil Sharma: Ongoing finalization of AQL
Note on K180: K.Murali Mohan Reddy: May be the figure will be vary with sales sheet due to over booking in previous months.
Note on M189: Shastry: Input is still being received
Note on O189: Shastry: For received inputs so far till 02-Jan
Note on N194: R Kumaran: Initially expected on 13th Feb. But now the client has do the data aqasition again & will come back to us on Input Date
Note on V202: R Kumaran: Added up in an existing QS
Note on K208: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M208: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N208: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O208: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on Q208: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on R208: This cell will accept date from today to 150 days before
Note on S208: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on T208: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V208: Sayak Chakraborty: Mail option
Note on Z208: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA208: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB208: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ208: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on M219: Shastry: Input is still being received
Note on O219: Shastry: For received inputs so far till 02-Jan
Note on M220: Shastry: DSM and DTM input received on 21-Dec-17; Images received on 13-Dec-17
Note on N240: Akhil Sharma: Final Specs : 15/12 3D engine : 12/01
Note on P240: Akhil Sharma: Ongoing finalization of AQL
Note on L242: Akhil Sharma: Billed 42,635 till Dec'17
Note on K274: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M274: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N274: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O274: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on Q274: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on R274: This cell will accept date from today to 150 days before
Note on S274: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on T274: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V274: Sayak Chakraborty: Mail option
Note on Z274: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA274: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB274: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ274: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on N287: Akhil Sharma: Final Specs : 15/12 3D engine : 12/01
Note on M288: R Kumaran: 45% Input Received by 7th Nov 55% Input Received by 24 Nov
Note on X288: R Kumaran: Communicated to Kanwal Gupta for Invoicing on 12 Dec 2017
Note on N289: R Kumaran: Inputs for More 757Hrs in LiDAR is Expected till 12 Dec 2017 No Update on Ortho Inputs
Note on O289: Partial Data
Note on K293: Deepa K.R: 300 hrs booked in nov
Note on AA304: Shastry: For DURH and HALT
Note on S306: Shastry: Information is not available as project was started in 2016
Note on S308: Shastry: Information is not available as project was started in 2016
Note on Q309: Shastry: Information is not available as project was started in 2016
Note on R309: Shastry: Actual date is 27-Jan-2017 and could not enter as column has validation
Note on S309: Shastry: Information is not available as project was started in 2016
Note on T309: Shastry: Actual date is 31-Jan-2017 and could not enter as column has validation
Note on R315: R Kumaran: Not in Written Format, Explained on System
Note on S315: R Kumaran: Communicated the Delivery Plan to the Customer
Note on AA315: R Kumaran: To Be Taken Every Quarter
Note on H320: R Kumaran: ATR Yet to be recieved
Note on Q320: A pilot was done in Nov, based on that 2 more Deliveries were Planned
Note on R320: Being Executed as per the Piot Done
Note on S320: Communicated Delivery Date via Email
Note on T320: Communicated Delivery Date via Email
Note on V320: R Kumaran: ATR Signatured Pending from CIL
Note on K329: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on M329: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N329: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O329: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on Q329: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on R329: This cell will accept date from today to 150 days before
Note on S329: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on T329: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on V329: Sayak Chakraborty: Mail option
Note on Z329: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA329: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB329: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ329: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on N341: Akhil Sharma: Final Specs
Note on M342: Akhil Sharma: Last input on 18/10
Note on Q342: Akhil Sharma: 04/09: LiDAR/AT 14/09: DTM/Contours/Ortho
Note on R342: Akhil Sharma: 2D vector 28/09 Others: 12/09
Note on S342: Akhil Sharma: Version 1 : 06/09 Version 1.1: 14/09 Version 1.2: 15/09
Note on AA342: Akhil Sharma: NA
Note on AB342: Akhil Sharma: NA
Note on AA343: Shastry: For DURH and HALT
Note on AF344: Shastry: This number indicates number of tiles for minor corrections
Note on Q345: Shastry: NA as it has started in early 2016
Note on AG345: Shastry: This was delivered on 23-Sep and feedback received in this month
Note on M348: R Kumaran: 45% Input Received by 7th Nov 55% Input Received by 24 Nov
Note on Q350: Shastry: It is a small job of 25 hours
Note on Q351: Shastry: It is a small job of 70 hours
Note on Q352: Shastry: NA as it has started in early 2016
Note on Q353: Shastry: It is a small job of 20 hours
Note on M367: R Kumaran: Partial Input received. Quantity will be updated downloadig the data
Note on N367: R Kumaran: Inputs for More 757Hrs in LiDAR is Expected till 12 Dec 2017 No Update on Ortho Inputs
Note on O367: Partial Data
Note on H380: Sujay L H: Machine Hours-116
Note on K386: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on L386: Sujay L H: Remaining hours= colJ-colK
Note on M386: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N386: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O386: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on Q386: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on R386: This cell will accept date from today to 150 days before
Note on S386: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on T386: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on Z386: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA386: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB386: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ386: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on AA396: Shastry: For DURH and HALT
Note on X402: Sayak Chakraborty: Invoicing info sent to Finance on 11-Oct-17
Note on M410: Akhil Sharma: Last input on 18/10
Note on Q410: Akhil Sharma: 04/09: LiDAR/AT 14/09: DTM/Contours/Ortho
Note on R410: Akhil Sharma: 2D vector 28/09 Others: 12/09
Note on S410: Akhil Sharma: Version 1 : 06/09 Version 1.1: 14/09 Version 1.2: 15/09
Note on R435: Shastry: Waiting for revised (as discussed in KOM) documents from ET
Note on V437: Shastry: Mail communication from customer
Note on K450: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on L450: Sujay L H: Remaining hours= colJ-colK
Note on M450: Sayak Chakraborty: Mention latest date Keep blank if input not received This cell will accept date from today to 150 days before
Note on N450: Sayak Chakraborty: Only use date format, if it is tentaive by mid of Oct. Mention 15-Oct-17 This cell will accept date from today to future 150 days
Note on O450: Sayak Chakraborty: This cell will accept date from today to 150 days before Keep blank if reception control not done for cases of future input It will give warning if reception control not doen within 7 days of input receipt
Note on Q450: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on R450: This cell will accept date from today to 150 days before
Note on S450: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on T450: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on Z450: Sayak Chakraborty: This cell will accept date from today to 150 days before
Note on AA450: Sayak Chakraborty: If CSS not sent/sent after 7 days of closure it will highlight This cell will accept date from today to 150 days before
Note on AB450: Sayak Chakraborty: If pending at client or receipt after 15 days it will highlight This cell will accept date from today to 150 days before
Note on AJ450: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on S454: Akhil Sharma: Version1: 13/06 Version2: 21/07 Version3: 10/08
Note on M455: Akhil Sharma: 26/07: Images, GCP's , Camera 15/08: Tiles
Note on Q455: Akhil Sharma: 26/07: AT 16/08: Ortho
Note on S455: Akhil Sharma: Version 1.2: 24/08 Version 1.3: 31/08
Note on P456: Akhil Sharma: Pending for 2D vector based on features list
Note on Q456: Akhil Sharma: 04/09: LiDAR/AT 14/09: DTM/Contours/Ortho
Note on R456: Akhil Sharma: Pending for 2D Vector only expected by 20/09
Note on S456: Akhil Sharma: Version 1 : 06/09 Version 1.1: 14/09 Version 1.2: 15/09
Note on M459: Naga Srinivasrao Pindi: Only inputs are received. No scope documents available and unable to start the production
Note on AC488: K.Murali Mohan Reddy: To COWI Norway
Note on J489: K.Murali Mohan Reddy: Flight line missing for on strip
Note on AC491: K.Murali Mohan Reddy: To COWI Norway
Note on K499: Sayak Chakraborty: Client corrections
Note on K500: Sayak Chakraborty: Client corrections
Note on H508: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on I508: Naga Srinivasrao Pindi: Total price of the project
Note on Q508: Naga Srinivasrao Pindi: Workflow and Guidelines available
Note on AJ508: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on AC513: Akhil Sharma: 2 Deliveries of Jul'17 not added in Aug Added Redelivery of Loch Lomond as we redelivered with new source
Note on AE513: Akhil Sharma: Added Loch Lomond redelivery feedback
Note on I520: M V V S Rao (Shastry): approximate value…will be updated later based on the extra ano count
Note on AC538: K.Murali Mohan Reddy: To COWI Norway
Note on AC541: K.Murali Mohan Reddy: To COWI Norway
Note on H555: Naga Srinivasrao Pindi: Planned Billable hours in a respective month
Note on I555: Naga Srinivasrao Pindi: Total price of the project
Note on Q555: Naga Srinivasrao Pindi: Workflow and Guidelines available
Note on AI555: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on I561: Shastry:Approximate value - actual value depends of number of ano+extra ano
Note on H562: Shastry: DTM - 2456 Ortho - 153
Note on H563: Naga Srinivasrao Pindi: 1500+1500, Remaining hours for the month of August 1378
Note on H565: Naga Srinivasrao Pindi: 1400+2400
Note on G583: K.Murali Mohan Reddy: Options are not included
Note on G584: K.Murali Mohan Reddy: Additional update approx 500 Buildingchange - 31 Hours - Not added New mapping FKB-C - 38 Hours - Not added
Note on G585: K.Murali Mohan Reddy: Hours calculation: Total-NOK/88
Note on G586: K.Murali Mohan Reddy: Not included for - "Full image coverage ordered for part of area"
Note on G587: K.Murali Mohan Reddy: Options are not included
Note on G588: K.Murali Mohan Reddy: Hours calculation: Total-NOK/88
Note on H602: Naga Srinivasrao Pindi: Remaining Billable hours
Note on Q602: Naga Srinivasrao Pindi: Workflow and Guidelines available
Note on AI602: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on I613: Shastry: Final price will be available after delivery as extra anomalies will be known after completion
Note on I620: Price for AT & additional hours sepnt on Ortho to be finalized by MADV & BEME:
Note on G635: K.Murali Mohan Reddy: Options are not included
Note on G636: K.Murali Mohan Reddy: Additional update approx 500 Buildingchange - 31 Hours - Not added New mapping FKB-C - 38 Hours - Not added
Note on G637: K.Murali Mohan Reddy: Hours calculation: Total-NOK/88
Note on G638: K.Murali Mohan Reddy: Not included for - "Full image coverage ordered for part of area"
Note on G639: K.Murali Mohan Reddy: Options are not included
Note on G640: K.Murali Mohan Reddy: Hours calculation: Total-NOK/88
Note on AI647: Naga Srinivasrao Pindi: Please mention your comment against delay and failure
Note on AD648: Deepa K.R: FB updaton
Note on I654: Shastry: AT hours to be included
Note on J657: Shastry: per unit price
Note on I664: Shastry: actual input differs from ATR
Note on J666: Shastry: may vary depends on the length that delivered
Note on O680: Manuj Dev: very small job
Note on S685: Naga Srinivasrao Pindi: 1662.9 KM can be invoiced by 20th April. Details shared with NASH/KLGA Another 1584KM invoice details given to NASH/KLGA on 23rd May
Note on S686: Naga Srinivasrao Pindi: 93KM details given to NASH/KLGA as a part of first invoice on 23rd May
Note on I694: K.Murali Mohan Reddy: Still some of the area AT is missing. Also need to estimate which is not estimated for extra mapping.
Note on M694: K.Murali Mohan Reddy: ATR not received for 8000 NOK and rest extra mapping.
Note on I696: K.Murali Mohan Reddy: Additional update approx 500 Buildingchange - 31 Hours - Not added New mapping FKB-C - 38 Hours - Not added
Note on I699: K.Murali Mohan Reddy: AT - 9 hours; Ortho - 66 hours are not added; Decision pending
Note on I704: K.Murali Mohan Reddy: AT hours are not included. These hours are including 30% profit.
Note on I705: K.Murali Mohan Reddy: AT hours are not included. These hours are including 20% profit.
Note on I706: K.Murali Mohan Reddy: AT hours are not included. These hours are including 35% profit.
Note on I707: K.Murali Mohan Reddy: AT hours are not included. These hours are including 20% profit.
Note on I708: K.Murali Mohan Reddy: AT hours are not included. These hours are including 50% profit.
Note on E743: Naga Srinivasrao Pindi: Billable hours/Services to be checked with MADV

## Sheet4
Year
Client Name
Project_Name
Servicelines
Service line count
PFM
PM
Current Status
CSS Sent Date
CSS feedback receipt date
Cust_resp_days
Customer type
NPS
Quality_score
Cost_score
Time_score
PM_score
Total_deliveries
Delayed_deliveries
Quality_feedback_on_delivery